## ADIF - April 22
IM | ID | Section | Direction | Line |  | Year |  | Week |  | Period from |  | Period to |  | Duration | Time of day | Reason for restriction | Traffic impact |  |  |  |  | Traffic measures |  |  |  |  | Description | International coordination | In yearly timetable | IM Project ID (Optional) | Last updated | Classification | Weekdays | Interval | Affected estimated travel volume | Affected border | Deviation location | Deviation border | Status | Additional information | Automatic process
|  |  |  | From | To | From | To | From | To | Date from | Time from | Date to | Time to |  |  |  | Total closure | Reduced Track Availability | Speed Restrictions | Weight, Length, Profile | Diesel only | Cancellation | Re-routing | Train replacement | Delay | Other
ADIF | 2019-1-002 | Madrid Chamartín – Aranjuez (Getafe Industrial - Pinto) | ambos | Madrid Chamartín | Valencia Nord | 2023 | 2023 |  |  | 3º trimestre 2023 |  |  |  |  | Banda de mantenimiento | Getafe Industrial-Pinto: sustitución de traviesas RS por PR-01 |  | x | x | [7 empty] | implantación de LTV.
ADIF | 2019-1-005 | San Cristobal Industrial-Aranjuez | ambos | Madrid Chamartín | Valencia Nord | 2021 | 2023 |  |  | 2021 |  | 1º trimestre 2023 |  | 21 meses | Banda de mantenimiento y cortes extraordinarios | Proyecto Constructivo de Instalaciones de Seguridad y Comunicaciones para la adaptación del Bloqueo Automático Banalizado en el tramo San Cristóbal – Aranjuez de la línea 300 Madrid Chamartín – Valencia Estació del Nord | x | x | x | [7 empty] | Puesta en servicio del BAB. Está prevista la puesta en explotación en cuatro fases, empezando por Aranjuez y acabando por San Cristóbal Industrial. La primera fase empezaría en el segundo trimestre del año 2022 y cada tres meses tendríamos una fase, con lo que se finalizaría en el primer trimestre del año 2023. Cada fase comprende un corte total a las circulaciones por trayectos en fin de semana. Una semana antes del fin de semana de la Puesta en Explotación se cortan vías 3 y 5 de Ciempozuelos. FIN DE SEMANA DE PUESTA EN EXPLOTACIÓN (1º FASE): NOCHE DE VIERNES A SÁBADO:  HORARIO DE 22:00 A 10:00 Corte de vía 1 entre Ciempozuelos y Aranjuez. (Entre señales de entrada) Vía 2 funcionamiento normal.  DE 10:00 DEL SÁBADO A 00:00 DEL DOMINGO: Circulación con Bloqueo Telefónico por vía 1 Circulación con Bloqueo Automático por vía 2  DE LAS 00:00 DEL DOMINGO HASTA LAS 4:30 DEL LUNES: Corte total entre Valdemoro y Aranjuez con carga de software en Aranjuez, Ciempozuelos y CTC de Chamartín. Una vez finalizada carga de software, Aranjuez admite trenes lado sur hasta estacionamientos.  A PARTIR DE LAS 4:30 DEL LUNES BAB ENTRE CIEMPOZUELOS Y ARANJUEZ POR AMBAS VÍAS
ADIF | 2020-1-004 | Vicálvaro Merc. | ambos | Vicálvaro Merc | Vicálvaro Merc | 2020 | 2024 |  |  | 2020-02-01 |  | 1º trimestre 2024 |  | 48 meses | Todo el día | Remodelación integral estación | x | x | x | [7 empty] | Consta de 4 fases constructivas, habiendo finalizado la primera 1A. Restantes fases: 1B: Modificaciones accesos desde San Fernando y Vicálvaro para homogeneizar rampas con la máxima de líneas de Barcelona y Levante/AndaluCía, varias modificaciones en configuración de vías generales y de contorno, así como enlace con O'Donnell. 1C: Construcción nuevo haz de tráfico intermodal de 4 vías para operar trenes de 750 ms. 1D: Construcción 6 nuevas vías haz de llegadas de más de 750 ms. Modificación de la posición de las vías generales y de contorno de forma agrupada, eliminación de PN actual.
ADIF | 2021-1-001 | Estación de Aranjuez | ambos | Madrid Chamartín | Valencia Nord | 2021 | 2022 |  |  | agosto 2021 |  | marzo 2022 |  | 7 meses | banda de mantenimiento | Obras de acccesibilidad en la estación de Aranjuez, continuación de las ya ejecutadas que se encontraban paralizadas. |  |  | x | [7 empty] | Trabajos en borde de anden y en marquesinas de andenes en banda de mantenimiento.Posibles LTVs.
ADIF | 2020-1-005 | Estación de Alcalá de Henares | ambos | Chamartin | BCN França | 2023 | 2024 |  |  | 2023-01-01 |  | septiembre 2024 |  | 20 meses | Nocturno | Obras del proyecto de ejecución de accesibilidad de la estación de Alcalá de Henares, y edificio de viajeros. | [10 empty] | Obras de remodelación de edificio de viajeros, normalización bordes de anden, mejoras en las marquesinas, ampliación paso inferior y construcción de ascensores para accesibilidad en vías 3-5. Trabajos en banda de mantenimiento.
ADIF | 2021-1-002 | Guadalaja- Ariza | ambos | Madrid Chamartín | Barna | 2023 |  |  |  | 2º semestre 2023 |  |  |  |  | todo el día | Obras relacionadas con la Autopista Ferroviaria Zaragoza Algeciras. Adaptación de galibos de tuneles. Racionalización de vías de estaciones y prolongación de vías de apartado a 750 ms e instalación BAB. Quedan operativas entre Guadalaja-Ariza: Apto Puerta Centro, Humanes, Jadraque, Baides (sin vías de apartado), Sigüenza, Torralba y Arcos de Jalón. | x | x | x | [7 empty] | Cortes permanentes puntuales. Pendiente de evaluación técnica del proyecto. SE INCORPORA EN ESTE PUNTO EL QUE APARECIA EN ANTERIORES LISTADOS DE REUNIONES CON EL Nº 2021-01-13 (QUE DESAPARECE) BAB GUADALAJARA-ARIZA, YA QUE LA EJECUCIÓN SERA CONJUNTA.
ADIF | 2021-1-007 | Alcázar-Manzanares | ambos | Alcázar de San Juan | Cadiz | 2022 | 2025 |  |  | 4º trimestre 2022 |  |  |  | 36 meses | Banda de mantenimiento y cortes extraordinarios | Instalación previa del BAB y sustitución enclavamiento de Manzanares. Posteriormente corte principal entre Herrera-Manzanares con actuación en vía y electrificación, con nueva variante, así como renovación completa de la estación de Herrera. Actuaciones de menor envergadura que quedaban pendientes de este proyecto en resto de trayectos. | x | x | x | [7 empty] | Primeros 6 meses sustitución enclavamiento de Manzanares y dotación BAB en trayecto, necesario algún corte extraordinario de fin de semana por definir. Restantes 30 meses, trabajos que quedaron pendientes en anterior actuación, teniendo especial relevancia el corte de una de las dos vías entre Herrera-Manzanares durante un período aún por definir, que sería la mayor parte de esta fase, teniendo una sola vía de circulación en dicho trayecto.
ADIF | 2021-1-008 | Aranjuez | ambos | Madrid Chamartín | Valencia Nord | 2023 | 2023 |  |  | 2023 |  | 2023 |  | 12 meses | Banda de mantenimiento y un corte extraordinario de 12 horas | Rehabilitación de catenaria con sustitución del hilo de contacto y sustentador en la cabecera lado Madrid y zona centro de la estación de Aranjuez | x | x | [8 empty] | Banda de mantenimiento y un corte extraordinario de 12 horas para sustitución pórticos sobre rio Tajo
ADIF | 2021-1-011 | Guadalajara | ambos | Chamartin | BCN França | 2023 | 2023 |  |  | 2º trimestre 2023 |  | 3º trimestre 2023 |  | 4 meses | Banda de Mantenimiento y cortes extraordinarios | Remodelación de vías toperas 4 a 10 de Guadalajara, prolongación vías 4-6-8 y renovación de vía, desvios y electrificación de dicha zona. |  | x | [8 empty] | Banda de Mantenimiento y cortes extraordinarios afectando solo a vías toperas secuencialmente.
ADIF | 2021-1-015 | Guadalajara-Bif. Rebolledo y O'Donnell | ambos | Chamartin | BCN França | 2022 | 2024 |  |  | 2º trimestre 2022 |  | 2024 |  | 24 meses | Banda de mantenimiento y posibles cortes extraordinarios sin definir | Renovación señalización en la red de cercanías zona noreste. Sustitución de los enclavamientos entre Guadalajara-Bif. Rebolledo y O'Donnell | x | x | [8 empty] | Banda de mantenimiento y posibles cortes extraordinarios Pendiente la firma del contrato.
ADIF | 2021-1-020 | Estación de Pinto | ambos | Chamartín | Valencia Nord | [8 empty] | 21 meses | Banda de mantenimiento y posibles cortes extraordinarios sin definir | Construcción nuevo apeadero de La Tenería | x | x | x | [7 empty] | Trabajos por fases, en banda de mantenimiento cuando tenga afectación al tráfico. Modificación en vía e II.SS en acceso a la DP Citroen.
ADIF | 2021-1-023 | Estación de Valdepeñas | ambos | Alcazar | Cádiz | 2022 | 2022 |  |  | 3º trimestre 2022 |  | 4º trimestre 2022 |  | 5 meses | todo el dia | construcción paso inferior |  | x | x | [7 empty] | Fases constructivas: Fase 1 (1.5 meses): trabajos con afectación al tráfico en BM (afectación tráfico mercancías). Fases 2 y 3 (3.5 meses) corte de vía 1 para construcción paso inferior y embocaduras. Circulación por vía 2.
ADIF | 2019-3-006 | San Pablo - Almoraima (p.k. 129/400 al 155/438) | ambos | Bif. Las Maravillas | Algeciras | 2019 | 2022 |  |  | 2019-05-01 |  | 1º trim. 2022 |  | 31,5 meses | - | Renovacion del tramo San Pablo - Almoraima (línea Bobadilla - Algeciras), entre los p.k. 129/400 y 155/438 |  |  | x | [7 empty] | Obras realizadas al amparo de TBA. No va a necesitar corte de vía (SO Sur).
ADIF | 2020-3-010 | Ampliación de la longitud útil de vía a 750 m en los apartaderos de Campillos y Setenil, del tramo Bobadilla – Algeciras |  | Bobadilla | Algeciras | 2021 | 2024 |  |  | 2º trimestre 2022 |  | 4º trimestre 2023 |  | 19 meses |  | Ampliación de vías de apartado a 750 m de longitud útil en las estaciones de Campillos y Setenil. |  | x | [8 empty] | Trabajos en BM + otros intervalos que pueda conceder el PM. Necesidad de CVE en distintas fases de obra y de distinta duración. 2022 Estación de Campillos: Fase 2 JUNIO CVE (3 días), OCTUBRE Fase 4 CVE (1 día). 2023 Estación de Setenil: Fase 2b MARZO (8 horas), Fase 3 JUNIO (2 días) y Fase 4 JULIO (8h).
ADIF | 2021-3-028 | Espeluy-Lora del Río |  |  |  | 2022 | [9 empty] | SUSTITUCIÓN DE CARRIL INÚTIL T/ESPELUY-LORA DEL RÍO. OBRA
ADIF | 2021-3-032 |  |  | Bobadilla | Ronda | 2023 | 2023 | [6 empty] | 4 meses |  | TRATAMIENTO DE LA LADERA DE ALMARGEN. TRAYECTO ALMARGEN - SETENIL
ADIF | 2022-3-001 | Jimena de la Frontera |  | Bif. Las Maravillas | Algeciras | 2022 | 2023 |  |  | 2022-11-01 |  | 01/12/2023 |  |  |  | Actuación integral en playa de vías y andenes de Jimena de la Frontera y reposición de pasos superiores por gálibos para electrificación futura | x | x | [8 empty] | Trabajos en BM + otros intervalos que pueda conceder el PM. Necesarios varios cortes de vía total (rebaje de plataforma y desvíos en vía general, y zonas de Paso Superiores) y corte de circulación por fases en las vías de Jimena. Coordinación con las obras de CMS. Cortes de vía total: *8h. Paso Sup (sept-22) *83h. Rebaje de plataforma y PS (nov 2022) *12h desvio 2 y PS (dic-22) *8h. Paso Sup (feb -23) *12h Desvío 1 (mayo-23) Cortes de vía general y auxiliares para la renovación por fases SIN corte total de circulación (enero/mayo 2023)
ADIF | 2022-3-002 | Campillos-Setenil |  | Bif. Las Maravillas | Algeciras | 2023 | 2024 |  |  | 2023-01-01 |  | feb-24 |  |  |  | EJECUCIÓN DE LAS OBRAS DE AMPLIACIÓN DE LA LONGITUD A 750 METROS DE LOS APARTADEROS DE CAMPILLOS Y SETENIL EN EL TRAMO BOBADILLA-RONDA | x | [9 empty] | 05/11/2021: Trabajos en BM + otros intervalos que pueda conceder el PM. Necesidad de CVE en distintas fases de obra y de distinta duración. Estación de Campillos: Fase 2 Enero 2023 CVE (3 días), Fase 4 Mayo 2023 CVE (1 día). Estación de Setenil: Fase 2b Noviembre 2023 (8 h) Fase 3 Enero 2024 CVE (2 días) Fase 4 Febrero 2024 (8h)
ADIF | 2022-3-004 | Calancha-Vilches |  |  |  | 2023 |  |  |  | 2021-11-01 |  | jun-23 |  |  |  | ACTUACIÓN CORRECTORA TUNEL 10 |  | x | [8 empty] | Se ha solicitado TBP del 7 al 31 de Marzo del 2022 con el que se amplía la BM.
ADIF | 2019-4-003 | 50: La Encina - Xàtiva | ambos | MADRID-CHAMARTIN | VALENCIA-NORD | 2022 | 2022 |  |  | nov.-22 |  | nov.-22 |  | 1 mes | Nocturno | Puesta en servicio de la L340 (nuevo trazado en vía única de la L300) en ASFA . Posteriormes PeS con ERTMS N1. | x | x | [8 empty] | Conexión entre la L300 y la L340 en la zona del Nudo de La Encina => implica el corte de una de las dos vías generales entre La Encina y PB La Font de la Figuera durante aproximadamente una mes antes de la puesta en servicio con solicitud de corte nocturno de ambas vías en el intervalo más amplio posible Conexión entre la L300 y la L340 en la zona de Xàtiva => implica el corte de una de las dos vías generales entre Xàtiva y Bif. Vallada durante aproximadamente 2 semanas antes de la puesta en servicio Previamente será necesario un corte de 7 meses en L340 (actuación con ref: 2021-4-014) Posteriormente se cortará la L300 desde el desvío de conexión en La Encina hasta Xàtiva para ejecutar la obra de cambio de ancho a 1435mm e integrarlo en la red de Adif AV
ADIF | 2019-4-004 | 50: La Encina - Xàtiva | ambos | MADRID-CHAMARTIN | VALENCIA-NORD | 2022 | 2024 |  |  | 2º semestre 2022 |  | 1º semestre 2024 |  | 22 meses | completo | Ejecución de obra de cambio de ancho de Xàtiva al nudo de La Teja. Las fechas contempladas prevén la puesta en servicio de la L340 en ASFA, en caso de considerar las fechas de puesta en servicio en ERTMS, sería necesario retrasar las fechas de comienzo y fin aproximadamente un año y medio. Relacionado con 2021-4-014 | x | [9 empty] | Cambio de ancho con corte total entre Xàtiva y el desvío de conexión con la L340 Previsto comenzar diciembre de 2.022. al finalizar los trabajos del 2021-4-014, se dará de baja el trazado actual de vía doble de la línea 300 entre Xàtiva y La Encina, y se pasará a circular por el nuevo trazado en vía única.
ADIF | 2019-4-006 | 60: Xàtiva - Silla | ambos | MADRID-CHAMARTIN | VALENCIA-NORD | 2021 | 2023 |  |  | Abril 2021 |  | dic-23 |  | 30 meses | Nocturno | Trabajos para renovación de vía y catenaria Las IISS se renovarán con la actuación prevista con ref: 2021-4-004 |  | x | x | [7 empty] | Previsto iniciar trabajos en estaciones en la segunda mitad del 2022: - Enero 2022 - Diciembre 2023: Bandas de mantenimiento 2 vías de 6/8 h - Noviembre 2022 - Diciembre 2022: Corte que afectará puntualmente a diversas estaciones - LTV móviles a 30 y 80km/h
ADIF | 2019-4-016 | 10: Valencia Nord - Sagunt | ambas | VALENCIA-NORD | CAMB. LA BOELLA | 2020 | 2023 |  |  | may.-20 |  | jun.-23 |  | 36 meses | Nocturno | Trabajos de adaptación de la electrificación al ancho mixto entre Bif. Puerto FSL y Sagunt. |  | x | x | [7 empty] | Corte de 23:40 a 5:40 de vía y tensión de ambas vías entre Bif. Puerto y Sagunt, afectando a 2 trayectos máximo, se restablecerá la circulación por una vía previa coordinación con el PM para facilitar el paso de trenes. LTV móvil a 30km/h en 1000m durante 2 días, pasando a 80km/h durante 2 semanas RESTRICCIONES A LA CIRCULACIÓN DURANTE LOS TRABAJOS De lunes a viernes de 23:40h a 05:40h corte de vía y tensión en una de las dos vías entre Bif. Puerto Cabanyal y Sagunt, garantizando siempre un encaminamiento posible para la circulación de los trenes por el tramo afectado.
ADIF | 2019-4-017 | 10: Valencia Nord - Sagunt | ambas | VALENCIA-NORD | CAMB. LA BOELLA | 2022 | 2023 |  |  | 2021-11-01 |  | abr-23 |  | 18 MESES | - | Enlace en ancho mixto entre las estaciones de Almussafes y Valencia FSL Relacionado con 2019-4-018 |  |  | x | [7 empty] | Sin afectación más allá de la derivada de la puesta en servicio de esta nueva línea
ADIF | 2019-4-018 | 10: Valencia Nord - Sagunt | ambas | VALENCIA-NORD | CAMB. LA BOELLA | 2022 | 2024 |  |  | 2º semestre 2022 |  | 2º semestre 2024 |  | 30 MESES | - | Conversión a ancho mixto la estación de Valencia FSL | x | x | x | [7 empty] | Ampliación de banda de mantenimiento a partir del segundo semestre de 2.022 en la cabecera norte de la estación de Sant Lluis. A lo largo del 2.023 se planificarán las vías generales con Alboraia y cortes puntuales en la terminal
ADIF | 2019-4-019 | 30: Castelló - L'Aldea-Amposta | ambas | VALENCIA-NORD | CAMB. LA BOELLA | 2022 | 2024 |  |  | 1º semestre 2022 |  | 1º semestre 2025 |  | 8 horas | Nocturno | Cambio de ancho a UIC entre Castellò y Vinaròs |  | x | x | [7 empty] | Trabajo nocturnos con ampliación del horario de la Banda de Mantenimiento (8 horas) y cortes puntuales en fines de semana entre estaciones. Para ejecutar el cambio de ancho está previsto realizarlo en una vía y posteriormente en la otra. Se deben planificar las fechas de cambio de ancho, tanto con las EF como con los trabajos de las actuaciones colaterales Relacionado con obra 2019-4-020
ADIF | 2019-4-020 | 30: Castelló - L'Aldea-Amposta | ambas | VALENCIA-NORD | CAMB. LA BOELLA | 2022 | 2023 |  |  | 2022-04-01 |  | 01/12/2023 |  | 8 horas | Nocturno | Cambio de ancho a UIC entre Vinaròs y Tortosa - L'Aldea - Vandellòs |  | x | x | [7 empty] | Bandas de mantenimiento de 6/8 horas en diversas vías (Abril 2022-Diciembre 2023).
ADIF | 2019-4-021 | 40: L'Aldea - Amposta - Camb. La Boella | ambas | VALENCIA-NORD | CAMB. LA BOELLA | 2023 | 2024 |  |  | 2ª semestre 2023 |  | 1º semestre 2025 |  | 8 horas | Nocturno | Cambio de ancho a UIC entre Vandellòs y el cambiador de La Boella |  | x | x | [7 empty] | Trabajo nocturnos con ampliación del horario de la Banda de Mantenimiento (8 horas) y cortes puntuales en fines de semana entre estaciones. Para ejecutar el cambio de ancho está previsto realizarlo en una vía y posteriormente en la otra. Se deben planificar las fechas de cambio de ancho, tanto con las EF como con los trabajos de las actuaciones colaterales
ADIF | 2019-4-025 | 20: Sagunt - Castellò de la Plana | ambas | VALENCIA-NORD | CAMB. LA BOELLA | 2020 | 2022 |  |  | ene.-21 |  | jun.-23 |  | 6 horas | Nocturno | Trabajos de adaptación al ancho estándar de la vía I entre Sagunt y Castellò (relacionado con id 2022-4-004) Electrificación trayecto Sagunt - Castellò, vía 2 y vías de apartado pares de Sagunt, Almenara, Moncofar, Burriana y Villarreal (relacionado con id 2022-4-001) Ampliación de plataforma de vías 4 y 6 de Sagunt para acondicionar futuro acceso al Puerto Ampliación de plataforma en vías 3 y 4 de Almenara y Burriana para adaptarlas a trenes de 750m Adaptación de catenaria en la estación de Castellón (prevista entre Junio y Octubre 2022) (ver id 2022-4-003) |  | x | x | [7 empty] | Cortes de 23:50 a 5:50 de vía y tensión de ambas vías entre Sagunt y Castellò, afectando a 2 trayectos máximo, se restablecerá la circulación por una vía previa coordinación con el PM para facilitar el paso de trenes. Se establecerá LTV móvil a 30km/h en 1000m durante 2 días, pasando a 80km/h durante 2 semanas. Restricciones al estacionamiento durante la adaptación de la catenaria en la estación de Castellón
ADIF | 2020-4-004 | Murcia Mercancías - Murcia del Carmen |  | CHINCHILLA | CARTAGENA | 2022 |  |  |  | 2022-02-01 |  | feb-25 |  | 36 meses | Dia completo | Obras del tramo Plataforma Nonduermas-Sangonera en Alcantarilla y soterramiento de Murcia | x | [9 empty] | Corte total de la línea 320 entre Murcia del Carmen y Murcia Mercancías
ADIF | 2020-4-007 | San Isidro-Murcia | única | MURCIA | SAN ISIDRO | 2025 | 2026 | [6 empty] | 12,5 meses | Dia completo | Cambio de ancho tramo Murcia - San Isidro (Línea Alta Velocidad 046 Monforte del Cid - Murcia), dando de baja la línea L336 de cercanías entre ambas estaciones. Aprobada modificación del contrato (29/12/2020), incluyendo los trabajos correspondientes de catenaria y una estructura de refuerzo en PS en Beniel. | x | [9 empty] | Duración total: 12,5 meses. Realización de trabajos en corte total. Este cambio de ancho no se va a realizar hasta que esté finalizado y en servicio el soterramiento de Murcia.
ADIF | 2020-4-013 | 40: L'Aldea - Amposta - Camb. La Boella | Ambas | VALENCIA-NORD | CAMB. LA BOELLA | 2021 | 2021 |  |  | 2º semestre 2022 |  | 2º semestre 2022 |  | 5 horas | Nocturno | Prolongación ERTMS N1 desde L'Hospitalet hasta L'Ametlla | x | [9 empty] | Corte total nocturno para conseguir al menos intervalos de 5 horas seguidas de prueba
ADIF | 2021-4-002 | 60: Xàtiva - Silla | ambos | MADRID-CHAMARTIN | VALENCIA-NORD | 2022 | 2023 |  |  | 2022-01-01 |  | dic-23 |  | 5 fines de semana | Nocturno | Obras de Drenaje Transversal | x |  | x | [7 empty] | Enero 2022 - Diciembre 2023: Banda de Mantenimiento con intervalo adicional 6/8 h para BLAU 2023: 5 Cortes puntuales en fin de semana para colocar una serie de obras de drenaje bajo vía
ADIF | 2021-4-004 | Valencia - La Encina | Ambas | MADRID-CHAMARTIN | VALENCIA-NORD | 2021 | 2023 |  |  | 3er trim 2021 |  | 4º trimestre 2023 |  | 26 meses | Nocturno | Actualización de instalaciones de seguridad del tramo nudo La Encina - Xàtiva - Valencia |  | x | [8 empty] | Se establecerán 4 zonas de actuación: - La Encina - Xàtiva: sin afectación al tráfico entre Moixent y La Encina. Con afectación entre Moixent y Xàtiva que coincidirá con la actuación con ref 2021-4-014 - Xàtiva - Benifaió: afectación coincidente con la actuación con ref 2019-4-006 - Silla: pendiente de definir afectación - Silla - Alfafar: pendiente de definir afectación
ADIF | 2021-4-012 | Bif. Alicante - La Encina | Única | LA ENCINA | ALACANT TERMINAL | 2025 | - |  |  | - |  | - |  | - | - | Obras de implantación de tercer carril La Encina a Bif Alicante. | [10 empty] | -
ADIF | 2021-4-013 | Alacant Terminal | Estación | LA ENCINA | ALACANT TERMINAL | 2023 | 2025 |  |  | 4º trim 2023 |  | 3º trim 2025 |  | 18 meses | completo | Ampliación playas de vía ancho estandar (actualmente en proyecto) |  | x | [8 empty] | Reducción de número de vías en 1668mm disponibles en Alacant Terminal
ADIF | 2021-4-014 | Moixent-Xàtiva | única | MOIXENT | XATIVA-AG.KM.47 | 2022 | 2022 |  |  | may.-22 |  | dic.-22 |  | 7 meses | completo | Actuaciones para adaptar la L340 al tráfico de la L300 por el futuro desvío por ella. El restablecimiento entre Moixent y La Encina requiere resolución de la AESF para proceder a la Puesta en Servicio. Tras la puesta a disposición de la infraestructura (prevista para finales de Septiembre '22), se darán 2 meses para formación de maquinistas. Relacionado con 2019-4-004 | x | [9 empty] | Corte total de la L340 para la adaptación de la cabecera de la estación de Xàtiva en la cabecera del lado "La Encina" Previsiblemente el corte será del 15/05/2022 hasta el 24/11/2022. Se está gestionando el TBP
ADIF | 2021-4-017 | Vila-Real - Castelló de la Plana | ambas | VALENCIA-NORD | CAMB. LA BOELLA | - | - |  |  | - |  | - |  | - | - | Acceso al puerto de Castelló |  |  | x | [7 empty] | -
ADIF | 2021-4-018 | El Reguerón-Murcia del Carmen | ambas | CHINCHILLA | CARTAGENA | 2022 | 2022 |  |  | 3º trimestre 2022 |  | 4º trimieste 2022 |  | 6 meses | nocturno | Línea afectada por la PeS del tramo de AV Beniel-Murcia del Carmen, de la L046 (en ASFA+ERTMS N2), tramo tercer carril | [10 empty] | -
ADIF | 2021-4-019 | Valencia Nord - L'Ametlla de Mar | ambas | VALENCIA-NORD | CAMB. LA BOELLA | - | - |  |  | - |  | - |  | 12 meses | Nocturno | Implantación ERTMS N1 Valencia Nord - L'Ametlla |  | x | [8 empty] | Corte nocturno en hoario ampliado a la banda de mantenimiento
ADIF | 2021-4-022 | La Roda - Villarrobledo | ambas | MADRID-CHAMARTIN | VALENCIA-NORD | 2023 | 2024 |  |  | 2º semestre 2023 |  | 2º semestre 2024 |  | 18 meses | - | Implantación BAB La Roda - Villarrobledo | x | x | [8 empty] | Ampliación de horario de la banda de mantenimiento y cortes puntuales de poca afectación para durante las fases de pruebas y cambios de enclavamientos. (En fase de proyecto)
ADIF | 2022-4-001 | Sagunt | ambas | VALENCIA-NORD | CAMB. LA BOELLA | - | - |  |  | jun.-22 |  | mar.-23 |  | - | Nocturno | SAGUNT: Adaptación de desvíos de la estación al ancho mixto |  | x | x | [7 empty] | Restricciones al estacionamiento de trenes en vías pares o impares según el transcurso de la obra Corte de continuidad del ancho 1435mm entre Valencia y Castelló durante 9 semanas Imposibilidad de acceso a la terminal de Sagunto Cargas directamente desde uno de los lados de la estación (Puçol o Almenara) alternativamente según el transcurso de la obra
ADIF | 2022-4-003 | Castellò | ambas | VALENCIA-NORD | CAMB. LA BOELLA | 2022 | 2022 |  |  | jun.-22 |  | Sept.-22 |  | 6 horas | Nocturno | CASTELLÒ: Electrificación (adpatación al ancho mixto) |  | x | x | [7 empty] | Restricciones al estacionamiento de trenes en vías pares o impares de la estación durante el desarrollo de las obras. Junio 2022 - Septiembre 2022: Cortes puntuales en vías de apartado y BM entre 6 y 8 h en diversas vías
ADIF | 2022-4-004 | Valencia - Castellò | ambas | VALENCIA-NORD | CAMB. LA BOELLA | 2022 | 2022 |  |  | ene.-22 |  | dic.-22 |  | 6 horas | Nocturno | VALENCIA-CASTELLO: Instalación de tercer carril |  | x | x | [7 empty] | Afección dentro de las previstas por la actuación con id 2019-4-025
ADIF | 2022-4-005 | MOREDA - ALMERÍA | ambas | LINARES BAEZA | ALMERÍA | 2023 | 2026 |  |  | 2trimestre 2023 |  | 1905-07-18 |  | 36 meses | - | PROYECTO DE CONSTRUCCIÓN DE LA INTEGRACIÓN DEL FERROCARRIL EN ALMERÍA | x | [9 empty] | Corte total del servicio de la Línea 410, Linares Baeza-Almería tramo Moreda-Almería durante aproximadamente 36 meses. Las afecciones se prevén desde el 2T 2023 hasta el 4T 2026, incluido
ADIF | 2022-4-006 | TORRE PACHECO - CARTAGENA | ambas | MURCIA | CARTAGENA | 2023 |  |  |  | 1 TRIMESTRE 2023 | [5 empty] | PROYECTO CONSTRUCCIÓN DE PLATAFORMA. CONEXIÓN MURCIA-CARTAGENA. RIQUELME-CARTAGENA. TRAMO: TORRE PACHECO-CARTAGENA | X | [9 empty] | Afecciones en estudio, similares a las comentadas para el PC Riquelme-Torre Pacheco a la Línea 320 Chinchilla-Cartagena (trabajos en Banda de Mantenimiento con intervalo adicional durante varios meses y 3-4 cortes puntuales de 2 días, fechas exactas de afección por determinar, serán en 2024 y 2025).
ADIF | 2019-5-001 | Castellbisbal – Martorell Seat | ambos | S.V. Calders | L'Hospitalet de Llobregat | 2019 | 2023 |  |  | 2020-05-01 |  | sep-23 |  | 40 meses | - | Implantación del tercer carril en el Corredor Mediterráneo en el tramo Castellbisbal – Martorell, | x | x | x | [7 empty] | Intervalos extraordinarios nocturnos y fines de semana. Limitaciones de velocidad según avance de los trabajos. Establecimiento de vía única entre 8 y 10 meses entre Castellbisbal-Martorell tras la puesta en servicio del ramal de Costablanca en el 1er trimestre del 2022. Se prevee vía unica(1) dCW-MR a determinar en función de autorización de la puesta en servicio del tunel de Costablanca. Previsión de corte de 3 semanas Seat estación en agosto 22.
ADIF | 2019-5-002 | Martorell - S. Vicenç de Calders | ambos | S.V. Calders | L'Hospitalet de Llobregat | 2018 | 2022 |  |  | 2018-03-01 |  | sep-22 |  | 54 meses | - | Implantación del tercer carril en el Corredor Mediterráneo en el tramo Martorell Seat - Sant Vicenç Calders | x | x | x | [7 empty] | Intervalos extraordinarios nocturnos y fines de semana. Limitaciones de velocidad según avance de los trabajos. La próxima actuación está prevista en La Granada, construción de paso inferior y nueva configuración de vías. Empezará en torno al primer cautrimestre 2022 (abril 2022), y se prolongará a lo largo del año 2022. Afectaciones: vías únicas entre Vilafranca y Sant Sadurni (en el fin de semana necesidad de corte hasta el triángulo de Seat). En función de las fases de obra, pasos por una sola vía y desviada, dentro de la estación. Tambien se ha de realizar una actuación similar en L' Arboç, con afectación similar pero pendiente de definir las fases. A continuación vía única entre Vilafranca y St. Vicenç durante 4+4 meses aproximadamente para acometer la instalación del tercer carril y finalmente corte en la estación de St. Vicenç de Calders durante 5 meses para la implantación del tercer carril, ripados de vías e instalación de aparatos de 3 hilos.
ADIF | 2019-5-003 | Bif. Vilaseca - Tarragona | ambos | Miraflores | Sant Vicenç de Calders | 2013 | 2023 |  |  | 2014-09-01 |  | 01/09/2022 |  | 96 meses | - | Implantación del tercer carril en el Corredor Mediterráneo en el tramo Bif. Vilaseca - Tarragona | x | x | x | [7 empty] | Intervalos extraordinarios nocturnos y fines de semana. Previsión instalación aparato de dilatación y encarriladora del viaducto metálico del río Francolí en febrero 2022 (en ejecución). Se realizó el cambio de enclavamiento en septiembre en Tarragona Clasificación y se continuará con los trabajos de levante de desvíos antigüos e instalación de cambiadores de hilo en marzo 2022 (en ejecución). En mayo 2022, previsión de instalar los aparatos mixtos de la estación de Alftafulla. Posteriormente se programará el corte de la vía de Salou entre Tarragona y el acceso al Puerto de Tarragona en Tarragona clasificación para el verano 2022 para acondicionamiento del viaducto metálico del río Francolí y la instalación de aparato de dilatación y encarriladora del lado Reus.
ADIF | 2019-5-004 | Sant Vicenç de Calders - Tarragona | ambos | Miraflores | Sant Vicenç de Calders | 2013 | 2023 |  |  | 2014-09-01 |  | may-2024 |  | 116 meses | - | Implantación del tercer carril en el Corredor Mediterráneo en el tramo Sant Vicenç Calders - Tarragona | x | x | x | [7 empty] | Intervalos extraordinarios nocturnos y fines de semana. Limitaciones de velocidad según avance de los trabajos. Pendiente programación corte total de mínimo 8-10 semanas entre Sant Vicenç de Calders y Tarragona para ejecución túnel Roda de Bará y las estación de Torredembarra y la cabecera lado Barcelona de Tarragona. Se retrasa su inicio al 4 trimestre 2023.
ADIF | 2019-5-006 | Maçanet – Bif. Sagrera (Mollet Sant Fost) | ambos | Cerbere | Bif. Aragó. | 2022 | 2023 |  |  | 2º trim. 2022 |  | 4º trim. 2023 |  | 16 meses | - | Recrecido de andenes, ripado de vía y catenaria en vía 4 y construcción de paso inferior en Mollet Sant Fost |  | x | x | [7 empty] | Limitaciones de velocidad y corte de las dos vías generales un fin de semana.
ADIF | 2019-5-009 | Villanueva de Gállego-Almudevar | ambos | Madrid-Chamartín | Barcelona Est. França | 2022 | 2023 |  |  | 2º sem. 2022 |  | 2º sem. 2023 |  | 24 meses |  | Mejora de la plataforma y corrección asentamientos. | x | x | x | [7 empty] | Intervalo extraordinario para obra mejora plataforma (previsto corte 1 mes en agosto 2022 en el ramal de Zuera, líneas 070 y 200). Pendiente licitación. Tanto la obra de convencional como la de Alta velocidad la va a ejecutar Alta Velocidad. Incompatible con los trabajos del túnel de Bara.
ADIF | 2019-5-011 | Girona - Maçanet (Caldes de Malavella - Maçanet Massanes) | ambos | Cerbere | Bif. Aragó. | 2021 | 2023 |  |  | 3 trim 2021 |  | 3 trim 2023 |  | 24 meses | Cortes fin de semana/ Cortes nocturnos | Renovación integral de catenaria Maçanet-Caldes 505/20 BA TBP-1 FECHAS: 22/02/21 al 23/12/21 Renovación integral de la catenaria de ambas vías generales del trayecto Maçanet - Caldas |  | x | x | [7 empty] | Intervalo Extraordinario en periodo nocturno afectando a una vía con cortes especiales en fin de semana para trabajos en estaciones 505/20 BA TBP-1 Del 22/02/21 al 23/12/21 : corte de vía entre Maçanet y Caldas de Malavella. Noches de Lunes a Viernes : De 23.30h. a 05.00h. ( Vía 1 ó 2, indistinta según avance de los trabajos ). Noche Sáb./Dom . : 23.15h. a 06.00h. ( Corte de vía 1 y 2 ). Noche Dom./Lun. : 23.15h. a 04.15h. ( Corte de vía 1 y 2 ). En estudio la posibilidad de ampliar los cortes.
ADIF | 2019-5-012 | Girona - Maçanet (Caldes de Malavella - Maçanet Massanes) | ambos | Cerbere | Bif. Aragó. | 2022 | 2024 |  |  | 1 er trm 2022 |  | 3 trim. 2024 |  | 32 meses | Intervalo extraordinario en periodo nocturno | BAB Maçanet-Girona |  | x | x | [7 empty] | Restricción de capacidad con corte puntual extraordinario en fin de semana. Intervalos nocturnos afectando a ambas vías por actuación en los ENCEs.
ADIF | 2019-5-013 | Girona - Figueres | ambos | Cerbere | Bif. Aragó. | 2022 | 2023 |  |  | 2º trm 2022 |  | 2º trm 2023 |  | 12 meses | Intervalo extraordinario en periodo nocturno | Renovación de Catenaria Girona-Figueres. Via Par |  | x | x | [7 empty] | Intervalo Extraordinario en periodo nocturno efectando a una vía con cortes especiales en fin de semana para trabajos en estaciones. Incompatible con el siguiente punto, Figueres-Portbou. Necesario programar en fechas distintas.
ADIF | 2019-5-014 | Figueres - Portbou | ambos | Cerbere | Bif. Aragó. | 2022 | 2023 |  |  | 1º trim 2023 |  | 1º trim 2024 |  | 12 meses | Intervalo extraordinario en periodo nocturno | Renovación de Catenaria Figueres-Portbou |  | x | x | [7 empty] | Intervalo Extraordinario en periodo nocturno efectando a una vía con cortes especiales en fin de semana para trabajos en estaciones. Incompatible con el punto anterior, Girona-Figueres. Necesario programar en fechas distintas.
ADIF | 2019-5-031 | S.V. Calders | ambos | S.V. Calders | L'Hospitalet de Llobregat | 2022 | 2022 |  |  | Pte. Licitacion |  |  |  | 5 meses | Intervalo extraordinario en periodo nocturno | Sustitución de desvíos en la estación de sant vicenç de calders. Se retrasa actuación por tener que modificar el proyecto a la nueva situación. |  | x | x | [7 empty] | Limitaciones de velocidad. Intervalo Extraordinario en periodo nocturno con cortes especiales en fin de semana para trabajos en estaciones
ADIF | 2019-5-032 | S.V. Calders | ambos | S.V. Calders | L'Hospitalet de Llobregat | 2022 | 2022 |  |  | Pte. Licitacion |  |  |  | 5 meses | Intervalo extraordinario en periodo nocturno | Adecuacion de las instalaciones de seguridad en la estacion de sant vicenç de calders. Se retrasa actuación por tener que modificar el proyecto a la nueva situación. |  | x | x | [7 empty] | Limitaciones de velocidad. Intervalo Extraordinario en periodo nocturno con cortes especiales en fin de semana para trabajos en estaciones
ADIF | 2020-5-001 | Estacion Tardienta |  | Chamartin | BCN Estacion França | 2021 | 2022 |  |  | 4º trimestre 2021 |  | 2on semestre del 2022 |  | 10 meses |  | Obras del proyecto contructivo de accesibilidad en la estación de Tardienta, Huesca | [10 empty] | Recrecido de andenes. Trabajos en banda de mantenimiento con algún corte puntual.
ADIF | 2020-5-006 | PLANA DE PICAMOIXONS- VALLS |  | MADRID-CHAMARTIN | BARNA-EST. DE FRANÇA | 2022 | 2022 |  |  | 1 trim 2023 |  | 2 trim 2023 |  | 5 MESES |  | PK1+308 Rehabilitación de la bóveda del túnel de Picamoixons, adecuación de gálibo, impermeabilización, mejora de drenaje y tratamiento emboquilles. L10-4 |  | x | x | [7 empty] | Banda de mantenimiento extendida nocturna y fines de semana (con TBA). Posible implantación de LTV. Se intentará coordinar el corte total con el resto de obras de la Línea
ADIF | 2020-5-007 | SALOMÓ - RODA DE BARÀ |  | MADRID-CHAMARTIN | BARNA-EST. DE FRANÇA | 2022 | 2022 |  |  | 1 trim 2023 |  | 2 trim 2023 |  | 2,25 meses |  | PK25,663 TÚNEL. Rehabilitación de la bóveda del túnel de Mas d'en Soté, adecuación de gálibo, impermeabilización, mejora de drenaje y tratamiento emboquilles. |  | x | x | [7 empty] | Banda de mantenimiento extendida nocturna y fines de semana (con TBA). Posible implantación de LTV. Se intentará coordinar el corte total con el resto de obras de la Línea
ADIF | 2020-5-008 | Salomo Svicente Calders |  | MADRID-CHAMARTIN | BARNA-EST. DE FRANÇA | 2023 | 2024 |  |  | 4 trim 2023 |  | 1 trim 2024 |  | 2 MESES |  | pk611+930 VIADUCTO. Trabajos ejecución Losa de reparto bajo las vías y balasto actuales. Viaducto Roda de Barà. L7-9 | x | x | x | [7 empty] | Corte total 3 semanas. Posible implantación LTV. Posible coordinación del corte total con otros viaductos de la línea. Se intentará coordinar el corte total con el resto de obras de la Línea
ADIF | 2020-5-011 | MORA LA NOVA - REUS |  | MIRAFLORES | S.VICENÇ DE CALDERS | 2022 | 2023 |  |  | 3 trim 2022 |  | 3 trim 2023 |  | 12 MESES |  | PK562,501 VIADUCTO. Reparación de los viadutos de Masos incluyendo ejección de losa de reparto y pasillos fuera de gálibo. L8-12 | x | x | x | [7 empty] | 3 semanas de corte total. Posible implantación LTV en un plazo adicional. Trabajos en banda de mantenimiento extendida (con TBA).
ADIF | 2020-5-012 | ST.SADURNÍ-MARTORELLL |  | S.V. Calders | L'Hospitalet de Llobregat | 2022 | 2023 |  |  | 4 trim 2022 |  | 3 trim 2023 |  | 8 MESES |  | VIADUCTO.Km 60+380. Reparación Viaducto st. Sadurní incluyendo ejecución de pasillos fuera de gálibo, reconstrucción muretes guardabalasto, mejora drenaje y juntas de dilatación del tablero. L8-14 |  | x | x | [7 empty] | Trabajos en banda de mantenimiento extendida (con TBA).
ADIF | 2020-5-013 | Figueres - Llançà |  | FRONTERA CERBERE/PORTBOU | BIF.ARAGÓ | 2023 | 2024 |  |  | 1 trim 2023 |  | 1 trim 2024 |  | 12 MESES |  | PK263,43 VIADUCTO Sustitución tablero metálico puente Llançà y mejora de estribos. L9-7 | x | x | x | [7 empty] | 1 corte total de 72+ 1 corte total 24 h (ambos para último trimestre obra). Resto trabajos en banda de mantenimiento. Posible implantación de LTV. Posible ejecución del corte conjuntamente con viaducto cercano.
ADIF | 2020-5-014 | Figueres - Llançà |  | FRONTERA CERBERE/PORTBOU | BIF.ARAGÓ | 2023 | 2024 |  |  | 1 trim 2023 |  | 1 trim 2024 |  | 12 MESES |  | PK264,418 VIADUCTO. Sustitución tablero metálico puente Massot y mejora de estribos. L9-12 | x | x | x | [7 empty] | 1 corte total de 72 h + 1 corte total de 40 h (para último trimestre obra). Resto trabajos en banda de mantenimiento. Posible implantación de LTV. Posible ejecución del corte conjuntamente con viaducto cercano.
ADIF | 2020-5-015 | ASCÓ - MORA LA NOVA |  | MIRAFLORES | S.VICENÇ DE CALDERS | 2023 | 2023 |  |  | 1905-07-15 |  | 1905-07-15 |  | 2 MESES |  | PK 519,2 TÚNEL. Rehabilitación de la bóveda del túnel de Ascó, adecuación de rasante, impermeabilización, mejora de drenaje y tratamiento emboquilles. . L10-7 | x | x | x | [7 empty] | Corte total duración estimada de 2 meses. Banda de mantenimiento ampliada. Intervalos extraordinarios fines de semana. Posible implantación de LTV El proyecto se encuentra en supervisión
ADIF | 2020-5-017 | CASTELLBISBAL-RUBÍ |  | MOLLET SANT FOST - | CASTELLBISBAL-AGUJAS RUBÍ | 2023 | 2023 |  |  | 1 trim 2023 |  | 3 trim 2023 |  | 8 MESES |  | PK 3,8-4,5 Tratamiento del terraplén, columnas de mortero y sustitución capa de forma, subbalasto y balasto Tramo MOLLET-CASTELLBISBAL. L5-2 | x | x | x | [7 empty] | Posibilidad de ejecutar trabajos con corte total de 2 meses. 4 meses de corte de 1 vía alternativamente. 2 meses Banda mantenimiento extendida (con TBA).
ADIF | 2020-5-018 | RIERA DE CALDES-BIF.NUDO MOLLET |  | MOLLET SANT FOST - | CASTELLBISBAL-AGUJAS RUBÍ | 2022 | 2023 |  |  | 4 trim 2022 |  | 1 trim 2023 |  | 6 MESES |  | PK20+82-20+834 Tratamiento terraplén contiguo estructura sobre la riera de caldes. L5-3 |  | x | x | [7 empty] | Banda de mantenimiento extendida (con TBA).
ADIF | 2020-5-019 | Estación de Can Tunis |  | Castellbisbal-Agujas Llobregat | Barcelona-Morrot | 2022 | 2023 |  |  | 2 trim 2022 |  | 1 trim 2023 |  | 10 MESES | - | VIA. Implantación del tercer carril en la vía 2 del túnel de Can Tunis, conexión vía 2 con Calle 4 en ancho mixto. Ancho mixto en vías 18-20-22-46-48-50 . Conexión con vía 2 cabecera lado Morrot. |  | x | x | x | [6 empty] | Vías de baja de forma alternativa para renovación de vía y desvíos, cortes en fin de semana y días progaramados en zonas de afectación a vías generales.
ADIF | 2020-5-020 | Calle 4 |  | Castellbisbal-Agujas Llobregat | Barcelona-Morrot | 2022 | 2022 |  |  | 2022-01-01 |  | 01/10/2022 |  | 10 MESES | - | VÍA. Implantación del tercer carril en la calle 4, conexión del Can Tunis con Puerto de Barcelona. |  | x | x | [7 empty] | Corte total de 10 meses, vía 4 Can Tunis - Puerto de Barcelona
ADIF | 2020-5-021 | Tarragona Estación | ambos | MIRAFLORES | S.VICENÇ DE CALDERS | 2022 | 2022 |  |  | 1 trim 2022 |  | 2 trim 2022 |  | 4 meses | - | Renovación de vía, aparatos de vía en la estación de Tarragona y Tarragona Clasificación. |  | x | x | [7 empty] | Renovación de vía en cortes nocturnos de 3 horas. Renovación de aparatos de vía en cortes extraordinarios en fin de semana.
ADIF | 2020-5-022 | Estación de Can Tunis |  | Castellbisbal-Agujas Llobregat | Barcelona-Morrot | 2022 | 2023 |  |  | 3 trim 2022 |  | 4 trim 2023 |  | 18 MESES | - | IISS. Implantación del tercer carril en la vía 2 del túnel de Can Tunis, conexión vía 2 con Calle 4 en ancho mixto. Ancho mixto en vías 18-20-22-46-48-50 . Conexión con vía 2 cabecera lado Morrot. |  | x | x | x | [6 empty] | Corte total noche puntual para poner el enclavamiento y pruebas.
ADIF | 2020-5-023 | Calle 4 |  | Castellbisbal-Agujas Llobregat | Barcelona-Morrot | 2022 | 2023 |  |  | 3 trim 2022 |  | 4 trim 2023 |  | 18 MESES | - | IISS. Implantación del tercer carril en la vía 1 de calle 4, conexión de Can Tunis con Puerto de Barcelona. |  | x | x | x | [6 empty] | Afectaciión maniobras al puerto
ADIF | 2020-5-025 | Nonaspe-Fayón | ambos | Miraflores | Tarragona | 2022 | 2022 |  |  | 2º semestre 2022 |  | 2º semestre 2022 |  | 1 semana | - | Depuración vía y supresión LTV en túneles 39 y 40. | x |  | x | [7 empty] | Desguarnecido de vía con medios especiales para retirar carbón acumulado en túnel, en corte de 5-7 días (a definir). Supresión LTV existente. El corte se estima en el 2º semestre de 2022. Pte. definir fechas
ADIF | 2021-5-004 | Ariza-Zaragoza | ambos | Madrid Chamartín | BARNA-EST. DE FRANÇA | 2023 |  |  |  | 1er trimestre 2023 |  |  |  |  | Todo el día | Obras relacionadas con la Autopista Ferroviaria Zaragoza Algeciras. Adaptación de galibos de tuneles. | x | [9 empty] | Cortes permanentes puntuales. Pendiente de evaluación técnica del proyecto
ADIF | 2021-5-005 | MORA LA NOVA - REUS |  | MIRAFLORES | S.VICENÇ DE CALDERS | 2023 | 2024 |  |  | 2 trim 2023 |  | 3 trim 2024 |  | 15 MESES |  | PK 556+636 TÚNEL. Rehabilitación del túnel de Argentera, mejoras en la bóveda, impermeabilización, mejora de drenaje y tratamiento emboquilles. . L10-3. Pradell-Riudecanyes. |  | x | x | [7 empty] | Banda de mantenimiento extendida (con TBA). Intervalos extraordinarios fines de semana. Posible implantación de LTV
ADIF | 2021-5-006 | MORA LA NOVA - REUS |  | MIRAFLORES | S.VICENÇ DE CALDERS | 2023 | 2023 |  |  | 2 trim 2023 |  | 3 TRIM 2023 |  | 5 meses |  | PK 544+856 TÚNEL. Rehabilitación del túnel de Capçanes, mejoras en la bóveda, impermeabilización, mejora de drenaje y tratamiento emboquilles. . L10-6. Marça-Els Guiamts. |  | x | x | [7 empty] | Banda de mantenimiento extendida (con TBA). Intervalos extraordinarios fines de semana. Posible implantación de LTV
ADIF | 2021-5-007 | Girona - Vilamalla |  | CERBERE | BIF.ARAGÓ | 2023 | 2024 |  |  | 2 trim 2023 |  | 4 trim 2024 |  | 18 MESES |  | PK236,079 VIADUCTO. Sustitución tablero metálico, sustitución de pilas puente Fluvià y mejora de estribos. L9-8. Sant Miguel de Fluvià | x | x | x | [7 empty] | 1 corte total de 72 h + 1 corte total de 24 h (para último trimestre obra). Resto trabajos en banda de mantenimiento. Posible implantación de LTV. Posible ejecución del corte conjuntamente con viaducto cercano.
ADIF | 2021-5-008 | Girona - Vilamalla |  | CERBERE | BIF.ARAGÓ | 2022 | 2023 |  |  | 4 trim 2022 |  | 3 trim 2023 |  | 10 MESES |  | PK217,037 VIADUCTO. Sustitución tablero hormigón Riera Palagret, eliminación pilas y mejora de estribos. L8-2. Flaça-Girona. | x | x | x | [7 empty] | 1 corte total de 48 (para último trimestre obra). Resto trabajos en banda de mantenimiento. Posible implantación de LTV. Posible ejecución del corte conjuntamente con viaducto cercano.
ADIF | 2021-5-009 | Mora la Nova - Reus |  | MIRAFLORES | S.VICENÇ DE CALDERS | 2023 | 2023 |  |  | 2 trim 2023 |  | 3 trim 2023 |  | 3 MESES |  | PK569,161 VIADUCTO. Sustitución tablero de hormigón por estructura mixta, refuerzo de pilas y mejora de estribos Riera de Riudecols. L7-4. Riudecanys.Les Borges del Camp. | x | x | x | [7 empty] | 1 corte total de 4 semanas. Resto trabajos en banda de mantenimiento. Posible implantación de LTV. Posible ejecución del corte conjuntamente con viaducto cercano.
ADIF | 2021-5-010 | Mora la Nova - Reus |  | MIRAFLORES | S.VICENÇ DE CALDERS | 2023 | 2023 |  |  | 2 trim 2023 |  | 3 trim 2023 |  | 5 MESES |  | PK571,587 VIADUCTO. Sustitución tablero de hormigón por estructura mixta, refuerzo de pilas y mejora de estribos Riera de les Borges del Camp. L7-5 | x | x | x | [7 empty] | En estudio corte total o cortes parciales de 1 vía (durante 15 semanas). Resto trabajos en banda de mantenimiento. Posible implantación de LTV. Posible ejecución del corte conjuntamente con viaducto Riudecols.
ADIF | 2021-5-011 | Mora la Nova - Reus |  | MIRAFLORES | S.VICENÇ DE CALDERS | 2023 | 2023 |  |  | 2 trim 2023 |  | 3 trim 2023 |  | 2 MESES |  | PK574,19 VIADUCTO. Ejecución de losa de impermeabilización, refuerzo de pilas y mejora de estribos Riera de Maspujols. L7-6. Les Borges del Camp-Reus. | x | x | x | [7 empty] | 1 corte total de 3 semanas. Resto trabajos en banda de mantenimiento. Posible implantación de LTV. Posible ejecución del corte conjuntamente con viaducto cercano.
ADIF | 2021-5-012 | Girona |  | CERBERE | BIF.ARAGÓ | 2023 | 2025 |  |  | 4 trim 2023 |  | 1 trim 2025 |  | 15 MESES |  | VIADUCTO ESTACIÓN GIRONA. Impermeabilización del tablero, reparación daños pilas, parte inferior, colocación de barandillas. L7-10 |  | x | x | [7 empty] | En estudio corte parcial por vías. Resto trabajos en banda de mantenimiento. Posible implantación de LTV.
ADIF | 2021-5-013 | Riu Llobregat - Barna-C.Tunis |  | Castellbisbal-Agujas Llobregat | BARCELONA MORROT | 2023 | 2023 |  |  | 2 trim 2023 |  | 4 trim 2023 |  | 6 MESES |  | Tratamiento Terraplén PK 13,990. Retirada capas superiores y restitución. Tratamiento profundo | x | x | x | [7 empty] | Corte total (estimado 20 días). Resto trabajos en banda de mantenimiento. Posible implantación de LTV.
ADIF | 2021-5-019 | Binefar - Almacelles |  | Madrid Chamartín | BARNA-EST. DE FRANÇA | 2023 | 2024 |  |  | 4 trim 2023 |  | 1 trim 2024 |  | 4 MESES |  | Tratamiento Terraplén PK 155,1. L6-2. Tamarite-Almacelles. | x | x | x | [7 empty] | Corte total de 43 días. Resto trabajos en banda de mantenimiento extendida. Posible implantación de LTV. Posible coordinación obras de terraplenes de la misma linea
ADIF | 2021-5-020 | Almacelles - Lleida-Pirineus |  | Madrid Chamartín | BARNA-EST. DE FRANÇA | 2023 | 2024 |  |  | 4 trim 2023 |  | 1 trim 2024 |  | 5 MESES |  | Tratamiento Terraplén PK 169,5. L6-5. Raimat-Montagut. | x | x | x | [7 empty] | Corte total de 75 días. Resto trabajos en banda de mantenimiento extendida. Posible implantación de LTV. Posible coordinación obras de terraplenes de la misma linea
ADIF | 2021-5-022 | Figueres-Portbou | ambos | Cerbere | BIF.ARAGÓ | 2022 | 2023 |  |  | 2 sem 22 |  | 2 sem 23 |  | 25 meses | Posibilidad de días completos | Redacción de proyecto constructivo y ejecución de las obras de instalación de bloqueo automático banalizado (B.A.B.) en el tramo Figueres-Portbou |  | x | [8 empty] | Trabajos nocturnos en banda de mantenimiento. Corte especial en algún fin de semana para la puesta en servicio en estaciones.
ADIF | 2021-5-023 | L'Arboç-Castellbisbal | ambos | St. Vicenç de Calders | L' Hospitalet | 2021 | 2022 |  |  | 4º trim 21 |  | 4º trim 22 |  | 12 meses | Cortes fin de semana/ Cortes nocturnos | Tratamiento integral en la línea aérea de contacto en el tramo L'Arboç-Els Monjos-Vilafranca del Penedés-La Granada-Sant Sadurní d'Anoia-Gelida-Martorell-Castellbisbal |  | x | x | [7 empty] | Corte especial en fin de semana
ADIF | 2021-5-025 | MORA LA NOVA - REUS |  | MIRAFLORES | S.VICENÇ DE CALDERS | 2023 | 2024 |  |  | 1 trim 2023 |  | 2 trim 2024 |  | 15 MESES |  | PK 556,636 TÚNEL. PROYECTO DE TRATAMIENTO DE LA INFRAESTRUCTURA DEL TÚNEL Nº 73 DE ARGENTERA. LÍNEA: MIRAFLORES ‐ TARRAGONA. TRAMO: MORA LA NOVA-REUS. L10-3 |  | x | x | [7 empty] | Posibilidad de Trabajos en banda de mantenimiento extendida (con TBA).
ADIF | 2021-5-026 | MORA LA NOVA - REUS |  | MIRAFLORES | S.VICENÇ DE CALDERS | 2023 | 2023 |  |  | 1 trim 2023 |  | 2 trim 2023 |  | 4,25 MESES |  | PK 544,856 TÚNEL. PROYECTO DE TRATAMIENTO DE LA INFRAESTRUCTURA DEL TÚNEL Nº 68 DE CAPÇANES. LÍNEA: MIRAFLORES ‐ TARRAGONA. TRAMO: MORA LA NOVA-REUS |  | x | x | [7 empty] | Posibilidad de Trabajos en banda de mantenimiento extendida (con TBA).
ADIF | 2021-5-027 | FLIX - MORA LA NOVA |  | MIRAFLORES | S.VICENÇ DE CALDERS | 2023 | 2024 |  |  | 4 trim 2023 |  | 1 trim 2024 |  | 5 meses |  | PK 514,627. TERRAPLÉN. PROYECTO DE TRATAMIENTO DEL TERRAPLÉN SITUADO EN LA LINEA MIRAFLORES - S.VICENÇ DE CALDERS. PK INICIO 514,627 A PK FINAL 514,85. TRAMO CASPE- MORA LA NOVA | X | X | X | [7 empty] | Corte total de 2 MESES. Resto trabajos en banda de mantenimiento extendida. Posible implantación de LTV.
ADIF | 2019-7-004 | estacion de Figueres Vilafant | ambos | Límite ADIF - LFPSA | Madrid -Puerta de Atocha | - | - | - | - | - | - | - | - | - | - | Obras de adecuación en la estación de Figueres Vilafant a su disposición definitiva, previsto TBA 80/14 |  | x | [8 empty] | Solo afecta a la capacidad de estacionamiento de Figueres Vilafant. Una vez finalizados se eliminará la LTV a 160 km/h de Figueres-Vilafant. Trabajos finalizados a falta de software.
ADIF | 2019-7-005 | estacion de Figueres Vilafant | ambos | Límite ADIF - LFPSA | Madrid -Puerta de Atocha | - | - | - | - | - | - | - | - | - | - | Incluir LTV de Figueres Vilafant Vía IV a 30 km/h en SSP. |  |  | x | [7 empty] | LTV 30 km/h
Note on B132: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B136: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B137: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B138: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B139: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B140: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B141: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B142: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B143: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B144: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B145: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B146: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B147: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B148: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B149: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B150: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B151: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B152: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B153: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B154: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B155: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B156: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B157: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B158: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B159: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B160: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B161: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B162: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B163: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B164: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B165: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B166: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B167: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B168: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B169: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B170: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B171: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B172: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B173: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B174: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B175: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B176: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B177: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B178: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B179: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B180: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B181: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B182: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B183: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B184: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B185: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B186: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B187: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B188: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B189: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B190: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B191: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B192: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B193: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B194: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B195: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B196: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B197: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B198: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B199: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B200: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B201: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B202: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B203: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B204: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B205: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B206: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B207: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B208: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B209: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B210: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B211: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B212: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B213: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B214: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B215: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B216: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B217: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B218: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B219: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B220: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B221: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B222: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B223: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B224: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B225: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B226: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B227: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B228: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B229: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B230: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B231: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B232: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B233: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B234: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B235: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B236: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B237: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B238: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B239: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B240: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B241: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B242: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B243: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B244: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B245: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B246: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B247: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B248: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B249: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B250: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B251: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B252: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B253: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B254: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B255: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B256: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B257: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B258: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B259: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B260: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B261: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B262: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B263: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B264: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B265: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B266: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B267: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B268: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B269: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B270: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B271: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B272: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B273: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B274: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B275: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B276: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B277: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B278: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B279: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B280: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B281: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B282: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B283: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B284: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B285: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B286: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B287: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B288: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B289: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B290: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B291: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B292: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B293: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B294: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B295: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B296: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B297: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B298: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B299: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B300: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B301: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B302: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B303: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B304: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B305: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B306: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B307: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on B308: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on C132: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on C134: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on C135: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on C136: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on C137: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on C138: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on C139: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on C140: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on C141: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on C142: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on F132: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on F134: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on F135: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on F136: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on F137: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on G132: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on G134: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on G135: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on G136: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on G137: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on Q132: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q134: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q135: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q136: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q137: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q138: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q139: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q140: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q141: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q142: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q143: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q144: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q145: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q146: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q147: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q148: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q149: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q150: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q151: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q152: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q153: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q154: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q155: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q156: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q157: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q158: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q159: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q160: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q161: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q162: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q163: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q164: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q165: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q166: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q167: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q168: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q169: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q170: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q171: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q172: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q173: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q174: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q175: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q176: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q177: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q178: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q179: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q180: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q181: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q182: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q183: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q184: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q185: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q186: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q187: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q188: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q189: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q190: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q191: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q192: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q193: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q194: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q195: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q196: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q197: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q198: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q199: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q200: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q201: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q202: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q203: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q204: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Q205: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S132: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S134: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S135: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S136: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S137: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S138: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S139: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S140: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S141: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S142: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S143: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S144: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S145: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S146: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S147: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S148: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S149: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S150: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S151: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S152: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S153: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S154: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S155: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S156: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S157: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S158: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S159: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S160: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S161: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S162: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S163: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S164: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S165: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S166: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S167: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S168: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S169: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S170: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S171: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S172: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S173: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S174: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S175: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S176: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S177: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S178: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S179: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S180: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S181: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S182: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S183: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S184: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S185: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S186: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S187: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S188: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S189: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S190: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S191: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S192: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S193: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S194: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S195: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S196: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S197: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S198: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S199: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S200: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S201: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S202: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S203: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S205: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S206: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S207: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S208: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S215: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S222: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S223: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S224: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S225: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S226: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S227: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S228: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S229: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S230: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S231: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S232: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S233: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S234: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S235: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S236: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S237: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S238: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S239: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S240: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S241: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S242: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S243: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S244: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S245: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S246: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S247: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S248: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S249: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S250: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S251: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S252: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S253: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S254: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S255: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S256: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S257: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S303: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S304: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S305: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S306: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S307: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on S308: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T132: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T134: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T135: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T136: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T137: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T138: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T139: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T140: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T141: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T142: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T143: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T144: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T145: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T146: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T147: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T148: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T149: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T150: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T151: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T152: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T153: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T154: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T155: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T156: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T157: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T158: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T159: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T160: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T161: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T162: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T163: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T164: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T165: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T166: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T167: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T168: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T169: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T170: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T171: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T172: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T173: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T174: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T175: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T176: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T177: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T178: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T179: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T180: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T181: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T182: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T183: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T184: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T185: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T186: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T187: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T188: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T189: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T190: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T191: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T192: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T193: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T194: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T195: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T196: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T197: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T198: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T199: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T200: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T201: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T202: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on T203: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X132: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X134: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X135: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X136: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X137: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X138: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X139: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X140: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X141: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X142: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X143: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X144: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X145: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X146: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X147: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X148: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X149: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X150: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X151: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X152: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X153: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X154: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X155: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X156: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X157: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X158: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X159: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X160: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X161: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X162: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X163: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X164: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X165: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X166: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X167: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X168: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X169: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X170: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X171: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X172: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X173: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X174: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X175: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X176: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X177: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X178: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X179: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X180: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X181: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X182: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X183: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X184: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X185: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X186: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X187: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X188: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X189: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X190: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X191: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X192: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X193: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X194: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X195: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X196: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X197: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X198: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X199: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X200: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X201: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X202: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X203: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X205: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X206: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X207: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X208: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X209: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X210: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X211: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X212: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X213: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X214: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X215: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X216: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X217: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X218: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X219: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X220: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X221: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X222: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X223: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X224: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X225: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X226: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X227: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X228: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X229: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X230: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X231: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X232: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X233: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X234: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X235: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X236: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X237: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X238: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X239: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X240: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X241: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X242: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X243: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X244: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X245: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X246: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X247: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X248: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X249: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X250: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X251: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X252: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X253: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X254: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X255: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X256: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X257: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X258: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X259: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X260: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X261: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X262: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X263: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X264: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X265: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X266: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X267: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X268: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X269: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X270: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X271: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X272: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X273: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X274: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X275: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X276: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X277: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X278: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X279: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X280: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X281: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X282: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X283: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X284: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X285: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X286: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X287: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X288: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X289: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X290: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X291: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X292: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X293: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X294: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X295: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X296: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X297: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X298: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X299: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X300: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X301: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X302: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X303: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X304: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X305: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X306: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X307: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on X308: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y132: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y133: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y134: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y135: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y136: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y137: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y138: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y139: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y140: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y141: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y142: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y143: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y144: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y145: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y146: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y147: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y148: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y149: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y150: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y151: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y152: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y153: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y154: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y155: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y156: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y157: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y158: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y159: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y160: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y161: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y162: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y163: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y164: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y165: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y166: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y167: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y168: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y169: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y170: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y171: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y172: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y173: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y174: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y175: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y176: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y177: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y178: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y179: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y180: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y181: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y182: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y183: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y184: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y185: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y186: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y187: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y188: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y189: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y190: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y191: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y192: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y193: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y194: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y195: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y196: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y197: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y198: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y199: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y200: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y201: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y202: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y203: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y204: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y205: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y206: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y207: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y208: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y209: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y210: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y211: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y212: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y213: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y214: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y215: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y216: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y217: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y218: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y219: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y220: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y221: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y222: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y223: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y224: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y225: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y226: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y227: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y228: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y229: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y230: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y231: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y232: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y233: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y234: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y235: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y236: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y237: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y238: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y239: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y240: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y241: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y242: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y243: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y244: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y245: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y246: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y247: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y248: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y249: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y250: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y251: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y252: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y253: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y254: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y255: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y256: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y257: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y258: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y259: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y260: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y261: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y262: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y263: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y264: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y265: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y266: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y267: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y268: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y269: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y270: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y271: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y272: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y273: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y274: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y275: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y276: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y277: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y278: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y279: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y280: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y281: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y282: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y283: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y284: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y285: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y286: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y287: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y288: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y289: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y290: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y291: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y292: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y293: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y294: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y295: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y296: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y297: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y298: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y299: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y300: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y301: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y302: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y303: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y304: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y305: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y306: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y307: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y308: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z132: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z133: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z134: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z135: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z136: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z137: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z138: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z139: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z140: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z141: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z142: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z143: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z144: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z145: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z146: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z147: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z148: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z149: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z150: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z151: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z152: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z153: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z154: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z155: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z156: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z157: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z158: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z159: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z160: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z161: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z162: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z163: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z164: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z165: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z166: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z167: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z168: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z169: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z170: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z171: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z172: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z173: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z174: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z175: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z176: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z177: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z178: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z179: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z180: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z181: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z182: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z183: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z184: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z185: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z186: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z187: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z188: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z189: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z190: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z191: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z192: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z193: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z194: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z195: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z196: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z197: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z198: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z199: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z200: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z201: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z202: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z203: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z204: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z205: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z206: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z207: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z208: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z209: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z210: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z211: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z212: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z213: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z214: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z215: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z216: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z217: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z218: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z219: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z220: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z221: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z222: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z223: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z224: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z225: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z226: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z227: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z228: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z229: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z230: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z231: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z232: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z233: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z234: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z235: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z236: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z237: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z238: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z239: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z240: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z241: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z242: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z243: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z244: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z245: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z246: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z247: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z248: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z249: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z250: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z251: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z252: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z253: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z254: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z255: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z256: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z257: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z258: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z259: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z260: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z261: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z262: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z263: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z264: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z265: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z266: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z267: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z268: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z269: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z270: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z271: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z272: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z273: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z274: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z275: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z276: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z277: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z278: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z279: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z280: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z281: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z282: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z283: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z284: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z285: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z286: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z287: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z288: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z289: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z290: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z291: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z292: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z293: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z294: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z295: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z296: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z297: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z298: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z299: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z300: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z301: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z302: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z303: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z304: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z305: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z306: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z307: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z308: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA132: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA133: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA134: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA135: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA136: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA137: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA138: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA139: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA140: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA141: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA142: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA143: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA144: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA145: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA146: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA147: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA148: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA149: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA150: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA151: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA152: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA153: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA154: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA155: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA156: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA157: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA158: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA159: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA160: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA161: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA162: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA163: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA164: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA165: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA166: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA167: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA168: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA169: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA170: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA171: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA172: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA173: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA174: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA175: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA176: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA177: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA178: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA179: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA180: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA181: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA182: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA183: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA184: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA185: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA186: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA187: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA188: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA189: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA190: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA191: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA192: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA193: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA194: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA195: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA196: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA197: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA198: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA199: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA200: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA201: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA202: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA203: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA204: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA205: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA206: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA207: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA208: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA209: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA210: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA211: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA212: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA213: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA214: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA215: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA216: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA217: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA218: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA219: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA220: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA221: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA222: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA223: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA224: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA225: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA226: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA227: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA228: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA229: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA230: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA231: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA232: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA233: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA234: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA235: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA236: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA237: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA238: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA239: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA240: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA241: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA242: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA243: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA244: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA245: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA246: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA247: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA248: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA249: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA250: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA251: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA252: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA253: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA254: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA255: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA256: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA257: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA258: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA259: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA260: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA261: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA262: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA263: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA264: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA265: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA266: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA267: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA268: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA269: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA270: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA271: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA272: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA273: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA274: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA275: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA276: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA277: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA278: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA279: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA280: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA281: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA282: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA283: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA284: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA285: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA286: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA287: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA288: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA289: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA290: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA291: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA292: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA293: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA294: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA295: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA296: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA297: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA298: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA299: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA300: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA301: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA302: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA303: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA304: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA305: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA306: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA307: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA308: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD132: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD134: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD135: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD136: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD137: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD138: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD139: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD140: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD141: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD142: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD143: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD144: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD145: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD146: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD147: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD148: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD149: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD150: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD151: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD152: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD153: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD154: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD155: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD156: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD157: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD158: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD159: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD160: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD161: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD162: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD163: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD164: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD165: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD166: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD167: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD168: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD169: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD170: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD171: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD172: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD173: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD174: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD175: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD176: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD177: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD178: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD179: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD180: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD181: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD182: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD183: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD184: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD185: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD186: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD187: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD188: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD189: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD190: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD191: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD192: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD193: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD194: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD195: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD196: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD197: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD198: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD199: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD200: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD201: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD202: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AD203: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ132: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ134: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ135: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ136: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ137: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ138: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ139: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ140: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ141: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ142: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ143: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ144: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ145: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ146: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ147: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ148: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ149: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ150: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ151: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ152: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ153: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ154: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ155: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ156: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ157: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ158: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ159: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ160: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ161: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ162: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ163: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ164: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ165: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ166: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ167: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ168: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ169: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ170: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ171: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ172: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ173: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ174: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ175: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ176: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ177: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ178: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ179: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ180: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ181: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ182: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ183: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ184: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ185: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ186: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ187: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ188: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ189: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ190: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ191: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ192: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ193: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ194: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ195: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ196: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ197: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ198: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ199: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ200: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ201: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ202: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AJ203: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK132: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK134: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK135: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK136: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK137: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK138: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK139: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK140: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK141: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK142: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK143: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK144: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK145: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK146: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK147: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK148: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK149: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK150: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK151: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK152: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK153: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK154: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK155: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK156: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK157: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK158: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK159: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK160: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK161: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK162: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK163: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK164: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK165: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK166: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK167: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK168: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK169: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK170: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK171: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK172: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK173: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK174: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK175: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK176: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK177: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK178: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK179: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK180: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK181: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK182: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK183: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK184: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK185: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK186: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK187: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK188: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK189: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK190: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK191: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK192: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK193: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK194: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK195: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK196: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK197: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK198: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK199: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK200: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK201: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK202: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AK203: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL132: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL134: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL135: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL136: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL137: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL138: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL139: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL140: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL141: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL142: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL143: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL144: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL145: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL146: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL147: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL148: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL149: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL150: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL151: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL152: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL153: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL154: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL155: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL156: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL157: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL158: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL159: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL160: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL161: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL162: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL163: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL164: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL165: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL166: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL167: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL168: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL169: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL170: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL171: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL172: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL173: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL174: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL175: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL176: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL177: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL178: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL179: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL180: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL181: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL182: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL183: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL184: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL185: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL186: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL187: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL188: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL189: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL190: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL191: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL192: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL193: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL194: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL195: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL196: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL197: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL198: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL199: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL200: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL201: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL202: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AL203: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM132: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM134: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM135: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM136: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM137: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM138: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM139: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM140: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM141: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM142: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM143: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM144: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM145: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM146: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM147: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM148: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM149: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM150: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM151: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM152: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM153: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM154: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM155: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM156: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM157: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM158: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM159: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM160: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM161: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM162: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM163: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM164: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM165: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM166: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM167: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM168: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM169: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM170: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM171: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM172: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM173: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM174: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM175: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM176: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM177: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM178: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM179: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM180: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM181: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM182: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM183: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM184: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM185: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM186: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM187: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM188: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM189: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM190: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM191: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM192: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM193: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM194: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM195: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM196: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM197: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM198: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM199: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM200: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM201: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM202: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM203: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN132: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN134: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN135: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN136: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN137: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN138: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN139: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN140: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN141: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN142: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN143: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN144: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN145: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN146: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN147: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN148: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN149: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN150: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN151: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN152: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN153: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN154: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN155: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN156: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN157: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN158: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN159: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN160: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN161: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN162: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN163: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN164: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN165: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN166: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN167: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN168: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN169: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN170: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN171: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN172: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN173: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN174: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN175: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN176: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN177: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN178: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN179: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN180: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN181: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN182: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN183: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN184: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN185: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN186: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN187: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN188: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN189: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN190: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN191: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN192: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN193: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN194: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN195: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN196: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN197: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN198: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN199: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN200: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN201: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN202: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN203: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP132: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP133: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP134: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP135: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP136: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP137: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP138: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP139: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP140: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP141: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP142: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP143: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP144: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP145: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP146: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP147: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP148: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP149: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP150: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP151: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP152: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP153: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP154: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP155: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP156: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP157: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP158: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP159: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP160: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP161: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP162: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP163: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP164: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP165: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP166: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP167: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP168: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP169: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP170: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP171: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP172: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP173: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP174: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP175: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP176: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP177: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP178: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP179: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP180: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP181: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP182: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP183: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP184: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP185: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP186: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP187: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP188: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP189: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP190: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP191: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP192: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP193: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP194: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP195: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP196: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP197: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP198: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP199: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP200: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP201: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP202: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AP203: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ132: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ134: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ135: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ136: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ137: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ138: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ139: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ140: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ141: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ142: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ143: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ144: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ145: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ146: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ147: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ148: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ149: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ150: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ151: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ152: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ153: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ154: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ155: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ156: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ157: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ158: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ159: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ160: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ161: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ162: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ163: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ164: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ165: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ166: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ167: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ168: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ169: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ170: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ171: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ173: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ174: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ175: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ176: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ177: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ178: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ179: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ180: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ181: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ182: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ183: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ184: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ185: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ186: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ187: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ188: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ189: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ190: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ191: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ192: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ193: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ194: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ195: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ196: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ197: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ198: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ199: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ200: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ201: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ202: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on AQ203: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".

## Modane - July 2022
SNCF RESEAU - WORKS TT2022 - AMBERIEU-MODANE
| =Total closure >12 hrs | [11 empty] | 2021 | [19 empty] | 2022
| = border point Modane | [11 empty] | DEC | [19 empty] | JAN | [30 empty] | FEV | [27 empty] | MAR | [30 empty] | AVR | [29 empty] | MAI | [30 empty] | JUN | [29 empty] | JUL | [30 empty] | AOU | [30 empty] | SEP | [29 empty] | OCT | [30 empty] | NOV | [29 empty] | DEC
Total closure >12 hrs ? | Border point ? | Identifiant Ressource | Localisation : Starting point | Localisation : Ending point | Start Time Starting point | End Time Starting point | Start Time Ending point | End Time Ending point | Days of activation (night works are identified by : Day1 / Day2) Period of activation | Type of works | Worksites | Weekend | 49 | 50 | [6 empty] | 51 | [6 empty] | 52 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40 | [6 empty] | 41 | [6 empty] | 42 | [6 empty] | 43 | [6 empty] | 44 | [6 empty] | 45 | [6 empty] | 46 | [6 empty] | 47 | [6 empty] | 48 | [6 empty] | 49
|  | DEF22_Amberieu-Culoz_001 | Ambérieu-P4 | Culoz-AE | 23:01 | 04:46 J+1 | 23:01 | 04:46 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 30/31-01-22 au JE/VE 17/18-02-22, du LU/MA 07/08-03-22 au JE/VE 10/11-03-22 et du LU/MA 18/19-04-22 au JE/VE 28/29-04-22 Sauf le(s) : DI/LU 24/25-04-22 | Def, V1,V2, 2V/2, IPCS=4 pas, 05:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA15_0008984_47 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Amberieu-Culoz_002 | Ambérieu-P4 | La Burbanche-00 | 10:06 | 13:05 | 10:06 | 13:05 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 07-03-22 au VE 18-03-22 et du LU 31-10-22 au JE 10-11-22 Sauf le(s) : MA 01-11-22 | Def, V1,V2, 1V/2, IPCS=1 pas, 02:59, Jour, LU,MA,ME,JE,VE | CHA15_0008984_47 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Amberieu-Culoz_003 | Ambérieu-P4 | Aig IPCS Km 642-00 | 23:34 | 00:37 J+1 | 23:34 | 00:37 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 21/22-03-22 au JE/VE 24/25-03-22 | Def, V2, 1V/1, IPCS=1 pas, 01:03, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA15_0008984_47 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Amberieu-Culoz_004 | Tenay-Hauteville-00 | Culoz-AE | 10:18 | 13:20 | 10:18 | 13:20 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 21-03-22 au VE 01-04-22 et du LU 14-11-22 au VE 25-11-22 | Def, V1,V2, 1V/2, IPCS=2 pas, 03:02, Jour, LU,MA,ME,JE,VE | CHA15_0008984_47 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Amberieu-Culoz_011 | La Burbanche-00 | Culoz-AE | 23:10 | 05:15 J+1 | 23:10 | 05:15 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-06-22 au JE/VE 30/01-07-22 | Def, V1,V2, 2V/2, 06:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA15_0008984_47 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Amberieu-Culoz_012 | Ambérieu-P4 | Aig IPCS Km 642-00 | 02:15 | 04:20 | 02:15 | 04:20 | Jours d'application : MA,ME,JE,VE Périodes : du MA 22-03-22 au VE 25-03-22 | Def, V2, 1V/1, IPCS=1 pas, 02:05, Nuit non passe-minuit, MA,ME,JE,VE | CHA15_0008984_47 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Amberieu-Culoz_001 | Ambérieu-P4 | Culoz-AE | 22:25 | 04:25 J+1 | 22:25 | 04:25 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-12-21 au JE/VE 16/17-12-21, du LU/MA 10/11-01-22 au JE/VE 14/15-04-22, du LU/MA 25/26-04-22 au JE/VE 28/29-04-22, du LU/MA 09/10-05-22 au JE/VE 12/13-05-22, du LU/MA 30/31-05-22 au JE/VE 07/08-07-22, du LU/MA 18/19-07-22 au JE/VE 28/29-07-22 et du LU/MA 22/23-08-22 au MA/ME 06/07-12-22 Sauf le(s) : JE/VE 10/11-11-22 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA15_0008984_47,CHA22_0022870_01 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
|  | FEN22_Amberieu-Culoz_002 | Ambérieu-P4 | Culoz-AE | 22:03 | 04:03 J+1 | 22:03 | 04:03 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 23/24-01-22 au DI/LU 24/25-04-22, du DI/LU 12/13-06-22 au DI/LU 03/04-07-22 et du DI/LU 21/22-08-22 au DI/LU 04/05-12-22 Et le(s) : DI/LU 12/13-12-21 Sauf le(s) : DI/LU 17/18-04-22 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA22_0022870_01,CHA15_0008984_47 | OUI | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Amberieu-Culoz_003 | Ambérieu-P4 | Culoz-AE | 00:03 | 04:03 | 00:03 | 04:03 | Jours d'application : LU Périodes : du LU 24-01-22 au LU 25-04-22, du LU 13-06-22 au LU 27-06-22 et du LU 22-08-22 au LU 05-12-22 Et le(s) : LU 13-12-21 Sauf le(s) : LU 18-04-22 | Gen, V1,V2, 2V/2, 04:00, Nuit non passe-minuit, LU | CHA15_0008984_47 | NON | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Amberieu-Culoz_008 | Ambérieu-P4 | Culoz-AE | 15:05 | 16:05 | 15:34 | 16:34 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : LU 18-04-22,JE 26-05-22,LU 06-06-22, JE 14-07-22,LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, V1, 1V/2, IPCS=4 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008984_47 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Amberieu-Culoz_009 | Ambérieu-P4 | Culoz-AE | 11:22 | 12:22 | 10:59 | 11:59 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : LU 18-04-22,JE 26-05-22,LU 06-06-22, JE 14-07-22,LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, V2, 1V/2, IPCS=4 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008984_47 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP22_Culoz_001 | Virieu-le-Grand-Belley-BV | Culoz-S1 | 22:40 | 04:50 J+1 | 22:40 | 04:50 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 04/05-09-22 au JE/VE 08/09-09-22 | Cap, H,V1,V2, 06:10, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022620_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Culoz_002 | Culoz-V3 | Culoz-S1 | 13:45 | 15:40 | 13:45 | 15:40 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 20-06-22 au VE 01-07-22 | Cap, V1, 01:55, Jour, LU,MA,ME,JE,VE | CHA15_0008984_48 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Culoz_017 | Culoz-V3 | - | 10:50 | 12:20 | 10:50 | 12:20 | Jours d'application : LU,MA,ME,JE,VE Périodes : du MA 07-06-22 au VE 17-06-22 | Cap, UNIQUE,V2, 01:30, Jour, LU,MA,ME,JE,VE | CHA15_0008984_48 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Culoz_018 | Culoz-V3 | Vions-Chanaz-00 | 22:40 | 04:50 J+1 | 22:40 | 04:50 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 25/26-09-22 au JE/VE 29/30-09-22 | Cap, C,CG,H,UNIQUE,V1,V1,V2, 06:10, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022620_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Culoz_019 | Virieu-le-Grand-Belley-BV | Culoz-S1 | 22:40 | 05:30 J+1 | 22:40 | 05:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 11/12-09-22 au JE/VE 15/16-09-22 | Cap, H,V1,V2, 06:50, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022620_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Culoz_020 | Culoz-V3 | Vions-Chanaz-00 | 22:40 | 05:30 J+1 | 22:40 | 05:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 18/19-09-22 au JE/VE 22/23-09-22 | Cap, C,CG,H,UNIQUE,V1,V1,V2, 06:50, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022620_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Culoz_021 | Culoz-BC | Vions-Chanaz-00 | 21:30 | 05:30 J+1 | 21:30 | 05:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 02/03-10-22 au JE/VE 13/14-10-22 | Cap, C,CG,UNIQUE,V1, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022620_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Culoz_022 | Culoz-BC | Vions-Chanaz-00 | 23:05 | 05:10 J+1 | 23:05 | 05:10 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 16/17-10-22 au JE/VE 20/21-10-22 | Cap, C,CG,UNIQUE,V1, 06:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022620_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Culoz_023 | Virieu-le-Grand-Belley-BV | Vions-Chanaz-00 | 23:02 | 04:55 J+1 | 23:02 | 04:55 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 09/10-01-22 au DI/LU 16/17-01-22 | Cap, 4C,C,CG,UNIQUE,V1,V1,V2,V2, 05:53, Passe-minuit, DI/LU | CHA17_0010710_228 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Culoz_024 | Virieu-le-Grand-Belley-BV | Vions-Chanaz-00 | 23:10 | 05:15 J+1 | 23:10 | 05:15 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-06-22 au JE/VE 30/01-07-22 | Cap, 4C,C,CG,UNIQUE,V1,V1,V2,V2, 06:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA15_0008984_48 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Culoz-AixLesBains_003 | Culoz-BG | Aix-les-Bains-Le Revard-P1 | 23:10 | 05:15 J+1 | 23:10 | 05:15 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-06-22 au JE/VE 30/01-07-22 | Def, V1,V2, 2V/2, 06:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA15_0008998_106 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Culoz-AixLesBains_008 | Culoz-BG | Aix-les-Bains-Le Revard-BV | 22:20 | 05:35 J+1 | 22:20 | 05:35 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 12/13-06-22 au JE/VE 30/01-07-22 Et le(s) : DI/LU 10/11-04-22 et DI/LU 24/25-04-22, DI/LU 22/23-05-22, DI/LU 29/30-05-22 et DI/LU 05/06-06-22 | Def, V1,V2, 2V/2, IPCS=2 pas, 07:15, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0023026_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Culoz-AixLesBains_015 | Culoz-BG | Aix-les-Bains-Le Revard-P1 | 09:30 | 12:30 | 09:30 | 12:30 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 14-03-22 au VE 25-03-22 et du LU 03-10-22 au VE 14-10-22 | Def, V1,V2, 1V/2, IPCS=1 pas, 03:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_106 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Culoz-AixLesBains_001 | Culoz-BG | Aix-les-Bains-Le Revard-P1 | 22:20 | 04:20 J+1 | 22:20 | 04:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 24/25-01-22 au MA/ME 25/26-01-22, du LU/MA 31/01-02-22 au JE/VE 28/29-04-22, du LU/MA 16/17-05-22 au JE/VE 19/20-05-22, du LU/MA 13/14-06-22 au JE/VE 30/01-07-22 et du LU/MA 29/30-08-22 au JE/VE 08/09-12-22 Et le(s) : ME/JE 15/16-12-21 Sauf le(s) : MA/ME 01/02-11-22,JE/VE 10/11-11-22 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA22_0022870_03,CHA22_0022478_02,CHA22_0023026_02,CHA15_0008998_106 | NON | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | FEN22_Culoz-AixLesBains_002 | Culoz-BG | Aix-les-Bains-Le Revard-P1 | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 06/07-02-22 au DI/LU 26/27-06-22 et du DI/LU 28/29-08-22 au DI/LU 04/05-12-22 Sauf le(s) : DI/LU 17/18-04-22,DI/LU 05/06-06-22 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA22_0023026_02,CHA22_0022478_02,CHA15_0008998_106 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Culoz-AixLesBains_003 | Culoz-BG | Aix-les-Bains-Le Revard-P1 | 00:34 | 04:42 | 00:34 | 04:42 | Jours d'application : LU Périodes : du LU 31-01-22 au LU 23-05-22, du LU 13-06-22 au LU 27-06-22 et du LU 29-08-22 au LU 05-12-22 Sauf le(s) : LU 18-04-22 | Gen, V1,V2, 2V/2, 04:08, Nuit non passe-minuit, LU | CHA15_0008998_106,CHA22_0022478_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Culoz-AixLesBains_008 | Culoz-BG | Aix-les-Bains-Le Revard-P1 | 11:30 | 12:30 | 11:45 | 12:45 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 17-12-21, du LU 03-01-22 au VE 08-07-22, du LU 18-07-22 au VE 05-08-22 et du LU 22-08-22 au VE 09-12-22 Sauf le(s) : LU 18-04-22,JE 26-05-22,LU 06-06-22, MA 01-11-22,VE 11-11-22 | Sur, V1, 1V/2, IPCS=1 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_106 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Culoz-AixLesBains_009 | Culoz-BG | Aix-les-Bains-Le Revard-BV | 10:55 | 11:55 | 10:42 | 11:42 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 17-12-21, du LU 03-01-22 au VE 08-07-22, du LU 18-07-22 au VE 05-08-22 et du LU 22-08-22 au VE 09-12-22 Sauf le(s) : LU 18-04-22,JE 26-05-22,LU 06-06-22, MA 01-11-22,VE 11-11-22 | Sur, V2, 1V/2, IPCS=1 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_106 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP22_AixLesBains_005 | Aix-les-Bains-Le Revard-BV | Viviers-du-Lac-00 | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 15/16-05-22 au JE/VE 19/20-05-22 | Cap, C,D,E,EV,IM,S,TC,UNIQUE,UNIQUE,V1,V2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA15_0008998_107,CHA15_0009000_13 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_AixLesBains_009 | Aix-les-Bains-Le Revard-P1 | Viviers-du-Lac-00 | 22:40 | 05:00 J+1 | 22:40 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 04/05-09-22 au JE/VE 08/09-09-22, du DI/LU 16/17-10-22 au JE/VE 27/28-10-22 et du MA/ME 01/02-11-22 au JE/VE 17/18-11-22 | Cap, EV,V1, 06:20, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA15_0008998_107 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_AixLesBains_013 | Champfleury-00 | Aix-les-Bains-Le Revard-P2 | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 16/17-10-22 au JE/VE 27/28-10-22 | Cap, C,D,E,TC,V2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA15_0008998_107 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_AixLesBains_014 | Aix-les-Bains-Le Revard-BV | Aix-les-Bains-Le Revard-P2 | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 30/31-10-22 au JE/VE 03/04-11-22 | Cap, S,TN,UNIQUE,V1, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA15_0008998_107,CHA15_0009000_13 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_AixLesBains-Chambery_001 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 10:35 | 12:30 | 10:35 | 12:30 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 02-05-22 au VE 20-05-22 et du LU 12-09-22 au VE 30-09-22 | Def, V1,V2, 1V/2, IPCS=1 pas, 01:55, Jour, LU,MA,ME,JE,VE | CHA15_0008998_108 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_AixLesBains-Chambery_002 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 21:39 | 10:01 J+1 | 21:39 | 10:01 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 29/30-10-22 | Def, V1,V2, 2V/2, 12:22, Passe-minuit, SA/DI | CHA22_0022825_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_AixLesBains-Chambery_003 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 20:40 | 10:00 J+4 | 20:40 | 10:00 J+4 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du ME 25-05-22 au DI 29-05-22 | Def, V1,V2, 2V/2, 85:20, Continu, ME,JE,VE,SA,DI | CHA22_0022825_01 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_AixLesBains-Chambery_004 | Aix-les-Bains-Le Revard-P1 | Chambéry-Challes-les-Eaux-AN | 00:47 | 02:59 | 00:47 | 02:59 | Jours d'application : MA Périodes : Et le(s) : MA 14-06-22 | Def, V1,V2, 2V/2, 02:12, Nuit non passe-minuit, MA | CHA22_0022825_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_AixLesBains-Chambery_005 | Viviers-du-Lac-00 | Chambéry-Challes-les-Eaux-AN | 21:50 | 05:45 J+1 | 21:50 | 05:45 J+1 | Jours d'application : MA/ME,ME/JE,JE/VE Périodes : du MA/ME 17/18-05-22 au ME/JE 25/26-05-22 | Def, V2, 1V/1, 07:55, Passe-minuit, MA/ME,ME/JE,JE/VE | CHA22_0023004_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_AixLesBains-Chambery_008 | Viviers-du-Lac-00 | Chambéry-Challes-les-Eaux-AN | 22:40 | 05:00 J+1 | 22:40 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,DI/LU Périodes : du DI/LU 30/31-10-22 au ME/JE 02/03-11-22 | Def, V2, 1V/1, 06:20, Passe-minuit, LU/MA,MA/ME,ME/JE,DI/LU | CHA22_0023004_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_AixLesBains-Chambery_001 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 22:20 | 04:20 J+1 | 22:20 | 04:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-12-21 au MA/ME 14/15-12-21, du LU/MA 31/01-02-22 au MA/ME 24/25-05-22, du MA/ME 31/01-06-22 au ME/JE 06/07-07-22 et du LU/MA 22/23-08-22 au JE/VE 08/09-12-22 Sauf le(s) : LU/MA 18/19-04-22,LU/MA 23/24-05-22, LU/MA 06/07-06-22 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA22_0022870_05,CHA22_0022825_01,CHA15_0008998_108 | NON | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | FEN22_AixLesBains-Chambery_002 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 06/07-02-22 au DI/LU 26/27-06-22 et du DI/LU 28/29-08-22 au DI/LU 04/05-12-22 Sauf le(s) : DI/LU 22/23-05-22,DI/LU 05/06-06-22 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA22_0022825_01,CHA15_0008998_108 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_AixLesBains-Chambery_003 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 00:34 | 04:34 | 00:34 | 04:34 | Jours d'application : LU Périodes : du LU 31-01-22 au LU 16-05-22, du LU 13-06-22 au LU 04-07-22 et du LU 29-08-22 au LU 05-12-22 | Gen, V1,V2, 2V/2, 04:00, Nuit non passe-minuit, LU | CHA22_0022825_01,CHA15_0008998_108 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  | FEN22_AixLesBains-Chambery_008 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 11:50 | 12:50 | 11:58 | 12:58 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 17-12-21, du LU 03-01-22 au VE 08-07-22, du LU 18-07-22 au VE 05-08-22 et du LU 22-08-22 au VE 09-12-22 Sauf le(s) : LU 18-04-22,JE 26-05-22,LU 06-06-22, MA 01-11-22,VE 11-11-22 | Sur, V1, 1V/2, IPCS=1 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_108 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_AixLesBains-Chambery_009 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 10:37 | 11:37 | 10:28 | 11:28 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 17-12-21, du LU 03-01-22 au VE 08-07-22, du LU 18-07-22 au VE 05-08-22 et du LU 22-08-22 au VE 09-12-22 Sauf le(s) : LU 18-04-22,JE 26-05-22,LU 06-06-22, MA 01-11-22,VE 11-11-22 | Sur, V2, 1V/2, IPCS=1 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_108 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP22_Chambery_001 | Chambéry-Challes-les-Eaux-AS | Chambéry-Poste-Bois-00 | 22:20 | 04:20 J+1 | 22:20 | 04:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 28/29-03-22 au JE/VE 31/01-04-22 | Cap, V1,V2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA22_0023004_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_002 | Chambéry-Challes-les-Eaux-AS | Chambéry-Poste-Bois-00 | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : DI/LU Périodes : Et le(s) : DI/LU 27/28-03-22 | Cap, V1,V2, 06:00, Passe-minuit, DI/LU | CHA22_0023004_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_003 | Chambéry-Challes-les-Eaux-AS | Chambéry-Poste-Bois-00 | 00:51 | 04:27 | 00:51 | 04:27 | Jours d'application : LU Périodes : Et le(s) : LU 28-03-22 | Cap, V1,V2, 03:36, Nuit non passe-minuit, LU | CHA22_0023004_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_004 | Viviers-du-Lac-00 | Chambéry-Poste-Bois-00 | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA,DI/LU Périodes : du MA/ME 31/01-06-22 au VE/SA 03/04-06-22 et du MA/ME 07/08-06-22 au JE/VE 30/01-07-22 Sauf le(s) : VE/SA 10/11-06-22,VE/SA 17/18-06-22,VE/SA 24/25-06-22 | Cap, 4I,C,V1,V2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA,DI/LU | CHA22_0023004_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_005 | Chambéry-Challes-les-Eaux-DP | Chambéry-Challes-les-Eaux-AS | 22:00 | 05:00 J+1 | 22:00 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 01/02-05-22 au LU/MA 16/17-05-22 | Cap, V1,V2, 07:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0023004_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_006 | Viviers-du-Lac-00 | Chambéry-Poste-Bois-00 | 22:00 | 10:00 J+3 | 22:00 | 10:00 J+3 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du JE 26-05-22 au DI 29-05-22 | Cap, 4I,C,V1,V2, 60:00, Continu, JE,VE,SA,DI | CHA22_0023004_02 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_017 | Viviers-du-Lac-00 | Chambéry-Poste-Bois-00 | 20:45 | 12:30 J+1 | 20:45 | 12:30 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 04/05-06-22 et SA/DI 29/30-10-22 | Cap, 4I,C,V1,V2, 15:45, Passe-minuit, SA/DI | CHA22_0023004_02 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_020 | Viviers-du-Lac-00 | Chambéry-Poste-Bois-00 | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 03/04-04-22 au DI/LU 10/11-04-22 et du DI/LU 17/18-04-22 au LU/MA 16/17-05-22 | Cap, 4I,C,D,E,V1,V2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0023004_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.80645 | 0.80645 | 0.80645 | 0.80645 | 0 | 0 | 0.80645 | 0 | 0 | 0 | 0 | 0 | 0 | 0.80645 | 0.80645 | 0.80645 | 0.80645 | 0.80645 | 0 | 0 | 0.80645 | 0.80645 | 0.80645 | 0.80645 | 0.80645 | 0 | 0 | 0.80645 | 0.80645 | 0.80645 | 0.80645 | 0.80645 | 0 | 0 | 0.80645 | 0.80645 | 0.80645 | 0.80645 | 0.80645 | 0 | 0 | 0.80645 | 0.80645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_021 | Viviers-du-Lac-00 | Chambéry-Poste-Bois-00 | 21:50 | 05:45 J+1 | 21:50 | 05:45 J+1 | Jours d'application : MA/ME,ME/JE,JE/VE Périodes : du MA/ME 17/18-05-22 au ME/JE 25/26-05-22 | Cap, 4I,V1,V2, 07:55, Passe-minuit, MA/ME,ME/JE,JE/VE | CHA22_0023004_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_022 | Viviers-du-Lac-00 | Chambéry-Poste-Bois-00 | 22:40 | 05:00 J+1 | 22:40 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,DI/LU Périodes : du DI/LU 30/31-10-22 au ME/JE 02/03-11-22 | Cap, 4I,V1,V2, 06:20, Passe-minuit, LU/MA,MA/ME,ME/JE,DI/LU | CHA22_0023004_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_023 | Viviers-du-Lac-00 | - | 23:30 | 04:15 J+1 | 23:30 | 04:15 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 06/07-02-22 au JE/VE 17/18-02-22 | Cap, 4I,C,D,E,V1,V2,VM1,VM2, 04:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA15_0008998_109 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_026 | Viviers-du-Lac-00 | Chambéry-Poste-Bois-00 | 12:30 | 15:35 | 12:30 | 15:35 | Jours d'application : DI Périodes : Et le(s) : DI 05-06-22 | Cap, 4I,C,V1,V2, 03:05, Jour, DI | CHA22_0023004_02 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_027 | Viviers-du-Lac-00 | Chambéry-Poste-Bois-00 | 20:30 | 20:45 | 20:30 | 20:45 | Jours d'application : SA Périodes : Et le(s) : SA 04-06-22 | Cap, 4I,C,V1,V2, 00:15, Nuit non passe-minuit, SA | CHA22_0023004_02 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_028 | Viviers-du-Lac-00 | Chambéry-Poste-Bois-00 | 22:00 | 07:00 J+1 | 22:00 | 07:00 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 05/06-11-22 | Cap, 4I,C,V1,V2, 09:00, Passe-minuit, SA/DI | CHA22_0023004_02 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_029 | Chambéry-Challes-les-Eaux-DP | Chambéry-Challes-les-Eaux-AS | 23:50 | 04:30 J+1 | 23:50 | 04:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 03/04-04-22 au JE/VE 19/20-05-22 | Cap, C,D,E, 04:40, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0023004_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Chambery_030 | Viviers-du-Lac-00 | Chambéry-Poste-Bois-00 | 23:06 | 05:06 J+1 | 23:06 | 05:06 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 11/12-04-22 au JE/VE 14/15-04-22 | Cap, 4I,C,D,E,V1,V2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA22_0023004_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Chambery-Montmelian_001 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 10:20 | 13:50 | 10:20 | 13:50 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 07-03-22 au VE 18-03-22 et du LU 10-10-22 au VE 21-10-22 | Def, V1,V2, 1V/2, IPCS=1 pas, 03:30, Jour, LU,MA,ME,JE,VE | CHA15_0008998_110 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Chambery-Montmelian_002 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 10/11-01-22 au JE/VE 10/11-03-22 et du LU/MA 13/14-06-22 au JE/VE 16/17-06-22 | Def, V1,V2, 2V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA22_0022811_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Chambery-Montmelian_004 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 23:20 | 05:20 J+1 | 23:20 | 05:20 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 09/10-01-22 au DI/LU 06/07-03-22 et du DI/LU 29/30-05-22 au DI/LU 12/13-06-22 Sauf le(s) : DI/LU 05/06-06-22 | Def, V1,V2, 2V/2, 06:00, Passe-minuit, DI/LU | CHA22_0022811_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Chambery-Montmelian_006 | Chambéry-Challes-les-Eaux-AS | Chambéry-Poste-Bois-00 | 22:40 | 05:00 J+1 | 22:40 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,DI/LU Périodes : du DI/LU 30/31-10-22 au ME/JE 02/03-11-22 | Def, V2, 1V/1, 06:20, Passe-minuit, LU/MA,MA/ME,ME/JE,DI/LU | CHA22_0023004_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Chambery-Montmelian_007 | Chambéry-Challes-les-Eaux-AS | Chambéry-Poste-Bois-00 | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 03/04-04-22 au DI/LU 10/11-04-22 et du DI/LU 17/18-04-22 au LU/MA 16/17-05-22 | Def, V1,V2, 2V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0023004_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Chambery-Montmelian_008 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 22:30 | 05:30 J+1 | 22:30 | 05:30 J+1 | Jours d'application : DI/LU Périodes : Et le(s) : DI/LU 10/11-04-22 | Def, V1,V2, 2V/2, 07:00, Passe-minuit, DI/LU | CHA15_0008998_110 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Chambery-Montmelian_009 | Chambéry-Poste-Bois-00 | Montmélian-BM | 22:40 | 05:40 J+1 | 22:40 | 05:40 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 11/12-04-22 au JE/VE 14/15-04-22 | Def, V1, 1V/2, 07:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA15_0008998_110 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Chambery-Montmelian_010 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 10:19 | 11:19 | 10:26 | 11:26 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 10-01-22 au VE 13-05-22, du LU 03-10-22 au VE 04-11-22 et du LU 28-11-22 au VE 09-12-22 Sauf le(s) : LU 18-04-22,MA 01-11-22 | Def, V1, 1V/2, IPCS=2 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_110 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | DEF22_Chambery-Montmelian_011 | Chambéry-Challes-les-Eaux-AS | Chambéry-Poste-Bois-00 | 23:06 | 05:06 J+1 | 23:06 | 05:06 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 11/12-04-22 au JE/VE 14/15-04-22 | Def, V1,V2, 2V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA22_0023004_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Chambery-Montmelian_001 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 22:20 | 04:20 J+1 | 22:20 | 04:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 07/08-02-22 au JE/VE 12/13-05-22, du LU/MA 20/21-06-22 au LU/MA 04/05-07-22 et du LU/MA 22/23-08-22 au JE/VE 08/09-12-22 Sauf le(s) : LU/MA 18/19-04-22,JE/VE 25/26-08-22, MA/ME 01/02-11-22,JE/VE 10/11-11-22 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA22_0023004_03,CHA15_0008998_110,CHA22_0022870_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | FEN22_Chambery-Montmelian_002 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 06/07-02-22 au DI/LU 24/25-04-22, du DI/LU 12/13-06-22 au DI/LU 26/27-06-22 et du DI/LU 21/22-08-22 au DI/LU 04/05-12-22 Sauf le(s) : DI/LU 17/18-04-22,DI/LU 19/20-06-22, DI/LU 28/29-08-22 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_110,CHA22_0023004_03 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Chambery-Montmelian_003 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 00:51 | 04:27 | 00:51 | 04:27 | Jours d'application : LU Périodes : du LU 31-01-22 au LU 25-04-22, du LU 13-06-22 au LU 04-07-22 et du LU 22-08-22 au LU 05-12-22 Sauf le(s) : LU 18-04-22,LU 20-06-22 | Gen, V1,V2, 2V/2, 03:36, Nuit non passe-minuit, LU | CHA22_0023004_03,CHA15_0008998_110 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Chambery-Montmelian_008 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 09:54 | 10:54 | 10:02 | 11:02 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 07-01-22, du LU 16-05-22 au VE 30-09-22 et du LU 07-11-22 au VE 25-11-22 Sauf le(s) : JE 26-05-22,LU 06-06-22,JE 14-07-22, LU 15-08-22,VE 11-11-22 | Sur, V1, 1V/2, IPCS=2 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_110 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Chambery-Montmelian_009 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 10:17 | 11:17 | 10:11 | 11:11 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : LU 18-04-22,JE 26-05-22,LU 06-06-22, JE 14-07-22,LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, V2, 1V/2, IPCS=2 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_110 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP22_Montmelian(900000)_003 | Chambéry-Poste-Bois-00 | Montmélian-BV | 22:55 | 05:40 J+1 | 22:55 | 05:40 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 11/12-04-22 au JE/VE 14/15-04-22 | Cap, V1,V2, 06:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA15_0008998_111 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Montmelian(900000)_004 | Chambéry-Poste-Bois-00 | Montmélian-BV | 22:20 | 04:20 J+1 | 22:20 | 04:20 J+1 | Jours d'application : ME/JE,JE/VE Périodes : du ME/JE 09/10-03-22 au JE/VE 10/11-03-22 | Cap, V2, 06:00, Passe-minuit, ME/JE,JE/VE | CHA22_0022870_08,CHA15_0008998_111 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Montmelian-StPierre-d'Albigny_001 | Montmélian-BR | St-Pierre-d'Albigny-BV | 10:10 | 12:45 | 10:10 | 12:45 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 21-03-22 au VE 01-04-22 et du LU 24-10-22 au JE 10-11-22 Sauf le(s) : MA 01-11-22 | Def, V1,V2, 1V/2, IPCS=1 pas, 02:35, Jour, LU,MA,ME,JE,VE | CHA15_0008998_112 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Montmelian-StPierre-d'Albigny_013 | Montmélian-BR | St-Pierre-d'Albigny-BV | 10:26 | 11:26 | 10:31 | 11:31 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 10-01-22 au VE 13-05-22, du LU 03-10-22 au VE 04-11-22 et du LU 28-11-22 au VE 09-12-22 Sauf le(s) : LU 18-04-22,MA 01-11-22 | Def, V1, 1V/2, IPCS=1 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_112 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Montmelian-StPierre-d'Albigny_001 | Montmélian-BR | St-Pierre-d'Albigny-BV | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 07/08-02-22 au JE/VE 24/25-02-22, du LU/MA 07/08-03-22 au MA/ME 05/06-04-22, du LU/MA 09/10-05-22 au MA/ME 10/11-05-22, du LU/MA 30/31-05-22 au JE/VE 02/03-06-22, du LU/MA 29/30-08-22 au JE/VE 27/28-10-22 et du LU/MA 07/08-11-22 au JE/VE 08/09-12-22 Sauf le(s) : VE/SA 11/12-02-22,VE/SA 18/19-02-22, VE/SA 11/12-03-22,VE/SA 18/19-03-22, VE/SA 25/26-03-22,VE/SA 01/02-04-22, VE/SA 02/03-09-22,VE/SA 09/10-09-22, VE/SA 16/17-09-22,VE/SA 23/24-09-22,VE/SA 30/01-10-22, VE/SA 07/08-10-22,VE/SA 14/15-10-22,VE/SA 21/22-10-22, VE/SA 11/12-11-22,VE/SA 18/19-11-22, VE/SA 25/26-11-22, VE/SA 02/03-12-22 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA22_0022870_09,CHA15_0008998_112 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | FEN22_Montmelian-StPierre-d'Albigny_002 | Montmélian-BR | St-Pierre-d'Albigny-BV | 22:00 | 04:00 J+1 | 22:10 | 04:10 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 06/07-02-22 au DI/LU 03/04-04-22 et du DI/LU 04/05-09-22 au DI/LU 04/05-12-22 Et le(s) : DI/LU 29/30-05-22 et DI/LU 31/01-08-22 Sauf le(s) : DI/LU 27/28-02-22,DI/LU 27/28-11-22 | Gen, V1, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_112 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Montmelian-StPierre-d'Albigny_003 | Montmélian-BR | St-Pierre-d'Albigny-BV | 23:00 | 05:00 J+1 | 22:50 | 04:50 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 06/07-02-22 au DI/LU 03/04-04-22 et du DI/LU 04/05-09-22 au DI/LU 04/05-12-22 Et le(s) : DI/LU 03/04-07-22 et DI/LU 31/01-08-22 Sauf le(s) : DI/LU 27/28-02-22,DI/LU 27/28-11-22 | Gen, V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_112 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Montmelian-StPierre-d'Albigny_006 | Montmélian-BR | St-Pierre-d'Albigny-BV | 10:05 | 11:05 | 10:10 | 11:10 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 07-01-22, du LU 16-05-22 au VE 30-09-22 et du LU 07-11-22 au VE 25-11-22 Sauf le(s) : JE 26-05-22,LU 06-06-22,JE 14-07-22, LU 15-08-22,VE 11-11-22 | Sur, V1, 1V/2, IPCS=1 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_112 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Montmelian-StPierre-d'Albigny_007 | Montmélian-BR | St-Pierre-d'Albigny-BV | 10:05 | 11:05 | 10:00 | 11:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : LU 18-04-22,JE 26-05-22,LU 06-06-22, JE 14-07-22,LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, V2, 1V/2, IPCS=1 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_112 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP22_StPierre-d'Albigny_002 | St-Pierre-d'Albigny-BA | Chamousset-00 | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 04/05-09-22 au JE/VE 08/09-09-22, du DI/LU 16/17-10-22 au JE/VE 27/28-10-22 et du MA/ME 01/02-11-22 au JE/VE 17/18-11-22 | Cap, UNIQUE,V1, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA15_0008998_113 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StPierre-d'Albigny_003 | Montmélian-BR | Chamousset-00 | 23:30 | 05:00 J+1 | 23:30 | 05:00 J+1 | Jours d'application : LU/MA Périodes : Et le(s) : LU/MA 31/01-02-22 | Cap, 4E,V1,V2, 05:30, Passe-minuit, LU/MA | CHA17_0010710_236 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StPierre-Aiguebelle_001 | Plateforme AFA-00 | Aiguebelle-BV | 11:15 | 15:55 | 11:15 | 15:55 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 10-01-22 au VE 06-05-22 et du LU 03-10-22 au VE 28-10-22 Sauf le(s) : LU 18-04-22 | Cap, V1, IPCS=1 pas, 04:40, Jour, LU,MA,ME,JE,VE | CHA22_0022990_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StPierre-Aiguebelle_002 | Plateforme AFA-00 | Aiguebelle-BV | 10:05 | 16:05 | 10:05 | 16:05 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 14-03-22 au VE 18-03-22, du LU 27-06-22 au VE 08-07-22 et du LU 05-09-22 au VE 30-09-22 | Cap, V1, 06:00, Jour, LU,MA,ME,JE,VE | CHA22_0022990_07,CHA15_0008998_114 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StPierre-Aiguebelle_003 | Plateforme AFA-00 | Aiguebelle-BV | 16:00 | 12:00 J+1 | 16:00 | 12:00 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 16/17-07-22 | Cap, V1, IPCS=1 pas, 20:00, Passe-minuit, SA/DI | CHA22_0022990_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_StPierre-Aiguebelle_001 | St-Pierre-d'Albigny-BB | Aiguebelle-BV | 11:15 | 15:55 | 11:15 | 15:55 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 31-01-22 au VE 01-04-22 et du MA 26-04-22 au ME 27-04-22 et du JE 05-05-22 au VE 06-05-22 et du LU 03-10-22 au VE 28-10-22 Et le(s) : LU 10-01-22 | Def, V1,V2, 2V/2, IPCS=1 pas, 04:40, Jour, LU,MA,ME,JE,VE | CHA22_0022990_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_StPierre-Aiguebelle_005 | St-Pierre-d'Albigny-BB | Aiguebelle-BV | 16:00 | 11:56 J+1 | 16:00 | 11:56 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 16/17-07-22 | Def, V1,V2, 2V/2, IPCS=1 pas, 19:56, Passe-minuit, SA/DI | CHA22_0022990_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_StPierre-Aiguebelle_006 | Plateforme AFA-AI | Aiguebelle-BV | 23:06 | 06:08 J+1 | 23:06 | 06:08 J+1 | Jours d'application : LU/MA,MA/ME,DI/LU Périodes : du DI/LU 17/18-04-22 au MA/ME 19/20-04-22 | Def, V1,V2, 2V/2, 07:02, Passe-minuit, LU/MA,MA/ME,DI/LU | CHA15_0008998_114 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_StPierre-Aiguebelle_004 | St-Pierre-d'Albigny-BB | Aiguebelle-BV | 22:45 | 04:45 J+1 | 22:37 | 04:37 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 06/07-03-22 au DI/LU 03/04-04-22 et du DI/LU 04/05-09-22 au DI/LU 04/05-12-22 | Gen, V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_114 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_StPierre-Aiguebelle_007 | St-Pierre-d'Albigny-BB | Aiguebelle-BV | 10:05 | 16:05 | 10:05 | 16:05 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au MA 14-12-21 et du LU 31-01-22 au VE 01-04-22 et du JE 05-05-22 au VE 06-05-22 et du LU 16-05-22 au MA 17-05-22 et du LU 30-05-22 au VE 10-06-22 et du LU 27-06-22 au VE 01-07-22 et du ME 27-07-22 au JE 28-07-22 et du JE 01-09-22 au VE 28-10-22 et du ME 02-11-22 au VE 09-12-22 Et le(s) : LU 10-01-22 Sauf le(s) : LU 06-06-22,VE 11-11-22 | Gen, V1,V2, 1V/2, IPCS=3 pas, 06:00, Jour, LU,MA,ME,JE,VE | CHA22_0022870_11,CHA17_0010710_237 CHA15_0008998_114,CHA22_0022990_07 | NON | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_StPierre-Aiguebelle_008 | St-Pierre-d'Albigny-BB | Plateforme AFA-00 | 22:10 | 04:10 J+1 | 22:17 | 04:17 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 06/07-03-22 au DI/LU 03/04-04-22 et du DI/LU 04/05-09-22 au DI/LU 04/05-12-22 | Gen, V1, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_114 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aiguebelle-StAvre_004 | Plateforme AFA-AI | St-Avre-la-Chambre-AN | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 10-01-22 au VE 06-05-22 et du LU 03-10-22 au VE 28-10-22 Sauf le(s) : LU 18-04-22 | Def, V1,V2, 2V/2, 04:45, Jour, LU,MA,ME,JE,VE | CHA22_0022990_08,CHA22_0022777_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aiguebelle-StAvre_005 | Plateforme AFA-AI | St-Avre-la-Chambre-AN | 16:00 | 12:00 J+1 | 16:00 | 12:00 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 16/17-07-22 | Def, V1,V2, 2V/2, 20:00, Passe-minuit, SA/DI | CHA22_0022990_08 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aiguebelle-StAvre_012 | Épierre-St-Léger-1B | St-Avre-la-Chambre-AN | 13:00 | 16:00 | 13:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 16-05-22 au ME 25-05-22, du LU 30-05-22 au VE 10-06-22, du LU 04-07-22 au ME 13-07-22 et du LU 18-07-22 au VE 22-07-22 Sauf le(s) : LU 06-06-22 | Def, V1,V2, 2V/2, 03:00, Jour, LU,MA,ME,JE,VE | CHA22_0022777_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aiguebelle-StAvre_013 | Aiguebelle-BV | St-Avre-la-Chambre-BV | 23:02 | 06:01 J+1 | 23:02 | 06:01 J+1 | Jours d'application : ME/JE,JE/VE Périodes : du ME/JE 20/21-04-22 au JE/VE 21/22-04-22 | Def, V1,V2, 2V/2, 06:59, Passe-minuit, ME/JE,JE/VE | CHA15_0008998_115 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Aiguebelle-StAvre_001 | Plateforme AFA-AI | St-Avre-la-Chambre-AN | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au JE 16-12-21, du LU 31-01-22 au MA 10-05-22, du LU 16-05-22 au ME 25-05-22, du LU 30-05-22 au VE 10-06-22, du LU 04-07-22 au ME 13-07-22, du LU 18-07-22 au VE 22-07-22, du LU 29-08-22 au VE 28-10-22 et du ME 02-11-22 au VE 09-12-22 Sauf le(s) : LU 18-04-22,LU 06-06-22,VE 11-11-22 | Gen, V1,V2, 1V/2, 06:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_115CHA17_0010710_238,CHA22_0022870_12,CHA22_0022777_03,CHA22_0022990_08 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Aiguebelle-StAvre_002 | Plateforme AFA-AI | St-Avre-la-Chambre-AN | 22:17 | 04:17 J+1 | 22:33 | 04:33 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 06/07-03-22 au DI/LU 03/04-04-22 et du DI/LU 04/05-09-22 au DI/LU 04/05-12-22 Et le(s) : DI/LU 24/25-04-22 | Gen, V1, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_115 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Aiguebelle-StAvre_003 | Plateforme AFA-AI | St-Avre-la-Chambre-AN | 22:37 | 04:37 J+1 | 22:24 | 04:24 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 06/07-03-22 au DI/LU 03/04-04-22 et du DI/LU 04/05-09-22 au DI/LU 04/05-12-22 Et le(s) : DI/LU 24/25-04-22 | Gen, V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_115 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StAvre_001 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 10-01-22 au VE 18-03-22, du LU 04-04-22 au VE 13-05-22, du LU 03-10-22 au VE 28-10-22, du ME 02-11-22 au VE 04-11-22 et du LU 28-11-22 au VE 09-12-22 Sauf le(s) : LU 18-04-22 | Cap, Gen,V1,V2, 04:45, Jour, LU,MA,ME,JE,VE | CHA22_0022777_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP22_StAvre_005 | St-Avre-la-Chambre-BV | St-Avre-la-Chambre-RL | 13:00 | 16:00 | 13:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 16-05-22 au ME 25-05-22, du LU 30-05-22 au ME 13-07-22 et du LU 18-07-22 au VE 26-08-22 Sauf le(s) : LU 06-06-22,LU 15-08-22 | Cap, Gen,V1,V2, 03:00, Jour, LU,MA,ME,JE,VE | CHA22_0022777_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StAvre_009 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 10:22 | 16:00 | 10:22 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 18-07-22 au VE 26-08-22 et du LU 07-11-22 au VE 25-11-22 Sauf le(s) : LU 15-08-22,VE 11-11-22 | Cap, V1,V2, 05:38, Jour, LU,MA,ME,JE,VE | CHA22_0022777_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StAvre_010 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 13:00 | 16:00 | 13:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 18-07-22 au VE 26-08-22 et du LU 07-11-22 au VE 25-11-22 Sauf le(s) : LU 15-08-22,VE 11-11-22 | Cap, V1,V2, 03:00, Jour, LU,MA,ME,JE,VE | CHA22_0022777_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StAvre_011 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 22:35 | 05:26 J+1 | 22:35 | 05:26 J+1 | Jours d'application : LU/MA,MA/ME Périodes : du LU/MA 25/26-04-22 au MA/ME 26/27-04-22 | Cap, Gen,V1,V2, 06:51, Passe-minuit, LU/MA,MA/ME | CHA15_0008998_116 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StAvre_012 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 22:35 | 05:35 J+1 | 22:35 | 05:35 J+1 | Jours d'application : ME/JE,JE/VE Périodes : du ME/JE 27/28-04-22 au JE/VE 28/29-04-22 | Cap, Gen,1BIS,V1, 07:00, Passe-minuit, ME/JE,JE/VE | CHA15_0008998_116 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StAvre_013 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 10:20 | 16:00 | 10:20 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 24-01-22 au ME 26-01-22 et du JE 10-02-22 au MA 15-02-22 | Cap, V1,V2, 05:40, Jour, LU,MA,ME,JE,VE | CHA17_0010710_239 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_StAvre-StJean_002 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 10-01-22 au VE 18-03-22, du LU 04-04-22 au LU 09-05-22, du LU 03-10-22 au VE 28-10-22, du ME 02-11-22 au VE 04-11-22 et du LU 28-11-22 au VE 09-12-22 Et le(s) : VE 13-05-22 Sauf le(s) : LU 18-04-22 | Def, V1,V2, 2V/2, IPCS=2 pas, 04:45, Jour, LU,MA,ME,JE,VE | CHA22_0022777_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | DEF22_StAvre-StJean_010 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 13:00 | 16:00 | 13:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 18-07-22 au VE 30-09-22 et du LU 07-11-22 au VE 25-11-22 Sauf le(s) : LU 15-08-22,VE 11-11-22 | Def, V1,V2, 2V/2, IPCS=2 pas, 03:00, Jour, LU,MA,ME,JE,VE | CHA22_0022777_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_StAvre-StJean_001 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au LU 09-05-22, du VE 13-05-22 au ME 25-05-22, du LU 30-05-22 au ME 13-07-22, du LU 18-07-22 au VE 28-10-22 et du ME 02-11-22 au VE 09-12-22 Sauf le(s) : LU 18-04-22,LU 06-06-22,VE 01-07-22, LU 15-08-22,VE 11-11-22 | Gen, V1,V2, 1V/2, 06:00, Jour, LU,MA,ME,JE,VE | CHA22_0022777_05,CHA17_0010710_240CHA15_0008998_117 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_StAvre-StJean_002 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 22:38 | 04:38 J+1 | 22:45 | 04:45 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 06/07-03-22 au DI/LU 03/04-04-22 et du DI/LU 04/05-09-22 au DI/LU 04/05-12-22 Et le(s) : DI/LU 24/25-04-22 | Gen, V1, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_117 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_StAvre-StJean_003 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 22:24 | 04:24 J+1 | 22:17 | 04:17 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 06/07-03-22 au DI/LU 03/04-04-22 et du DI/LU 04/05-09-22 au DI/LU 04/05-12-22 Et le(s) : DI/LU 24/25-04-22 | Gen, V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_117 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StJean_001 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-FR | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 10-01-22 au VE 18-03-22 et du LU 04-04-22 au VE 13-05-22 Sauf le(s) : LU 18-04-22 | Cap, V1,V2, 04:45, Jour, LU,MA,ME,JE,VE | CHA22_0022777_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StJean_011 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-TR | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 03-10-22 au VE 28-10-22, du ME 02-11-22 au VE 04-11-22 et du LU 28-11-22 au VE 09-12-22 | Cap, V1,V2, 04:45, Jour, LU,MA,ME,JE,VE | CHA22_0022777_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP22_StJean_012 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-FR | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 16-05-22 au ME 25-05-22 | Cap, V2, 06:00, Jour, LU,MA,ME,JE,VE | CHA22_0022777_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StJean_013 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-TR | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 18-07-22 au VE 30-09-22 et du LU 07-11-22 au VE 25-11-22 Sauf le(s) : LU 15-08-22,VE 11-11-22 | Cap, V1,V2, 06:00, Jour, LU,MA,ME,JE,VE | CHA22_0022777_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StJean_015 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-TR | 13:00 | 16:00 | 13:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 18-07-22 au VE 30-09-22 et du LU 07-11-22 au VE 25-11-22 Sauf le(s) : LU 15-08-22,VE 11-11-22 | Cap, V1,V2, 03:00, Jour, LU,MA,ME,JE,VE | CHA22_0022777_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StJean_016 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-FR | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : MA,ME,JE,VE Périodes : du ME 26-01-22 au VE 28-01-22 et du MA 08-02-22 au JE 10-02-22 | Cap, V1,V2, 06:00, Jour, MA,ME,JE,VE | CHA17_0010710_241 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StJean_019 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-FR | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 26-09-22 au VE 07-10-22 | Cap, V1, 06:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_118 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_StJean_020 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-FR | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 10-10-22 au VE 21-10-22 | Cap, V2, 06:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_118 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_StJean-Modane_001 | St-Jean-de-Maurienne-Arvan-P1 | Modane-AG | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 29-04-22 et du LU 31-10-22 au VE 09-12-22 Sauf le(s) : LU 18-04-22,VE 11-11-22 | Def, V1,V2, 1V/2, IPCS=1 pas, 06:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_119 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | DEF22_StJean-Modane_002 | St-Jean-de-Maurienne-Arvan-P1 | Modane-Berchette-00 | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 31-01-22 au VE 18-03-22, du LU 04-04-22 au VE 29-04-22, du LU 03-10-22 au VE 28-10-22, du ME 02-11-22 au VE 04-11-22 et du LU 28-11-22 au VE 09-12-22 Sauf le(s) : LU 18-04-22 | Def, V1,V2, 2V/2, IPCS=1 pas, 04:45, Jour, LU,MA,ME,JE,VE | CHA22_0022777_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | DEF22_StJean-Modane_016 | St-Jean-de-Maurienne-Arvan-P1 | Modane-Berchette-00 | 13:00 | 16:00 | 13:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 04-07-22 au ME 13-07-22, du LU 29-08-22 au VE 30-09-22 et du LU 07-11-22 au VE 25-11-22 Sauf le(s) : VE 11-11-22 | Def, V1,V2, 2V/2, 03:00, Jour, LU,MA,ME,JE,VE | CHA22_0022777_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_StJean-Modane_017 | St-Jean-de-Maurienne-Arvan-P1 | Modane-Berchette-00 | 16:15 | 12:00 J+1 | 16:15 | 12:00 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 16/17-07-22 | Def, V1,V2, 2V/2, 19:45, Passe-minuit, SA/DI | CHA22_0022777_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF22_StJean-Modane_019 | St-Jean-de-Maurienne-Arvan-P1 | Modane-Berchette-00 | 23:20 | 23:20 J+4 | 23:20 | 23:20 J+4 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 28-10-22 au MA 01-11-22 | Def, V1,V2, 2V/2, IPCS=2 pas, 96:00, Continu, LU,MA,VE,SA,DI | CHA22_0022691_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_StJean-Modane_020 | St-Jean-de-Maurienne-Arvan-P1 | Modane-AG | 10:00 | 14:55 | 10:00 | 14:55 | Jours d'application : VE Périodes : Et le(s) : VE 11-11-22 | Def, V1,V2, 1V/2, IPCS=1 pas, 04:55, Jour, VE | CHA15_0008998_119 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_StJean-Modane_001 | St-Jean-de-Maurienne-Arvan-P1 | Modane-AG | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du JE 27-01-22 au ME 25-05-22, du LU 30-05-22 au ME 13-07-22, du LU 18-07-22 au VE 29-07-22, du LU 29-08-22 au VE 28-10-22 et du ME 02-11-22 au VE 09-12-22 Et le(s) : ME 10-08-22 Sauf le(s) : LU 18-04-22,MA 10-05-22,LU 06-06-22, VE 01-07-22,VE 11-11-22 | Gen, V1,V2, 1V/2, 06:00, Jour, LU,MA,ME,JE,VE | CHA17_0010710_242,CHA22_0022777_07,CHA15_0008998_119 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_StJean-Modane_002 | St-Jean-de-Maurienne-Arvan-P1 | Modane-AG | 22:38 | 04:38 J+1 | 22:58 | 04:58 J+1 | Jours d'application : SA/DI,DI/LU Périodes : du DI/LU 06/07-03-22 au DI/LU 03/04-04-22, du DI/LU 04/05-09-22 au DI/LU 16/17-10-22 et du DI/LU 06/07-11-22 au DI/LU 20/21-11-22 Et le(s) : DI/LU 24/25-04-22 et DI/LU 04/05-12-22 Sauf le(s) : SA/DI 12/13-03-22,SA/DI 19/20-03-22, SA/DI 26/27-03-22,SA/DI 02/03-04-22, SA/DI 10/11-09-22,SA/DI 17/18-09-22, SA/DI 24/25-09-22,SA/DI 01/02-10-22, SA/DI 08/09-10-22,SA/DI 15/16-10-22, SA/DI 12/13-11-22,SA/DI 19/20-11-22 | Gen, V1, 1V/2, 06:00, Passe-minuit, SA/DI,DI/LU | CHA15_0008998_119 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_StJean-Modane_003 | St-Jean-de-Maurienne-Arvan-P1 | Modane-AG | 22:17 | 04:17 J+1 | 22:00 | 04:00 J+1 | Jours d'application : SA/DI,DI/LU Périodes : du DI/LU 06/07-03-22 au DI/LU 03/04-04-22, du DI/LU 04/05-09-22 au DI/LU 16/17-10-22 et du DI/LU 06/07-11-22 au DI/LU 20/21-11-22 Et le(s) : DI/LU 24/25-04-22 et DI/LU 04/05-12-22 Sauf le(s) : SA/DI 12/13-03-22,SA/DI 19/20-03-22, SA/DI 26/27-03-22,SA/DI 02/03-04-22, SA/DI 10/11-09-22,SA/DI 17/18-09-22, SA/DI 24/25-09-22,SA/DI 01/02-10-22, SA/DI 08/09-10-22,SA/DI 15/16-10-22, SA/DI 12/13-11-22,SA/DI 19/20-11-22 | Gen, V2, 1V/2, 06:00, Passe-minuit, SA/DI,DI/LU | CHA15_0008998_119 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Modane_008 | La Praz-00 | Modane-XI | 23:20 | 05:00 J+1 | 23:20 | 05:00 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 30/31-01-22 au DI/LU 06/07-02-22 | Cap, B,D,E,V1,V2, 05:40, Passe-minuit, DI/LU | CHA17_0010710_295 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SNCF RESEAU - WORKS TT2023 - AMBERIEU-MODANE
| =Total closure >12 hrs | [11 empty] | 2022 | [20 empty] | 2023
| = border point Modane | [11 empty] | DEC | [20 empty] | JAN | [30 empty] | FEV | [27 empty] | MAR | [30 empty] | AVR | [29 empty] | MAI | [30 empty] | JUN | [29 empty] | JUL | [30 empty] | AOU | [30 empty] | SEP | [29 empty] | OCT | [30 empty] | NOV | [29 empty] | DEC
Total closure >12 hrs ? | Border point ? | Identifiant Ressource | Localisation : Starting point | Localisation : Ending point | Start Time Starting point | End Time Starting point | Start Time Ending point | End Time Ending point | Days of activation (night works are identified by : Day1 /Day2) Period of activation | Type of works | Worksites | Weekend | 49 | 50 | [6 empty] | 51 | [6 empty] | 52 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40 | [6 empty] | 41 | [6 empty] | 42 | [6 empty] | 43 | [6 empty] | 44 | [6 empty] | 45 | [6 empty] | 46 | [6 empty] | 47 | [6 empty] | 48 | [6 empty] | 49
|  | DEF23_Amberieu-Culoz_001 | Ambérieu-P4 | Culoz-AE | 22:35 | 04:50 J+1 | 22:35 | 04:50 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du MA/ME 02/03-05-23 au JE/VE 25/26-05-23 et du DI/LU 17/18-09-23 au JE/VE 28/29-09-23 | Def, V1,V2, 2V/2, 06:15, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA15_0008984_54 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Amberieu-Culoz_002 | Ambérieu-P4 | Culoz-AE | 11:10 | 16:10 | 11:10 | 16:10 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 23-01-23 au VE 03-02-23 et du LU 09-10-23 au VE 20-10-23 | Def, V1,V2, 1V/2, IPCS=1 pas, 05:00, Jour, LU,MA,ME,JE,VE | CHA23_0025499_14 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Amberieu-Culoz_005 | Ambérieu-P4 | Aig IPCS Km 642-00 | 00:05 | 05:00 | 00:05 | 05:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 03-07-23 au VE 04-08-23 Sauf le(s) : VE 14-07-23 | Def, V1,V2, 2V/2, 04:55, Nuit non passe-minuit, LU,MA,ME,JE,VE | CHA23_0024416_01, CHA23_0024504_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_Amberieu-Culoz_010 | Ambérieu-P4 | Tenay-Hauteville-00 | 21:20 | 20:45 J+3 | 21:20 | 20:45 J+3 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du JE 13-07-23 au DI 16-07-23 | Def, V1,V2, 2V/2, 71:25, Continu, JE,VE,SA,DI | CHA23_0024504_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Amberieu-Culoz_011 | Ambérieu-P4 | Tenay-Hauteville-00 | 21:20 | 19:55 J+1 | 21:20 | 19:55 J+1 | Jours d'application : VE/SA Périodes : Et le(s) : VE/SA 21/22-07-23 | Def, V1,V2, 2V/2, 22:35, Passe-minuit, VE/SA | CHA23_0024416_01, CHA23_0024504_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Amberieu-Culoz_001 | Ambérieu-P4 | Culoz-AE | 22:25 | 04:25 J+1 | 22:25 | 04:25 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 12/13-12-22 au JE/VE 15/16-12-22, du LU/MA 09/10-01-23 au JE/VE 06/07-07-23, du LU/MA 24/25-07-23 au JE/VE 03/04-08-23 et du LU/MA 28/29-08-23 au JE/VE 07/08-12-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23,LU/MA 08/09-05-23, JE/VE 18/19-05-23,LU/MA 29/30-05-23,ME/JE 01/02-11-23 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA23_0024535_01, CHA15_0008984_54 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | FEN23_Amberieu-Culoz_002 | Ambérieu-P4 | Culoz-AE | 22:03 | 04:03 J+1 | 22:03 | 04:03 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 08/09-01-23 au DI/LU 23/24-04-23, du DI/LU 14/15-05-23 au DI/LU 30/31-07-23 et du DI/LU 20/21-08-23 au DI/LU 03/04-12-23 Et le(s) : DI/LU 11/12-12-22 Sauf le(s) : DI/LU 09/10-04-23,DI/LU 28/29-05-23,DI/LU 09/10-07-23 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008984_54 | OUI | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Amberieu-Culoz_003 | Ambérieu-P4 | Culoz-AE | 00:03 | 04:03 | 00:03 | 04:03 | Jours d'application : LU Périodes : du LU 09-01-23 au LU 24-04-23, du LU 15-05-23 au LU 31-07-23 et du LU 21-08-23 au LU 04-12-23 Et le(s) : LU 12-12-22 Sauf le(s) : LU 10-04-23,LU 29-05-23,LU 10-07-23 | Gen, V1,V2, 2V/2, 04:00, Nuit non passe-minuit, LU | CHA15_0008984_54 | NON | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Amberieu-Culoz_008 | Ambérieu-P4 | Culoz-AE | 15:05 | 16:05 | 15:34 | 16:34 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au ME 17-05-23, du LU 22-05-23 au VE 11-08-23 et du ME 16-08-23 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,LU 29-05-23,VE 14-07-23, ME 01-11-23 | Sur, V1, 1V/2, IPCS=4 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008984_54 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_Amberieu-Culoz_009 | Ambérieu-P4 | Culoz-AE | 11:22 | 12:22 | 10:59 | 11:59 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au ME 17-05-23 du LU 22-05-23 au VE 11-08-23 et du ME 16-08-23 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,LU 29-05-23,VE 14-07-23, ME 01-11-23 | Sur, V2, 1V/2, IPCS=4 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008984_54 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_Culoz_001 | Culoz-V3 | Culoz-S1 | 13:42 | 15:40 | 13:42 | 15:40 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 19-06-23 au VE 07-07-23 | Cap, V1, 01:58, Jour, LU,MA,ME,JE,VE | CHA15_0008984_55 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Culoz_005 | Virieu-le-Grand-Belley-BV | Culoz-BV | 22:20 | 04:20 J+1 | 22:20 | 04:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 27/28-02-23 au JE/VE 16/17-03-23 | Cap, V2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA15_0008984_55 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Culoz_008 | Culoz-V3 | - | 10:50 | 12:25 | 10:50 | 12:25 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 19-06-23 au VE 07-07-23 | Cap, UNIQUE,V2, 01:35, Jour, LU,MA,ME,JE,VE | CHA15_0008984_55 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Culoz_010 | Virieu-le-Grand-Belley-BV | Vions-Chanaz-00 | 22:35 | 04:50 J+1 | 22:35 | 04:50 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du MA/ME 02/03-05-23 au JE/VE 25/26-05-23 | Cap, 4C,C,CG,UNIQUE,V1,V1,V2,V2, 06:15, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA15_0008984_55 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Culoz-AixLesBains_008 | Chindrieux-00 | Aix-les-Bains-Le Revard-P1 | 21:51 | 05:34 J+1 | 21:51 | 05:34 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du LU/MA 01/02-05-23 au ME/JE 17/18-05-23 Sauf le(s) : DI/LU 07/08-05-23 | Def, V1,V2, 2V/2, 07:43, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024220_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Culoz-AixLesBains_009 | Chindrieux-00 | Aix-les-Bains-Le Revard-P1 | 20:56 | 05:34 J+1 | 20:56 | 05:34 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 21/22-05-23 au JE/VE 28/29-09-23 Sauf le(s) : DI/LU 28/29-05-23 | Def, V1,V2, 1V/2, 08:38, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024220_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Culoz-AixLesBains_010 | Chindrieux-00 | Aix-les-Bains-Le Revard-P1 | 00:48 | 04:00 | 00:48 | 04:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 22-05-23 au VE 01-09-23 Sauf le(s) : LU 29-05-23 | Def, V1,V2, 2V/2, 03:12, Nuit non passe-minuit, LU,MA,ME,JE,VE | CHA23_0024220_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Culoz-AixLesBains_001 | Culoz-BG | Aix-les-Bains-Le Revard-P1 | 22:20 | 04:20 J+1 | 22:20 | 04:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 12/13-12-22 au JE/VE 15/16-12-22 du LU/MA 02/03-01-23 au JE/VE 10/11-08-23 et du LU/MA 21/22-08-23 au JE/VE 07/08-12-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23,LU/MA 08/09-05-23, JE/VE 18/19-05-23,LU/MA 29/30-05-23 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA15_0008998_122,CHA23_0024220_01 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | FEN23_Culoz-AixLesBains_002 | Culoz-BG | Aix-les-Bains-Le Revard-P1 | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 08/09-01-23 au DI/LU 26/27-03-23 du DI/LU 16/17-04-23 au DI/LU 23/24-04-23 et du DI/LU 14/15-05-23 au DI/LU 03/04-12-23 Et le(s) : DI/LU 11/12-12-22 Sauf le(s) : DI/LU 28/29-05-23,DI/LU 13/14-08-23 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_122,CHA23_0024220_01 | OUI | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Culoz-AixLesBains_003 | Culoz-BG | Aix-les-Bains-Le Revard-P1 | 00:34 | 04:42 | 00:34 | 04:42 | Jours d'application : LU Périodes : du LU 09-01-23 au LU 27-03-23 du LU 17-04-23 au LU 24-04-23 et du LU 15-05-23 au LU 04-12-23 Et le(s) : LU 12-12-22 Sauf le(s) : LU 29-05-23,LU 14-08-23 | Gen, V1,V2, 2V/2, 04:08, Nuit non passe-minuit, LU | CHA15_0008998_122,CHA23_0024220_01 | NON | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Culoz-AixLesBains_008 | Culoz-BG | Aix-les-Bains-Le Revard-P1 | 11:30 | 12:30 | 11:45 | 12:45 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 16-12-22 du LU 09-01-23 au ME 17-05-23 du LU 22-05-23 au VE 04-08-23 et du LU 21-08-23 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,LU 29-05-23,VE 14-07-23, ME 01-11-23 | Sur, V1, 1V/2, IPCS=1 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_122 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_Culoz-AixLesBains_009 | Culoz-BG | Aix-les-Bains-Le Revard-BV | 10:55 | 11:55 | 10:42 | 11:42 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 16-12-22, du LU 09-01-23 au ME 17-05-23, du LU 22-05-23 au VE 04-08-23 et du LU 21-08-23 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,LU 29-05-23,VE 14-07-23, ME 01-11-23 | Sur, V2, 1V/2, IPCS=1 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_122 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_AixLesBains_008 | Aix-les-Bains-Le Revard-BV | Aix-les-Bains-Le Revard-P2 | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 02/03-04-23 au JE/VE 13/14-04-23 du DI/LU 23/24-04-23 au JE/VE 27/28-04-23 et du DI/LU 21/22-05-23 au JE/VE 25/26-05-23 | Cap, TN,UNIQUE,V1, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024930_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_AixLesBains_011 | Aix-les-Bains-Le Revard-BV | Viviers-du-Lac-00 | 22:05 | 05:34 J+1 | 22:05 | 05:34 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,SA/DI,DI/LU Périodes : du LU/MA 01/02-05-23 au JE/VE 04/05-05-23 du LU/MA 08/09-05-23 au ME/JE 17/18-05-23 et du SA/DI 16/17-09-23 au DI/LU 17/18-09-23 Sauf le(s) : SA/DI 13/14-05-23 | Cap, C,D,E,EV,S,TC,TN,UNIQUE,UNIQUE,V1,V2, 07:29, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,SA/DI,DI/LU | CHA23_0024930_02, CHA15_0008998_123 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_AixLesBains_014 | Aix-les-Bains-Le Revard-BV | Viviers-du-Lac-00 | 23:54 | 04:57 J+1 | 23:54 | 04:57 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 21/22-05-23 au JE/VE 08/09-06-23 | Cap, C,D,E,EV,S,TC,TN,UNIQUE,UNIQUE,V1,V2, 05:03, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA15_0008998_123 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_AixLesBains_015 | Aix-les-Bains-Le Revard-BV | Viviers-du-Lac-00 | 23:15 | 05:24 J+1 | 23:15 | 05:24 J+1 | Jours d'application : DI/LU Périodes : Et le(s) : DI/LU 19/20-03-23 | Cap, EV,V1,V2, 06:09, Passe-minuit, DI/LU | CHA15_0008998_123 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_AixLesBains_016 | Aix-les-Bains-Le Revard-BV | Viviers-du-Lac-00 | 23:15 | 05:25 J+1 | 23:15 | 05:25 J+1 | Jours d'application : LU/MA,MA/ME Périodes : du LU/MA 20/21-03-23 au MA/ME 21/22-03-23 | Cap, EV,V2, 06:10, Passe-minuit, LU/MA,MA/ME | CHA15_0008998_123 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_AixLesBains_017 | Aix-les-Bains-Le Revard-P1 | Viviers-du-Lac-00 | 23:15 | 05:24 J+1 | 23:15 | 05:24 J+1 | Jours d'application : LU/MA,MA/ME Périodes : du LU/MA 20/21-03-23 au MA/ME 21/22-03-23 | Cap, EV,V1, 06:09, Passe-minuit, LU/MA,MA/ME | CHA15_0008998_123 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_AixLesBains-Chambery_002 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 21:40 | 05:35 J+1 | 21:40 | 05:35 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 09/10-04-23 au JE/VE 27/28-04-23 | Def, V2, 1V/2, 07:55, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024347_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_AixLesBains-Chambery_003 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 22:35 | 05:00 J+1 | 22:35 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du LU/MA 01/02-05-23 au JE/VE 25/26-05-23 Sauf le(s) : DI/LU 07/08-05-23,JE/VE 18/19-05-23 | Def, V1,V2, 2V/2, 06:25, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024781_02, CHA23_0025357_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_AixLesBains-Chambery_004 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 22:35 | 05:20 J+1 | 22:35 | 05:20 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 04/05-06-23 au DI/LU 23/24-07-23 | Def, V1,V2, 2V/2, 06:45, Passe-minuit, DI/LU | CHA23_0024781_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_AixLesBains-Chambery_001 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 22:20 | 04:20 J+1 | 22:20 | 04:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 12/13-12-22 au JE/VE 15/16-12-22 du LU/MA 02/03-01-23 au MA/ME 31/01-11-23 et du LU/MA 06/07-11-23 au JE/VE 07/08-12-23 Sauf le(s) : JE/VE 18/19-05-23,LU/MA 14/15-08-23 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA15_0008998_124, CHA23_0025375_02, CHA23_0024347_04, CHA23_0024781_02, CHA23_0025357_05 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 3 | 4 | 4 | 4 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | FEN23_AixLesBains-Chambery_002 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 08/09-01-23 au DI/LU 23/24-04-23 et du DI/LU 14/15-05-23 au DI/LU 03/04-12-23 Et le(s) : DI/LU 11/12-12-22 Sauf le(s) : DI/LU 09/10-04-23,DI/LU 28/29-05-23 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_124,CHA23_0024347_04, CHA23_0024781_02, CHA23_0025375_02, CHA23_0025357_05 | OUI | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_AixLesBains-Chambery_003 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 00:34 | 04:34 | 00:34 | 04:34 | Jours d'application : LU Périodes : du LU 09-01-23 au LU 24-04-23 et du LU 15-05-23 au LU 04-12-23 Et le(s) : LU 12-12-22 Sauf le(s) : LU 10-04-23,LU 29-05-23 | Gen, V1,V2, 2V/2, 04:00, Nuit non passe-minuit, LU | CHA15_0008998_124,CHA23_0025375_02, CHA23_0024781_02 | NON | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  | FEN23_AixLesBains-Chambery_008 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 11:50 | 12:50 | 11:58 | 12:58 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 16-12-22 du LU 09-01-23 au ME 17-05-23 du LU 22-05-23 au VE 04-08-23 et du LU 21-08-23 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,LU 29-05-23,VE 14-07-23, ME 01-11-23 | Sur, V1, 1V/2, IPCS=1 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_124 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_AixLesBains-Chambery_009 | Aix-les-Bains-Le Revard-P2 | Chambéry-Challes-les-Eaux-AN | 10:37 | 11:37 | 10:28 | 11:28 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 16-12-22 du LU 09-01-23 au ME 17-05-23 du LU 22-05-23 au VE 04-08-23 et du LU 21-08-23 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,LU 29-05-23,VE 14-07-23, ME 01-11-23 | Sur, V2, 1V/2, IPCS=1 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_124 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_Chambery_001 | Viviers-du-Lac-00 | - | 23:30 | 04:15 J+1 | 23:30 | 04:15 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 16/17-07-23 au JE/VE 10/11-08-23 | Cap, 4I,C,D,E,V1,V2,VM1,VM2, 04:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA15_0008998_125 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Chambery_003 | Viviers-du-Lac-00 | Chambéry-Challes-les-Eaux-DP | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 08/09-01-23 au DI/LU 29/30-01-23 du DI/LU 26/27-03-23 au DI/LU 02/03-04-23 et du DI/LU 14/15-05-23 au DI/LU 21/22-05-23 | Cap, V2, 06:00, Passe-minuit, DI/LU | CHA23_0024347_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Chambery_004 | Viviers-du-Lac-00 | Chambéry-Challes-les-Eaux-DP | 22:20 | 04:20 J+1 | 22:20 | 04:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 09/10-01-23 au JE/VE 02/03-02-23 du LU/MA 27/28-03-23 au JE/VE 06/07-04-23 et du LU/MA 01/02-05-23 au JE/VE 01/02-06-23 | Cap, V2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA23_0024347_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Chambery_005 | Viviers-du-Lac-00 | Chambéry-Challes-les-Eaux-DP | 21:40 | 05:35 J+1 | 21:40 | 05:35 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 09/10-04-23 au JE/VE 27/28-04-23 | Cap, V2, 07:55, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024347_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Chambery_006 | Chambéry-Challes-les-Eaux-DP | Chambéry-Challes-les-Eaux-DP | 23:35 | 05:35 J+1 | 23:35 | 05:35 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 09/10-04-23 au JE/VE 27/28-04-23 | Cap, 4I, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024347_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Chambery_007 | Viviers-du-Lac-00 | Chambéry-Challes-les-Eaux-AS | 23:35 | 05:35 J+1 | 23:35 | 05:35 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 09/10-04-23 au JE/VE 27/28-04-23 | Cap, V2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024347_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Chambery_008 | Chambéry-Challes-les-Eaux-DP | Chambéry-Challes-les-Eaux-AS | 20:59 | 04:30 J+1 | 20:59 | 04:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 05/06-02-23 au JE/VE 06/07-04-23 | Cap, C,D,E, 07:31, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024356_01, CHA23_0024294_03, CHA23_0024756_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Chambery_009 | Chambéry-Challes-les-Eaux-DP | Chambéry-Challes-les-Eaux-AS | 20:59 | 04:30 J+1 | 20:59 | 04:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 09/10-04-23 au JE/VE 27/28-04-23 | Cap, D,E, 07:31, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024356_01, CHA23_0024294_03, CHA23_0024756_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Chambery_010 | Chambéry-Challes-les-Eaux-DP | Chambéry-Challes-les-Eaux-AS | 21:40 | 05:15 J+1 | 21:40 | 05:15 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 27/28-08-23 au JE/VE 05/06-10-23 et du DI/LU 29/30-10-23 au JE/VE 30/01-12-23 | Cap, 4I,V1,V2, 07:35, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024356_01 ,CHA23_0024756_03, CHA23_0024294_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | CAP23_Chambery_011 | Chambéry-Challes-les-Eaux-DP | Chambéry-Challes-les-Eaux-AS | 22:00 | 10:00 J+2 | 22:00 | 10:00 J+2 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du SA 06-05-23 au LU 08-05-23 | Cap, C,D, 36:00, Continu, LU,SA,DI | CHA23_0024356_01, CHA23_0024294_03, CHA23_0024756_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Chambery_013 | Chambéry-Challes-les-Eaux-DP | Chambéry-Challes-les-Eaux-AS | 21:40 | 05:15 J+1 | 21:40 | 05:15 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du MA/ME 02/03-05-23 au JE/VE 01/02-06-23 Sauf le(s) : DI/LU 07/08-05-23,JE/VE 18/19-05-23,DI/LU 28/29-05-23 | Cap, C,V1,V2, 07:35, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024294_03, CHA23_0024756_03, CHA23_0024356_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Chambery_014 | Chambéry-Challes-les-Eaux-DP | Chambéry-Challes-les-Eaux-AS | 20:59 | 04:30 J+1 | 20:59 | 04:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 04/05-06-23 au JE/VE 06/07-07-23 | Cap, C,D,V1, 07:31, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024294_03, CHA23_0024356_01, CHA23_0024756_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Chambery_015 | Chambéry-Challes-les-Eaux-DP | Chambéry-Challes-les-Eaux-AS | 20:59 | 04:30 J+1 | 20:59 | 04:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 09/10-07-23 au JE/VE 27/28-07-23 | Cap, C,D,V1, 07:31, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024756_03, CHA23_0024356_01, CHA23_0024294_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Chambery_016 | Chambéry-Challes-les-Eaux-DP | Chambéry-Challes-les-Eaux-AS | 21:40 | 05:15 J+1 | 21:40 | 05:15 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 30/31-07-23 au JE/VE 24/25-08-23 | Cap, C,V1,V2, 07:35, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024294_03, CHA23_0024356_01, CHA23_0024756_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Chambery_018 | Chambéry-Challes-les-Eaux-BV | Chambéry-Poste-Bois-00 | 23:30 | 04:15 J+1 | 23:30 | 04:15 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 02/03-07-23 au ME/JE 12/13-07-23 | Cap, V1,V2, 04:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA15_0008998_125 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Chambery_019 | Chambéry-Challes-les-Eaux-DP | Chambéry-Challes-les-Eaux-AS | 22:00 | 05:00 J+1 | 22:00 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 08/09-10-23 au JE/VE 26/27-10-23 | Cap, 4I,V2, 07:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024756_03, CHA23_0024356_01, CHA23_0024294_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Chambery-Montmelian_004 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 10:19 | 11:19 | 10:27 | 11:27 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 16-01-23 au VE 10-02-23 du LU 13-03-23 au VE 14-04-23 du MA 02-05-23 au VE 05-05-23 du LU 02-10-23 au VE 27-10-23 et du LU 27-11-23 au VE 08-12-23 Sauf le(s) : LU 10-04-23 | Def, V1, 1V/2, IPCS=2 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_126 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_Chambery-Montmelian_001 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 22:20 | 04:20 J+1 | 22:20 | 04:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 12/13-12-22 au JE/VE 15/16-12-22 du LU/MA 09/10-01-23 au JE/VE 06/07-07-23 du LU/MA 24/25-07-23 au JE/VE 10/11-08-23 et du LU/MA 21/22-08-23 au JE/VE 07/08-12-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23,LU/MA 08/09-05-23, JE/VE 18/19-05-23,LU/MA 29/30-05-23 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA23_0024535_03, CHA15_0008998_126 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | FEN23_Chambery-Montmelian_002 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 08/09-01-23 au DI/LU 23/24-04-23 du DI/LU 14/15-05-23 au DI/LU 02/03-07-23 et du DI/LU 23/24-07-23 au DI/LU 03/04-12-23 Et le(s) : DI/LU 11/12-12-22 Sauf le(s) : DI/LU 09/10-04-23,DI/LU 28/29-05-23 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_126 | OUI | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Chambery-Montmelian_003 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 00:51 | 04:27 | 00:51 | 04:27 | Jours d'application : LU Périodes : du LU 09-01-23 au LU 24-04-23 du LU 15-05-23 au LU 03-07-23 et du LU 24-07-23 au LU 04-12-23 Et le(s) : LU 12-12-22 Sauf le(s) : LU 10-04-23,LU 29-05-23 | Gen, V1,V2, 2V/2, 03:36, Nuit non passe-minuit, LU | CHA15_0008998_126 | NON | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Chambery-Montmelian_008 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 09:54 | 10:54 | 10:02 | 11:02 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 13-01-23 du LU 13-02-23 au VE 10-03-23 du LU 17-04-23 au VE 28-04-23 du MA 09-05-23 au VE 29-09-23 et du LU 30-10-23 au VE 24-11-23 Sauf le(s) : JE 18-05-23,LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V1, 1V/2, IPCS=2 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_126 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Chambery-Montmelian_009 | Chambéry-Challes-les-Eaux-AS | Montmélian-BM | 10:17 | 11:17 | 10:11 | 11:11 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23,LU 29-05-23, VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V2, 1V/2, IPCS=2 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_126 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_Montmelian(900000)_003 | Chambéry-Poste-Bois-00 | Montmélian-BR | 23:10 | 05:06 J+1 | 23:10 | 05:06 J+1 | Jours d'application : LU/MA,DI/LU Périodes : du DI/LU 26/27-03-23 au LU/MA 27/28-03-23 | Cap, RA,V1,V2, 05:56, Passe-minuit, LU/MA,DI/LU | CHA15_0008998_127 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Montmelian-StPierre-d'Albigny_003 | Montmélian-BR | St-Pierre-d'Albigny-BV | 21:30 | 05:30 J+1 | 21:30 | 05:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 29/30-10-23 au JE/VE 07/08-12-23 | Def, V1, 1V/1, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024309_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0
|  | DEF23_Montmelian-StPierre-d'Albigny_006 | Montmélian-BR | St-Pierre-d'Albigny-BV | 10:27 | 11:27 | 10:33 | 11:33 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 16-01-23 au VE 10-02-23 du LU 13-03-23 au VE 14-04-23 du MA 02-05-23 au VE 05-05-23 du LU 02-10-23 au VE 27-10-23 et du LU 27-11-23 au VE 08-12-23 Sauf le(s) : LU 10-04-23 | Def, V1, 1V/2, IPCS=1 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_128 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 11 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_Montmelian-StPierre-d'Albigny_001 | Montmélian-BR | St-Pierre-d'Albigny-BV | 23:00 | 05:00 J+1 | 23:00 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 12/13-12-22 au VE/SA 16/17-12-22 du LU/MA 16/17-01-23 au JE/VE 16/17-02-23 du LU/MA 06/07-03-23 au JE/VE 06/07-04-23 du MA/ME 11/12-04-23 au JE/VE 27/28-04-23 du MA/ME 02/03-05-23 au ME/JE 17/18-05-23 du LU/MA 22/23-05-23 au JE/VE 25/26-05-23 du MA/ME 30/31-05-23 au JE/VE 06/07-07-23 du LU/MA 24/25-07-23 au JE/VE 10/11-08-23 du LU/MA 21/22-08-23 au JE/VE 26/27-10-23 et du LU/MA 06/07-11-23 au JE/VE 07/08-12-23 Sauf le(s) : VE/SA 20/21-01-23,VE/SA 27/28-01-23,VE/SA 03/04-02-23, VE/SA 10/11-02-23,VE/SA 10/11-03-23,VE/SA 17/18-03-23,VE/SA 24/25-03-23, VE/SA 31/01-04-23,VE/SA 21/22-04-23,LU/MA 08/09-05-23, VE/SA 09/10-06-23,VE/SA 16/17-06-23,VE/SA 23/24-06-23, VE/SA 30/01-07-23,VE/SA 28/29-07-23,VE/SA 04/05-08-23, VE/SA 25/26-08-23,VE/SA 01/02-09-23,VE/SA 08/09-09-23,VE/SA 15/16-09-23, VE/SA 22/23-09-23,VE/SA 29/30-09-23,VE/SA 13/14-10-23,VE/SA 20/21-10-23, VE/SA 10/11-11-23,VE/SA 17/18-11-23,VE/SA 24/25-11-23,VE/SA 01/02-12-23 | Gen, V1,V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA15_0008998_128,CHA23_0024535_05 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | FEN23_Montmelian-StPierre-d'Albigny_002 | Montmélian-BR | St-Pierre-d'Albigny-BV | 22:02 | 04:02 J+1 | 22:12 | 04:12 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 15/16-01-23 au DI/LU 12/13-02-23 du DI/LU 05/06-03-23 au DI/LU 23/24-04-23 du DI/LU 14/15-05-23 au DI/LU 02/03-07-23 et du DI/LU 23/24-07-23 au DI/LU 03/04-12-23 Et le(s) : DI/LU 11/12-12-22 Sauf le(s) : DI/LU 09/10-04-23,DI/LU 28/29-05-23,DI/LU 13/14-08-23 | Gen, V1, 1V/2, 06:00, Passe-minuit, DI/LU | CHA23_0024309_02, CHA15_0008998_128 | NON | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Montmelian-StPierre-d'Albigny_003 | Montmélian-BR | St-Pierre-d'Albigny-BV | 23:00 | 05:00 J+1 | 22:50 | 04:50 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 15/16-01-23 au DI/LU 12/13-02-23 du DI/LU 05/06-03-23 au DI/LU 23/24-04-23 du DI/LU 14/15-05-23 au DI/LU 02/03-07-23 et du DI/LU 23/24-07-23 au DI/LU 03/04-12-23 Et le(s) : DI/LU 11/12-12-22 Sauf le(s) : DI/LU 09/10-04-23,DI/LU 28/29-05-23,DI/LU 13/14-08-23 | Gen, V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_128,CHA23_0024309_02 | NON | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Montmelian-StPierre-d'Albigny_006 | Montmélian-BR | St-Pierre-d'Albigny-BV | 10:05 | 11:05 | 10:10 | 11:10 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 13-01-23 du LU 13-02-23 au VE 10-03-23 du LU 17-04-23 au VE 28-04-23 du MA 09-05-23 au VE 29-09-23 et du LU 30-10-23 au VE 24-11-23 Sauf le(s) : JE 18-05-23,LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V1, 1V/2, IPCS=1 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_128 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Montmelian-StPierre-d'Albigny_007 | Montmélian-BR | St-Pierre-d'Albigny-BV | 10:05 | 11:05 | 10:00 | 11:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23,LU 29-05-23, VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V2, 1V/2, IPCS=1 pas, 01:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_128 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_StPierre-d'Albigny_001 | St-Pierre-d'Albigny-BA | Chamousset-00 | 21:35 | 05:30 J+1 | 21:35 | 05:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 03/04-12-23 au JE/VE 07/08-12-23 | Cap, UNIQUE,V1, 07:55, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024309_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0
|  | CAP23_StPierre-d'Albigny_003 | St-Pierre-d'Albigny-BA | Chamousset-00 | 23:00 | 04:00 J+1 | 23:00 | 04:00 J+1 | Jours d'application : DI/LU Périodes : Et le(s) : DI/LU 03/04-12-23 | Cap, UNIQUE,V1,V2, 05:00, Passe-minuit, DI/LU | CHA23_0024309_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StPierre-d'Albigny_004 | Montmélian-BR | Chamousset-00 | 23:00 | 04:57 J+1 | 23:00 | 04:57 J+1 | Jours d'application : MA/ME,ME/JE Périodes : du MA/ME 28/29-03-23 au ME/JE 29/30-03-23 | Cap, V2, 05:57, Passe-minuit, MA/ME,ME/JE | CHA15_0008998_129 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StPierre-d'Albigny_005 | St-Pierre-d'Albigny-BA | Chamousset-00 | 23:00 | 04:58 J+1 | 23:00 | 04:58 J+1 | Jours d'application : JE/VE Périodes : Et le(s) : JE/VE 30/31-03-23 | Cap, UNIQUE,V1, 05:58, Passe-minuit, JE/VE | CHA15_0008998_129 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StPierre-d'Albigny_006 | Montmélian-BR | St-Pierre-d'Albigny-BV | 23:00 | 04:00 J+1 | 23:00 | 04:00 J+1 | Jours d'application : ME/JE,JE/VE Périodes : du ME/JE 15/16-03-23 au JE/VE 16/17-03-23 | Cap, V1,V2, 05:00, Passe-minuit, ME/JE,JE/VE | CHA15_0008998_129 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StPierre-Aiguebelle_001 | Plateforme AFA-00 | Aiguebelle-BV | 10:05 | 16:05 | 10:05 | 16:05 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 02-10-23 au VE 27-10-23 et du LU 06-11-23 au VE 08-12-23 | Cap, V1, 06:00, Jour, LU,MA,ME,JE,VE | CHA23_0024580_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_StPierre-Aiguebelle_002 | Plateforme AFA-00 | Aiguebelle-BV | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 20-03-23 au VE 14-04-23 Sauf le(s) : LU 10-04-23 | Cap, V1, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024580_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | CAP23_StPierre-Aiguebelle_003 | Plateforme AFA-00 | Aiguebelle-BV | 21:20 | 23:20 J+3 | 21:20 | 23:20 J+3 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du LU 30-10-23 au JE 02-11-23 | Cap, V1, 74:00, Continu, LU,MA,ME,JE | CHA23_0024580_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StPierre-Aiguebelle_004 | Plateforme AFA-00 | Aiguebelle-BV | 10:05 | 15:35 | 10:05 | 15:35 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 03-07-23 au VE 11-08-23 et du ME 16-08-23 au VE 25-08-23 Sauf le(s) : VE 14-07-23 | Cap, V1, 05:30, Jour, LU,MA,ME,JE,VE | CHA23_0024309_04, CHA23_0024580_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StPierre-Aiguebelle_002 | St-Pierre-d'Albigny-BB | Aiguebelle-BV | 08:04 | 10:05 | 08:04 | 10:05 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 20-03-23 au VE 14-04-23 du LU 03-07-23 au VE 11-08-23 du ME 16-08-23 au VE 25-08-23 du LU 02-10-23 au VE 27-10-23 et du LU 06-11-23 au VE 08-12-23 Sauf le(s) : LU 10-04-23,VE 14-07-23 | Def, V2, 1V/1, IPCS=1 pas, 02:01, Jour, LU,MA,ME,JE,VE | CHA23_0024580_06, CHA23_0024309_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | DEF23_StPierre-Aiguebelle_005 | St-Pierre-d'Albigny-BB | Aiguebelle-BV | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 20-03-23 au VE 14-04-23 Sauf le(s) : LU 10-04-23 | Def, V1,V2, 2V/2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024580_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StPierre-Aiguebelle_006 | St-Pierre-d'Albigny-BB | Aiguebelle-BV | 13:05 | 16:00 | 13:05 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 03-07-23 au VE 11-08-23 du ME 16-08-23 au VE 25-08-23 et du LU 06-11-23 au VE 24-11-23 Sauf le(s) : VE 14-07-23 | Def, V1,V2, 2V/2, 02:55, Jour, LU,MA,ME,JE,VE | CHA23_0024309_04, CHA23_0024580_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_StPierre-Aiguebelle_007 | St-Pierre-d'Albigny-BB | Aiguebelle-BV | 21:20 | 23:20 J+3 | 21:20 | 23:20 J+3 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du LU 30-10-23 au JE 02-11-23 | Def, V1,V2, 2V/2, 74:00, Continu, LU,MA,ME,JE | CHA23_0024580_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StPierre-Aiguebelle_008 | St-Pierre-d'Albigny-BB | Aiguebelle-BV | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 02-10-23 au VE 27-10-23 et du LU 27-11-23 au VE 08-12-23 | Def, V1,V2, 2V/2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024580_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_StPierre-Aiguebelle_004 | St-Pierre-d'Albigny-BB | Aiguebelle-BV | 22:45 | 04:45 J+1 | 22:37 | 04:37 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 12/13-03-23 au DI/LU 02/03-04-23 du DI/LU 23/24-04-23 au DI/LU 25/26-06-23 et du DI/LU 10/11-09-23 au DI/LU 03/04-12-23 Sauf le(s) : DI/LU 07/08-05-23,DI/LU 28/29-05-23,DI/LU 12/13-11-23 | Gen, V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_130 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_StPierre-Aiguebelle_007 | St-Pierre-d'Albigny-BB | Aiguebelle-BV | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23,LU 29-05-23, VE 14-07-23,MA 15-08-23,ME 01-11-23 | Gen, V1,V2, 1V/2, IPCS=3 pas, 06:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_130, CHA23_0024580_06, CHA23_0024309_04 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 2 | 0 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0
|  | FEN23_StPierre-Aiguebelle_008 | St-Pierre-d'Albigny-BB | Plateforme AFA-00 | 22:22 | 04:22 J+1 | 22:29 | 04:29 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 12/13-03-23 au DI/LU 02/03-04-23 du DI/LU 23/24-04-23 au DI/LU 25/26-06-23 et du DI/LU 10/11-09-23 au DI/LU 03/04-12-23 Sauf le(s) : DI/LU 07/08-05-23,DI/LU 28/29-05-23,DI/LU 12/13-11-23 | Gen, V1, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_130 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_Aiguebelle-StAvre_003 | Épierre-St-Léger-1B | St-Avre-la-Chambre-AN | 23:25 | 08:50 | 23:25 | 08:50 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 05-05-23 au VE 12-05-23 | Def, 2V/2, 05-05-2023, 12-05-2023, Continu | CHA23_0024754_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aiguebelle-StAvre_004 | Épierre-St-Léger-1B | St-Avre-la-Chambre-AN | 13:00 | 16:00 | 13:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 15-05-23 au ME 17-05-23 du LU 22-05-23 au VE 11-08-23 et du ME 16-08-23 au VE 25-08-23 Sauf le(s) : LU 29-05-23,VE 14-07-23 | Def, V1,V2, 2V/2, 03:00, Jour, LU,MA,ME,JE,VE | CHA23_0024754_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aiguebelle-StAvre_005 | Plateforme AFA-AI | Épierre-St-Léger-2B | 08:04 | 10:00 | 08:04 | 10:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 20-03-23 au VE 14-04-23 Sauf le(s) : LU 10-04-23 | Def, V2, 1V/1, 01:56, Jour, LU,MA,ME,JE,VE | CHA23_0024580_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aiguebelle-StAvre_006 | Plateforme AFA-AI | Épierre-St-Léger-2B | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 02-10-23 au VE 27-10-23 et du LU 27-11-23 au VE 08-12-23 | Def, V1,V2, 2V/2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024580_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | DEF23_Aiguebelle-StAvre_007 | Plateforme AFA-AI | Épierre-St-Léger-2B | 08:00 | 10:00 | 08:00 | 10:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 03-07-23 au VE 11-08-23 et du ME 16-08-23 au VE 18-08-23 Sauf le(s) : VE 14-07-23 | Def, V1, 1V/1, 02:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aiguebelle-StAvre_008 | Plateforme AFA-AI | Épierre-St-Léger-2B | 13:00 | 16:00 | 13:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 03-07-23 au VE 11-08-23 du ME 16-08-23 au VE 18-08-23 et du LU 06-11-23 au VE 24-11-23 Sauf le(s) : VE 14-07-23 | Def, V1,V2, 2V/2, 03:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_05, CHA23_0024580_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aiguebelle-StAvre_009 | Plateforme AFA-AI | St-Avre-la-Chambre-AN | 08:00 | 10:00 | 08:00 | 10:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 21-08-23 au VE 25-08-23 | Def, V1, 1V/1, 02:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aiguebelle-StAvre_010 | Plateforme AFA-AI | St-Avre-la-Chambre-AN | 13:00 | 16:00 | 13:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 21-08-23 au VE 29-09-23 | Def, V1,V2, 2V/2, 03:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_05, CHA23_0024580_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aiguebelle-StAvre_011 | Plateforme AFA-AI | St-Avre-la-Chambre-AN | 08:00 | 10:00 | 08:00 | 10:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 28-08-23 au VE 29-09-23 | Def, V1,V2, 1V/2, 02:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_05, CHA23_0024580_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aiguebelle-StAvre_012 | Plateforme AFA-AI | Épierre-St-Léger-2B | 08:00 | 10:00 | 08:00 | 10:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 02-10-23 au VE 27-10-23 et du LU 06-11-23 au VE 08-12-23 | Def, V1,V2, 1V/2, 02:00, Jour, LU,MA,ME,JE,VE | CHA23_0024580_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | DEF23_Aiguebelle-StAvre_013 | Épierre-St-Léger-1B | St-Avre-la-Chambre-AN | 08:00 | 10:00 | 08:00 | 10:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 02-10-23 au VE 06-10-23 | Def, V1, 1V/1, 02:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aiguebelle-StAvre_014 | Épierre-St-Léger-1B | St-Avre-la-Chambre-AN | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 02-10-23 au VE 06-10-23 | Def, V1,V2, 2V/2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024309_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_Aiguebelle-StAvre_015 | Plateforme AFA-AI | Épierre-St-Léger-2B | 21:20 | 23:20 J+3 | 21:20 | 23:20 J+3 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du LU 30-10-23 au JE 02-11-23 | Def, V1,V2, 2V/2, 74:00, Continu, LU,MA,ME,JE | CHA23_0024580_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aiguebelle-StAvre_016 | Plateforme AFA-AI | St-Avre-la-Chambre-AN | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 16-01-23 au VE 10-02-23 et du LU 13-03-23 au VE 14-04-23 Sauf le(s) : LU 10-04-23 | Def, V1,V2, 2V/2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024754_03, CHA23_0024580_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aiguebelle-StAvre_017 | Plateforme AFA-AI | St-Avre-la-Chambre-AN | 00:00 | 05:15 | 00:00 | 05:15 | Jours d'application : MA,ME,JE,VE,SA Périodes : du MA 14-02-23 au SA 11-03-23 | Def, V1,V2, 2V/2, 05:15, Nuit non passe-minuit, MA,ME,JE,VE,SA | CHA23_0024754_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Aiguebelle-StAvre_001 | Plateforme AFA-AI | St-Avre-la-Chambre-AN | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23,LU 29-05-23, VE 14-07-23,MA 15-08-23,ME 01-11-23 | Gen, V1,V2, 1V/2, 06:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_131,CHA23_0024754_03, CHA23_0024580_07, CHA23_0024309_05 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 0 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 0 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0
|  | FEN23_Aiguebelle-StAvre_002 | Plateforme AFA-AI | St-Avre-la-Chambre-AN | 22:22 | 04:22 J+1 | 22:38 | 04:38 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 12/13-03-23 au DI/LU 02/03-04-23 du DI/LU 23/24-04-23 au DI/LU 25/26-06-23 et du DI/LU 10/11-09-23 au DI/LU 03/04-12-23 Sauf le(s) : DI/LU 07/08-05-23,DI/LU 28/29-05-23,DI/LU 12/13-11-23 | Gen, V1, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_131 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Aiguebelle-StAvre_003 | Plateforme AFA-AI | St-Avre-la-Chambre-AN | 22:37 | 04:37 J+1 | 22:24 | 04:24 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 12/13-03-23 au DI/LU 02/03-04-23 du DI/LU 23/24-04-23 au DI/LU 25/26-06-23 et du DI/LU 10/11-09-23 au DI/LU 03/04-12-23 Sauf le(s) : DI/LU 07/08-05-23,DI/LU 28/29-05-23,DI/LU 12/13-11-23 | Gen, V2, 1V/2, 06:00, Passe-minuit, DI/LU | CHA15_0008998_131 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | CAP23_StAvre_002 | St-Avre-la-Chambre-AN | St-Avre-la-Chambre-AS | 10:30 | 09:00 | 10:30 | 09:00 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du MA 02-05-23 au VE 12-05-23 | Cap, Gen,02-05-2023, 12-05-2023, Continu | CHA23_0024754_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | CAP23_StAvre_003 | St-Avre-la-Chambre-AN | St-Avre-la-Chambre-AS | 10:30 | 16:30 J+3 | 10:30 | 16:30 J+3 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du LU 03-04-23 au JE 06-04-23 du MA 11-04-23 au JE 13-04-23 du LU 17-04-23 au JE 20-04-23 et du LU 24-04-23 au JE 27-04-23 | Cap, Gen,1BIS, 78:00, Continu, LU,MA,ME,JE | CHA23_0024754_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | CAP23_StAvre_004 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 23:25 | 08:50 | 23:25 | 08:50 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 05-05-23 au VE 12-05-23 | Cap, Gen,05-05-2023, 12-05-2023, Continu | CHA23_0024754_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StAvre_005 | St-Avre-la-Chambre-BV | St-Avre-la-Chambre-RL | 13:00 | 16:00 | 13:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 15-05-23 au ME 17-05-23 et du LU 22-05-23 au JE 13-07-23 Sauf le(s) : LU 29-05-23 | Cap, Gen,V1,V2, 03:00, Jour, LU,MA,ME,JE,VE | CHA23_0024754_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StAvre_007 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 13:00 | 16:00 | 13:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 17-07-23 au VE 11-08-23 du ME 16-08-23 au VE 25-08-23 et du LU 06-11-23 au VE 24-11-23 | Cap, V1,V2, 03:00, Jour, LU,MA,ME,JE,VE | CHA23_0024754_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StAvre_008 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 17-07-23 au VE 11-08-23 du ME 16-08-23 au VE 25-08-23 et du LU 06-11-23 au VE 24-11-23 | Cap, V1,V2, 06:00, Jour, LU,MA,ME,JE,VE | CHA23_0024754_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StAvre_011 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 08:00 | 10:00 | 08:00 | 10:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 02-10-23 au VE 06-10-23 | Cap, V1, 02:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StAvre_012 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 02-10-23 au VE 06-10-23 | Cap, V1, 06:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StAvre_013 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 24-04-23 au VE 28-04-23 | Cap, V2, 06:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_132 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StAvre_014 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 02-10-23 au VE 27-10-23 et du LU 27-11-23 au VE 08-12-23 | Cap, Gen,V1,V2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024754_04, CHA23_0024309_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_StAvre_015 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 00:00 | 05:15 | 00:00 | 05:15 | Jours d'application : MA,ME,JE,VE,SA Périodes : du MA 14-02-23 au SA 11-03-23 | Cap, Gen,V1,V2, 05:15, Nuit non passe-minuit, MA,ME,JE,VE,SA | CHA23_0024754_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StAvre_016 | St-Avre-la-Chambre-BV | St-Jean-de-Maurienne-Arvan-CR | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 16-01-23 au VE 10-02-23 du LU 13-03-23 au VE 14-04-23 et du MA 02-05-23 au JE 04-05-23 Sauf le(s) : LU 10-04-23 | Cap, Gen,V1,V2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024754_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_StAvre-StJean_002 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 23:25 | 08:50 | 23:25 | 08:50 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 05-05-23 au VE 12-05-23 | Def, 2V/2, 05-05-2023, 12-05-2023, Continu | CHA23_0024754_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StAvre-StJean_003 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 13:00 | 16:00 | 13:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 15-05-23 au ME 17-05-23 du LU 22-05-23 au VE 11-08-23 du ME 16-08-23 au VE 25-08-23 et du LU 06-11-23 au VE 24-11-23 Sauf le(s) : LU 29-05-23,VE 14-07-23 | Def, V1,V2, 2V/2, 03:00, Jour, LU,MA,ME,JE,VE | CHA23_0024754_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_StAvre-StJean_004 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 21:15 | 09:00 J+1 | 21:15 | 09:00 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 01/02-07-23 | Def, V1,V2, 2V/2, 11:45, Passe-minuit, SA/DI | CHA23_0024754_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_StAvre-StJean_005 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 19:45 | 14:40 J+1 | 19:45 | 14:40 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 22/23-07-23 | Def, V1,V2, 2V/2, 18:55, Passe-minuit, SA/DI | CHA23_0024754_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_StAvre-StJean_006 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 21:20 | 23:20 J+3 | 21:20 | 23:20 J+3 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du LU 30-10-23 au JE 02-11-23 | Def, V1,V2, 2V/2, 74:00, Continu, LU,MA,ME,JE | CHA23_0024754_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StAvre-StJean_007 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 08:00 | 10:00 | 08:00 | 10:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 02-10-23 au VE 27-10-23 | Def, V1, 1V/1, IPCS=1 pas, 02:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StAvre-StJean_008 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 02-10-23 au VE 27-10-23 et du LU 27-11-23 au VE 08-12-23 | Def, V1,V2, 2V/2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024754_05, CHA23_0024309_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | DEF23_StAvre-StJean_009 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 16-01-23 au VE 10-02-23 du LU 13-03-23 au VE 14-04-23 et du MA 02-05-23 au JE 04-05-23 Sauf le(s) : LU 10-04-23 | Def, V1,V2, 2V/2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024754_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StAvre-StJean_010 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 00:00 | 05:15 | 00:00 | 05:15 | Jours d'application : MA,ME,JE,VE,SA Périodes : du MA 14-02-23 au SA 11-03-23 | Def, V1,V2, 2V/2, 05:15, Nuit non passe-minuit, MA,ME,JE,VE,SA | CHA23_0024754_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_StAvre-StJean_001 | St-Avre-la-Chambre-AS | St-Jean-de-Maurienne-Arvan-BV | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23,LU 29-05-23, VE 14-07-23,MA 15-08-23,ME 01-11-23 | Gen, V1,V2, 1V/2, 06:00, Jour, LU,MA,ME,JE,VE | CHA23_0024754_05, CHA23_0024309_07, CHA15_0008998_133 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 0 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_StJean_002 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-FR | 08:00 | 16:00 | 08:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du MA 30-05-23 au VE 07-07-23 | Cap, V2, 08:00, Jour, LU,MA,ME,JE,VE | CHA23_0024754_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | CAP23_StJean_003 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-FR | 23:25 | 08:50 | 23:25 | 08:50 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 05-05-23 au VE 12-05-23 | Cap, 05-05-2023, 12-05-2023, Continu | CHA23_0024754_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StJean_004 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-TR | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 17-07-23 au VE 11-08-23 du ME 16-08-23 au VE 29-09-23 et du LU 06-11-23 au VE 24-11-23 | Cap, V1,V2, 06:00, Jour, LU,MA,ME,JE,VE | CHA23_0024754_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StJean_005 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-TR | 13:00 | 16:00 | 13:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 17-07-23 au VE 11-08-23 du ME 16-08-23 au VE 29-09-23 et du LU 06-11-23 au VE 24-11-23 | Cap, V1,V2, 03:00, Jour, LU,MA,ME,JE,VE | CHA23_0024754_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StJean_006 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-TR | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 02-10-23 au VE 27-10-23 et du LU 27-11-23 au VE 08-12-23 | Cap, V1,V2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024754_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_StJean_007 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-FR | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 15-05-23 au ME 17-05-23 et du LU 22-05-23 au VE 26-05-23 | Cap, V2, 06:00, Jour, LU,MA,ME,JE,VE | CHA23_0024754_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StJean_012 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-FR | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 17-04-23 au VE 21-04-23 | Cap, V1, 06:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_134 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StJean_013 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-FR | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 24-04-23 au VE 28-04-23 | Cap, V2, 06:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_134 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StJean_014 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-FR | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 16-01-23 au VE 10-02-23 du LU 13-03-23 au VE 14-04-23 et du MA 02-05-23 au JE 04-05-23 Sauf le(s) : LU 10-04-23 | Cap, V1,V2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024754_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StJean_015 | St-Jean-de-Maurienne-Arvan-CR | St-Jean-de-Maurienne-Arvan-FR | 00:00 | 05:15 | 00:00 | 05:15 | Jours d'application : MA,ME,JE,VE,SA Périodes : du MA 14-02-23 au SA 11-03-23 | Cap, V1,V2, 05:15, Nuit non passe-minuit, MA,ME,JE,VE,SA | CHA23_0024754_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StJean-Modane_001 | St-Jean-de-Maurienne-Arvan-P1 | Modane-AG | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 28-04-23 et du LU 06-11-23 au VE 08-12-23 Sauf le(s) : LU 10-04-23 | Def, V1,V2, 1V/2, IPCS=1 pas, 06:00, Jour, LU,MA,ME,JE,VE | CHA15_0008998_135 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Yes |  | DEF23_StJean-Modane_003 | St-Jean-de-Maurienne-Arvan-P1 | Modane-Berchette-00 | 21:15 | 09:00 J+1 | 21:15 | 09:00 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 01/02-07-23 | Def, V1,V2, 2V/2, 11:45, Passe-minuit, SA/DI | CHA23_0024754_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_StJean-Modane_004 | St-Jean-de-Maurienne-Arvan-P1 | Modane-AG | 23:25 | 08:50 | 23:25 | 08:50 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 05-05-23 au VE 12-05-23 | Def, 2V/2, 05-05-2023, 12-05-2023, Continu | CHA23_0024754_07, CHA23_0024772_01, CHA23_0025381_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StJean-Modane_005 | St-Jean-de-Maurienne-Arvan-P1 | Modane-Berchette-00 | 13:00 | 16:00 | 13:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 22-05-23 au JE 13-07-23 du LU 28-08-23 au VE 29-09-23 et du LU 06-11-23 au VE 24-11-23 Sauf le(s) : LU 29-05-23 | Def, V1,V2, 2V/2, 03:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_09, CHA23_0024754_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_StJean-Modane_006 | St-Jean-de-Maurienne-Arvan-P1 | Modane-Berchette-00 | 19:45 | 14:40 J+1 | 19:45 | 14:40 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 22/23-07-23 | Def, V1,V2, 2V/2, 18:55, Passe-minuit, SA/DI | CHA23_0024754_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_StJean-Modane_007 | St-Jean-de-Maurienne-Arvan-P1 | Modane-Berchette-00 | 23:25 | 23:20 J+4 | 23:25 | 23:20 J+4 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du DI 29-10-23 au JE 02-11-23 | Def, V1,V2, 2V/2, 95:55, Continu, LU,MA,ME,JE,DI | CHA23_0024754_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StJean-Modane_008 | St-Jean-de-Maurienne-Arvan-P1 | Modane-AG | 10:46 | 11:31 | 10:46 | 11:31 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 17-07-23 au VE 04-08-23 | Def, V1,V2, 2V/2, 00:45, Jour, LU,MA,ME,JE,VE | CHA23_0025357_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StJean-Modane_009 | St-Jean-de-Maurienne-Arvan-P1 | Modane-AG | 15:00 | 16:00 | 15:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 17-07-23 au VE 04-08-23 | Def, V1,V2, 2V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA23_0025357_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StJean-Modane_010 | St-Michel-Valloire-00 | Modane-AG | 08:00 | 10:00 | 08:00 | 10:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du MA 11-04-23 au VE 28-04-23 | Def, V1, 1V/1, 02:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_09 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StJean-Modane_011 | St-Michel-Valloire-00 | Modane-AG | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du MA 11-04-23 au VE 14-04-23 et du MA 02-05-23 au VE 05-05-23 | Def, V1,V2, 2V/2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024309_09 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StJean-Modane_012 | St-Michel-Valloire-00 | Modane-Berchette-00 | 08:00 | 10:00 | 08:00 | 10:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du MA 02-05-23 au VE 05-05-23 | Def, V1, 1V/1, 02:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_09 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StJean-Modane_013 | St-Michel-Valloire-00 | Modane-AG | 08:00 | 10:00 | 08:00 | 10:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du MA 02-05-23 au VE 05-05-23 | Def, V2, 1V/1, 02:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_09 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_StJean-Modane_014 | St-Michel-Valloire-00 | Modane-AG | 23:25 | 08:50 | 23:25 | 08:50 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 05-05-23 au VE 12-05-23 | Def, 2V/2, 05-05-2023, 12-05-2023, Continu | CHA23_0024309_09 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StJean-Modane_015 | St-Jean-de-Maurienne-Arvan-P1 | Modane-AG | 08:00 | 10:00 | 08:00 | 10:00 | Jours d'application : LU,MA,ME Périodes : du LU 15-05-23 au ME 17-05-23 | Def, V2, 1V/1, 02:00, Jour, LU,MA,ME | CHA23_0024309_09 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StJean-Modane_016 | St-Jean-de-Maurienne-Arvan-P1 | Modane-AG | 13:20 | 15:45 | 13:20 | 15:45 | Jours d'application : LU,MA,ME Périodes : du LU 15-05-23 au ME 17-05-23 | Def, V1,V2, 2V/2, 02:25, Jour, LU,MA,ME | CHA23_0024309_09 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StJean-Modane_017 | St-Jean-de-Maurienne-Arvan-P1 | Modane-Berchette-00 | 08:00 | 10:00 | 08:00 | 10:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 22-05-23 au VE 30-06-23 Sauf le(s) : LU 29-05-23 | Def, V1,V2, 1V/2, 02:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_09 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StJean-Modane_018 | St-Jean-de-Maurienne-Arvan-P1 | Modane-Berchette-00 | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 02-10-23 au VE 27-10-23 et du LU 27-11-23 au VE 08-12-23 | Def, V1,V2, 2V/2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024754_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | DEF23_StJean-Modane_019 | St-Jean-de-Maurienne-Arvan-P1 | Modane-Berchette-00 | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 16-01-23 au VE 10-02-23 et du LU 13-03-23 au VE 14-04-23 Sauf le(s) : LU 10-04-23 | Def, V1,V2, 2V/2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024754_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StJean-Modane_020 | St-Jean-de-Maurienne-Arvan-P1 | Modane-Berchette-00 | 00:00 | 05:15 | 00:00 | 05:15 | Jours d'application : MA,ME,JE,VE,SA Périodes : du MA 14-02-23 au SA 11-03-23 | Def, V1,V2, 2V/2, 05:15, Nuit non passe-minuit, MA,ME,JE,VE,SA | CHA23_0024754_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_StJean-Modane_001 | St-Jean-de-Maurienne-Arvan-P1 | Modane-AG | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23,LU 29-05-23, VE 14-07-23,MA 15-08-23,ME 01-11-23 | Gen, V1,V2, 1V/2, 06:00, Jour, LU,MA,ME,JE,VE | CHA23_0024754_07, CHA15_0008998_135, CHA23_0025381_03, CHA23_0024772_01, CHA23_0024309_09, CHA23_0025357_03 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 0 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_Modane_002 | La Praz-00 | Modane-AG | 10:00 | 16:00 | 10:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 17-07-23 au VE 04-08-23 | Cap, V2, 06:00, Jour, LU,MA,ME,JE,VE | CHA23_0025357_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Modane_003 | La Praz-00 | Modane-AG | 10:46 | 11:31 | 10:46 | 11:31 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 17-07-23 au VE 04-08-23 | Cap, V1, 00:45, Jour, LU,MA,ME,JE,VE | CHA23_0025357_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Modane_004 | La Praz-00 | Modane-AG | 15:00 | 16:00 | 15:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 17-07-23 au VE 04-08-23 | Cap, V1, 01:00, Jour, LU,MA,ME,JE,VE | CHA23_0025357_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Modane_005 | La Praz-00 | Modane-AG | 08:00 | 16:00 | 08:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du MA 11-04-23 au VE 28-04-23 | Cap, V1, 08:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_10 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Modane_006 | La Praz-00 | Modane-PO | 11:15 | 16:00 | 11:15 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du MA 11-04-23 au VE 14-04-23 et du MA 02-05-23 au VE 05-05-23 | Cap, V1,V2, 04:45, Jour, LU,MA,ME,JE,VE | CHA23_0024309_10 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Modane_007 | La Praz-00 | Modane-PO | 08:00 | 16:00 | 08:00 | 16:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du MA 02-05-23 au VE 05-05-23 et du LU 15-05-23 au ME 17-05-23 | Cap, V2, 08:00, Jour, LU,MA,ME,JE,VE | CHA23_0024309_10 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Modane_008 | La Praz-00 | Modane-PO | 23:25 | 08:50 | 23:25 | 08:50 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 05-05-23 au VE 12-05-23 | Cap, 05-05-2023, 12-05-2023, Continu | CHA23_0024309_10 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Modane_010 | La Praz-00 | Modane-PO | 13:20 | 15:45 | 13:20 | 15:45 | Jours d'application : LU,MA,ME Périodes : du LU 15-05-23 au ME 17-05-23 | Cap, V1,V2, 02:25, Jour, LU,MA,ME | CHA23_0024309_10 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Modane_011 | Modane-PO | Modane-FP | 23:17 | 05:30 J+1 | 23:17 | 05:30 J+1 | Jours d'application : DI/LU Périodes : Et le(s) : DI/LU 09/10-07-23 | Cap, V1,V2, 06:13, Passe-minuit, DI/LU | CHA15_0008998_136 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Modane_012 | Modane-AG | Modane-FP | 23:16 | 05:20 J+1 | 23:16 | 05:20 J+1 | Jours d'application : ME/JE,JE/VE Périodes : du ME/JE 04/05-10-23 au JE/VE 05/06-10-23 | Cap, V1,V2, 06:04, Passe-minuit, ME/JE,JE/VE | CHA15_0008998_136 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Vintimillia - July 2022
SNCF RESEAU - WORKS TT2022 - MARSEILLE-VENTIMIGLIA
| =Total closure >12 hrs | [11 empty] | 2021 | [19 empty] | 2022
| = border point Ventimiglia | [11 empty] | DEC | [19 empty] | JAN | [30 empty] | FEV | [27 empty] | MAR | [30 empty] | AVR | [29 empty] | MAI | [30 empty] | JUN | [29 empty] | JUL | [30 empty] | AOU | [30 empty] | SEP | [29 empty] | OCT | [30 empty] | NOV | [29 empty] | DEC
Total closure >12 hrs ? | Border point ? | Identifiant Ressource | Localisation : Starting point | Localisation : Ending point | Start Time Starting point | End Time Starting point | Start Time Ending point | End Time Ending point | Days of activation (night works are identified by : Day1 / Day2) Period of activation | Type of works | Worksites | Weekend | 49 | 50 | [6 empty] | 51 | [6 empty] | 52 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40 | [6 empty] | 41 | [6 empty] | 42 | [6 empty] | 43 | [6 empty] | 44 | [6 empty] | 45 | [6 empty] | 46 | [6 empty] | 47 | [6 empty] | 48 | [6 empty] | 49
|  | CAP22_Marseille_030 | - | Marseille-Blancarde-AB | 23:50 | 04:55 J+1 | 23:50 | 04:55 J+1 | Jours d'application : SA/DI Périodes : du SA/DI 10/11-09-22 au SA/DI 05/06-11-22 et du SA/DI 26/27-11-22 au SA/DI 10/11-12-22 | Cap, 3,5,A,GCIRC,MV1,MV2,V1,V1,V2,V2, 05:05, Passe-minuit, SA/DI | CHA21_0021170_20 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | CAP22_Marseille_031 | Marseille-St-Charles-BV | Marseille-Blancarde-AB | 23:50 | 04:55 J+1 | 23:50 | 04:55 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 05/06-02-22 et SA/DI 03/04-09-22 | Cap, 3,5,A,GCIRC,MV1,MV2,V1,V1,V2,V2, 05:05, Passe-minuit, SA/DI | CHA21_0021170_20 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Marseille_032 | Marseille-Blancarde-AB | La Pomme-00 | 23:19 | 05:25 J+1 | 23:19 | 05:25 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 20/21-03-22 au JE/VE 07/08-04-22 et du DI/LU 01/02-05-22 au JE/VE 12/13-05-22 | Cap, MV1,MV2,V1,V2, 06:06, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022924_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Marseille_033 | Marseille-Blancarde-AB | La Pomme-00 | 20:36 | 04:36 J+1 | 20:36 | 04:36 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 10/11-04-22 au ME/JE 13/14-04-22 et du ME/JE 27/28-04-22 au JE/VE 28/29-04-22 | Cap, MV1,MV2,V1, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022924_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Marseille_034 | Marseille-Blancarde-CD | La Pomme-00 | 23:19 | 08:19 J+3 | 23:19 | 08:19 J+3 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 15-04-22 au LU 18-04-22 | Cap, MV1,MV2,V1,V2, 57:00, Continu, LU,VE,SA,DI | CHA22_0022924_01 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Marseille_035 | Marseille-Blancarde-AB | La Pomme-00 | 23:19 | 05:35 J+1 | 23:19 | 05:35 J+1 | Jours d'application : ME/JE,JE/VE,DI/LU Périodes : du ME/JE 20/21-04-22 au JE/VE 21/22-04-22 | Cap, V2, 06:16, Passe-minuit, ME/JE,JE/VE,DI/LU | CHA22_0022924_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Marseille_036 | Marseille-Blancarde-AB | La Pomme-00 | 23:19 | 11:30 J+2 | 23:19 | 11:30 J+2 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 22-04-22 au DI 24-04-22 | Cap, MV1,MV2,V1,V2,VMV3, 36:11, Continu, VE,SA,DI | CHA22_0022924_01 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Marseille_039 | Marseille-St-Charles-BC | Marseille-Blancarde-AB | 00:25 | 05:10 | 00:25 | 05:10 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 21-02-22 au VE 04-03-22 | Cap, V1,V2, 04:45, Nuit non passe-minuit, LU,MA,ME,JE,VE | CHA21_0021958_16 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Marseille_042 | Marseille-Blancarde-AB | La Pomme-00 | 23:19 | 05:35 J+1 | 23:19 | 05:35 J+1 | Jours d'application : ME/JE,JE/VE Périodes : du ME/JE 20/21-04-22 au JE/VE 21/22-04-22 | Cap, MV1,MV2,V1,V2, 06:16, Passe-minuit, ME/JE,JE/VE | CHA22_0022924_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Marseille_043 | Marseille-Blancarde-CD | La Pomme-00 | 20:36 | 04:36 J+1 | 20:36 | 04:36 J+1 | Jours d'application : ME/JE,JE/VE Périodes : du ME/JE 27/28-04-22 au JE/VE 28/29-04-22 | Cap, MV1,MV2,V1,V2, 08:00, Passe-minuit, ME/JE,JE/VE | CHA22_0022924_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Marseille_044 | - | Marseille-Blancarde-AB | 01:00 | 04:00 | 01:00 | 04:00 | Jours d'application : SA Périodes : Et le(s) : SA 21-05-22 | Cap, 3,5,A,GCIRC,MV1,MV2,V1,V1,V1,V2,V2,V2, 03:00, Nuit non passe-minuit, SA | CHA22_0023028_17 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Marseille-Aubagne_007 | Marseille-Blancarde-BV | Aubagne-00 | 23:50 | 04:55 J+1 | 23:50 | 04:55 J+1 | Jours d'application : SA/DI Périodes : du SA/DI 10/11-09-22 au SA/DI 05/06-11-22 et du SA/DI 26/27-11-22 au SA/DI 10/11-12-22 | Def, V1,V2,VMV3, , 05:05, Passe-minuit, SA/DI | CHA21_0021170_21 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | DEF22_Marseille-Aubagne_008 | Marseille-Blancarde-BV | Aubagne-00 | 23:50 | 04:55 J+1 | 23:50 | 04:55 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 05/06-02-22 et SA/DI 03/04-09-22 | Def, V1,V2,VMV3, , 05:05, Passe-minuit, SA/DI | CHA21_0021170_21 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Marseille-Aubagne_009 | Marseille-Blancarde-BV | St-Marcel-V3 | 20:36 | 04:36 J+1 | 20:36 | 04:36 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 11/12-04-22 au ME/JE 13/14-04-22 | Def, V1,V2, , 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA22_0022924_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Marseille-Aubagne_010 | Marseille-Blancarde-BV | St-Marcel-V3 | 23:19 | 08:19 J+3 | 23:19 | 08:19 J+3 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 15-04-22 au LU 18-04-22 | Def, V1,V2, 2V/2, 57:00, Continu, LU,VE,SA,DI | CHA22_0022924_02 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Marseille-Aubagne_011 | Marseille-Blancarde-BV | St-Marcel-V3 | 23:19 | 11:30 J+2 | 23:19 | 11:30 J+2 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 22-04-22 au DI 24-04-22 | Def, V1,V2, 2V/2, 36:11, Continu, VE,SA,DI | CHA22_0022924_02 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Marseille-Aubagne_014 | La Barasse-00 | Aubagne-00 | 23:35 | 05:47 J+1 | 23:35 | 05:47 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 16/17-01-22 au DI/LU 12/13-06-22 Sauf le(s) : DI/LU 05/06-06-22 | Def, V1,V2,VMV3, , 06:12, Passe-minuit, DI/LU | CHA21_0021549_08,CHA21_0021546_08 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Marseille-Aubagne_015 | La Barasse-00 | Aubagne-00 | 22:21 | 05:45 J+1 | 22:21 | 05:45 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 10/11-01-22 au JE/VE 23/24-06-22 Sauf le(s) : LU/MA 18/19-04-22,ME/JE 25/26-05-22 | Def, V1,V2,VMV3, , 07:24, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021549_08,CHA21_0021546_08 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Marseille-Aubagne_016 | Marseille-Blancarde-BV | La Pomme-00 | 23:19 | 05:25 J+1 | 23:19 | 05:25 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 20/21-03-22 au JE/VE 07/08-04-22 et du DI/LU 01/02-05-22 au JE/VE 12/13-05-22 | Def, V1, , 06:06, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022924_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Marseille-Aubagne_017 | Marseille-Blancarde-BV | La Pomme-00 | 20:36 | 04:36 J+1 | 20:36 | 04:36 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 10/11-04-22 au ME/JE 13/14-04-22 et du ME/JE 27/28-04-22 au JE/VE 28/29-04-22 | Def, V1, , 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022924_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Marseille-Aubagne_020 | Marseille-Blancarde-BV | La Pomme-00 | 23:19 | 05:35 J+1 | 23:19 | 05:35 J+1 | Jours d'application : ME/JE,JE/VE Périodes : du ME/JE 20/21-04-22 au JE/VE 21/22-04-22 | Def, V1, , 06:16, Passe-minuit, ME/JE,JE/VE | CHA22_0022924_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Marseille-Aubagne_023 | Marseille-Blancarde-BV | Aubagne-00 | 01:00 | 04:00 | 01:00 | 04:00 | Jours d'application : SA Périodes : Et le(s) : SA 21-05-22 | Def, V1,V2,VMV3, , 03:00, Nuit non passe-minuit, SA | CHA22_0023028_18 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Marseille-Aubagne_002 | Marseille-Blancarde-BV | Aubagne-00 | 23:19 | 05:35 J+1 | 23:19 | 05:35 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 13/14-12-21 au VE/SA 09/10-12-22 Sauf le(s) : LU/MA 18/19-04-22,JE/VE 26/27-05-22, LU/MA 06/07-06-22,JE/VE 14/15-07-22, LU/MA 15/16-08-22,MA/ME 01/02-11-22,VE/SA 11/12-11-22 | Gen, V1,V2,VMV3, 3V/3, 06:16, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_64,CHA20_0019010_22,CHA21_0022003_14 | NON | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Marseille-Aubagne_003 | Marseille-Blancarde-BV | Aubagne-00 | 08:38 | 09:38 | 08:45 | 09:45 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : ME 26-01-22,LU 18-04-22,JE 26-05-22, LU 06-06-22,JE 14-07-22,LU 15-08-22,MA 01-11-22, VE 11-11-22 | Sur, V1, 1V/3, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_64 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Marseille-Aubagne_004 | Marseille-Blancarde-J1 | Aubagne-00 | 11:20 | 12:20 | 11:12 | 12:12 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : LU 18-04-22,JE 26-05-22,LU 06-06-22, JE 14-07-22,LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, V2, 1V/3, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_64 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Marseille-Aubagne_005 | Marseille-Blancarde-BV | Aubagne-00 | 23:05 | 05:35 J+1 | 23:05 | 05:35 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 13/14-12-21 au VE/SA 08/09-07-22 Sauf le(s) : LU/MA 18/19-04-22,JE/VE 26/27-05-22, LU/MA 06/07-06-22 | Gen, V1, 2V/3, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_64 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Marseille-Aubagne_006 | Marseille-Blancarde-J1 | Aubagne-00 | 23:05 | 05:35 J+1 | 23:05 | 05:35 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 13/14-12-21 au VE/SA 08/09-07-22 Sauf le(s) : LU/MA 18/19-04-22,JE/VE 26/27-05-22, LU/MA 06/07-06-22 | Gen, V2, 2V/3, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_64 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Marseille-Aubagne_007 | Marseille-Blancarde-J1 | Aubagne-00 | 23:05 | 05:35 J+1 | 23:05 | 05:35 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 11/12-07-22 au VE/SA 09/10-12-22 Sauf le(s) : JE/VE 14/15-07-22,LU/MA 15/16-08-22, MA/ME 01/02-11-22,VE/SA 11/12-11-22 | Gen, VMV3, 2V/3, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_64 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Marseille-Aubagne_008 | Marseille-Blancarde-J1 | Aubagne-00 | 11:10 | 12:10 | 11:10 | 12:10 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : LU 18-04-22,JE 26-05-22,LU 06-06-22, JE 14-07-22,LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, VMV3, 1V/3, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_64 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP22_Aubagne_012 | Aubagne-J3 | ITE Camp-Militaire-Carpiagne-00 | 23:50 | 04:55 J+1 | 23:50 | 04:55 J+1 | Jours d'application : SA/DI Périodes : du SA/DI 10/11-09-22 au SA/DI 05/06-11-22 et du SA/DI 26/27-11-22 au SA/DI 10/11-12-22 | Cap, A,D,E,V1,V2,VMV3, 05:05, Passe-minuit, SA/DI | CHA21_0021170_22 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | CAP22_Aubagne_013 | Aubagne-J3 | ITE Camp-Militaire-Carpiagne-00 | 21:58 | 05:40 J+1 | 21:58 | 05:40 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-12-21 au ME/JE 22/23-12-21 | Cap, V1, 07:42, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021546_09 | NON | 0 | 1.25 | 1.25 | 1.25 | 1.25 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Aubagne_016 | Aubagne-J3 | ITE Camp-Militaire-Carpiagne-00 | 23:40 | 05:44 J+1 | 23:40 | 05:44 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-12-21 au ME/JE 22/23-12-21 | Cap, V2, 06:04, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021546_09 | NON | 0 | 1.25 | 1.25 | 1.25 | 1.25 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Aubagne_017 | Aubagne-J3 | ITE Camp-Militaire-Carpiagne-00 | 23:50 | 04:55 J+1 | 23:50 | 04:55 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 05/06-02-22 et SA/DI 03/04-09-22 | Cap, A,D,E,V1,V2,VMV3, 05:05, Passe-minuit, SA/DI | CHA21_0021170_22 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Aubagne_019 | Aubagne-J3 | ITE Camp-Militaire-Carpiagne-00 | 22:21 | 05:45 J+1 | 22:21 | 05:45 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 10/11-01-22 au JE/VE 23/24-06-22 Sauf le(s) : ME/JE 25/26-05-22 | Cap, V1,V2,VMV3, 07:24, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021549_09,CHA21_0021546_09 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Aubagne_020 | Aubagne-J3 | ITE Camp-Militaire-Carpiagne-00 | 23:35 | 05:47 J+1 | 23:35 | 05:47 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 16/17-01-22 au DI/LU 26/27-06-22 | Cap, V1,V2,VMV3, 06:12, Passe-minuit, DI/LU | CHA21_0021549_09,CHA21_0021546_09 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Aubagne_022 | Aubagne-00 | ITE Camp-Militaire-Carpiagne-00 | 21:58 | 05:45 J+1 | 21:58 | 05:45 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 03/04-10-22 au JE/VE 08/09-12-22 Sauf le(s) : JE/VE 10/11-11-22 | Cap, V1,V2, 07:47, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA22_0023722_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | CAP22_Aubagne_023 | Aubagne-00 | ITE Camp-Militaire-Carpiagne-00 | 23:08 | 05:45 J+1 | 23:08 | 05:45 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 25/26-09-22 au DI/LU 04/05-12-22 | Cap, V1,V2, 06:37, Passe-minuit, DI/LU | CHA22_0023722_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Aubagne_024 | Aubagne-00 | ITE Camp-Militaire-Carpiagne-00 | 23:30 | 05:30 J+1 | 23:59 | 04:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 19/20-09-22 au JE/VE 29/30-09-22 | Cap, V1,V2, 05:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA22_0023722_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Aubagne_025 | Aubagne-J3 | ITE Camp-Militaire-Carpiagne-00 | 23:30 | 05:30 J+1 | 23:59 | 04:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : Et le(s) : LU/MA 26/27-09-22 | Cap, V2, 05:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA20_0019010_23 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Aubagne_026 | Aubagne-J3 | ITE Camp-Militaire-Carpiagne-00 | 22:45 | 06:00 J+1 | 22:45 | 06:00 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 12/13-12-21 au DI/LU 19/20-12-21 | Cap, V2, 07:15, Passe-minuit, DI/LU | CHA21_0021546_09 | NON | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Aubagne_027 | Aubagne-J3 | ITE Camp-Militaire-Carpiagne-00 | 22:10 | 06:09 J+1 | 22:10 | 06:09 J+1 | Jours d'application : VE/SA,DI/LU Périodes : du DI/LU 19/20-12-21 au DI/LU 26/27-12-21 Sauf le(s) : VE/SA 24/25-12-21 | Cap, V1, 07:59, Passe-minuit, VE/SA,DI/LU | CHA21_0021546_09 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Aubagne_030 | Aubagne-J3 | ITE Camp-Militaire-Carpiagne-00 | 01:00 | 04:00 | 01:00 | 04:00 | Jours d'application : SA Périodes : Et le(s) : SA 21-05-22 | Cap, A,D,E,V1,V2,VMV3, 03:00, Nuit non passe-minuit, SA | CHA22_0023028_19 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aubagne-Toulon_010 | Aubagne-00 | St-Antoine (M) Poste 1-00 | 21:58 | 05:40 J+1 | 21:58 | 05:40 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-12-21 au ME/JE 22/23-12-21 | Def, V1, , 07:42, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021546_10 | NON | 0 | 1.25 | 1.25 | 1.25 | 1.25 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aubagne-Toulon_015 | ITE Camp-Militaire-Carpiagne-00 | La Seyne-Tamaris-sur-Mer-P1 | 22:21 | 05:45 J+1 | 22:21 | 05:45 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,SA/DI Périodes : du LU/MA 10/11-01-22 au JE/VE 03/04-03-22 Sauf le(s) : SA/DI 15/16-01-22,SA/DI 22/23-01-22, SA/DI 29/30-01-22,SA/DI 05/06-02-22,SA/DI 12/13-02-22, SA/DI 19/20-02-22,SA/DI 26/27-02-22 | Def, V1, , 07:24, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,SA/DI | CHA21_0021546_10 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aubagne-Toulon_016 | ITE Camp-Militaire-Carpiagne-00 | La Seyne-Tamaris-sur-Mer-PA | 22:21 | 05:45 J+1 | 22:21 | 05:45 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,SA/DI Périodes : du LU/MA 10/11-01-22 au JE/VE 03/04-03-22 Sauf le(s) : SA/DI 15/16-01-22,SA/DI 22/23-01-22, SA/DI 29/30-01-22,SA/DI 05/06-02-22,SA/DI 12/13-02-22, SA/DI 19/20-02-22,SA/DI 26/27-02-22 | Def, V2, , 07:24, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,SA/DI | CHA21_0021546_10 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aubagne-Toulon_017 | Aubagne-00 | St-Antoine (M) Poste 1-00 | 23:40 | 05:44 J+1 | 23:40 | 05:44 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-12-21 au ME/JE 22/23-12-21 | Def, V2, , 06:04, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021546_10 | NON | 0 | 1.25 | 1.25 | 1.25 | 1.25 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aubagne-Toulon_018 | ITE Camp-Militaire-Carpiagne-00 | La Seyne-Tamaris-sur-Mer-P1 | 23:35 | 05:47 J+1 | 23:35 | 05:47 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 16/17-01-22 au DI/LU 06/07-03-22 | Def, V1, , 06:12, Passe-minuit, DI/LU | CHA21_0021546_10 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aubagne-Toulon_019 | ITE Camp-Militaire-Carpiagne-00 | La Seyne-Tamaris-sur-Mer-PA | 23:35 | 05:47 J+1 | 23:35 | 05:47 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 16/17-01-22 au DI/LU 06/07-03-22 | Def, V2, , 06:12, Passe-minuit, DI/LU | CHA21_0021546_10 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aubagne-Toulon_020 | Aubagne-00 | Toulon-BV | 23:35 | 05:47 J+1 | 23:35 | 05:47 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 06/07-03-22 au DI/LU 12/13-06-22 Sauf le(s) : DI/LU 05/06-06-22 | Def, V1,V2, , 06:12, Passe-minuit, DI/LU | CHA21_0021549_10 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aubagne-Toulon_021 | Aubagne-00 | Toulon-BV | 22:21 | 05:45 J+1 | 22:21 | 05:45 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 28/01-03-22 au JE/VE 23/24-06-22 Sauf le(s) : LU/MA 18/19-04-22,ME/JE 25/26-05-22 | Def, V1,V2, , 07:24, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021549_10 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aubagne-Toulon_023 | Aubagne-00 | St-Antoine (M) Poste 1-00 | 21:58 | 05:45 J+1 | 21:58 | 05:45 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 03/04-10-22 au JE/VE 08/09-12-22 Sauf le(s) : JE/VE 10/11-11-22 | Def, V1,V2, , 07:47, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA22_0023722_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | DEF22_Aubagne-Toulon_024 | Aubagne-00 | Cassis-BV | 23:08 | 05:45 J+1 | 23:08 | 05:45 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 25/26-09-22 au DI/LU 04/05-12-22 | Def, V1,V2, , 06:37, Passe-minuit, DI/LU | CHA22_0023722_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aubagne-Toulon_025 | Aubagne-00 | St-Antoine (M) Poste 1-00 | 22:45 | 06:00 J+1 | 22:45 | 06:00 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 12/13-12-21 au DI/LU 19/20-12-21 | Def, V2, , 07:15, Passe-minuit, DI/LU | CHA21_0021546_10 | NON | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aubagne-Toulon_026 | Aubagne-00 | St-Antoine (M) Poste 1-00 | 22:10 | 06:09 J+1 | 22:10 | 06:09 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 12/13-12-21 au DI/LU 19/20-12-21 | Def, V1, , 07:59, Passe-minuit, DI/LU | CHA21_0021546_10 | NON | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Aubagne-Toulon_027 | Aubagne-00 | Toulon-BV | 22:58 | 05:45 J+1 | 22:58 | 05:45 J+1 | Jours d'application : ME/JE Périodes : Et le(s) : ME/JE 25/26-05-22 | Def, V1,V2, , 06:47, Passe-minuit, ME/JE | CHA21_0021549_10 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Aubagne-Toulon_006 | Aubagne-00 | Toulon-BV | 08:48 | 09:48 | 09:32 | 10:32 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : ME 26-01-22,LU 18-04-22,JE 26-05-22,LU 06-06-22,JE 14-07-22,LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, V1, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_66 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Aubagne-Toulon_007 | Aubagne-00 | Toulon-BV | 11:10 | 12:10 | 10:26 | 11:26 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : VE 07-01-22,LU 18-04-22,JE 26-05-22,LU 06-06-22,JE 14-07-22,LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, V2, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_66 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Aubagne-Toulon_008 | Aubagne-00 | Toulon-BV | 23:30 | 05:30 J+1 | 23:59 | 04:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 13/14-12-21 au VE/SA 09/10-12-22 Sauf le(s) : LU/MA 18/19-04-22,JE/VE 26/27-05-22, LU/MA 06/07-06-22,JE/VE 14/15-07-22, LU/MA 15/16-08-22,MA/ME 01/02-11-22,VE/SA 11/12-11-22 | Gen, V1,V2, 2V/2, 05:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_66,CHA21_0021546_10,CHA22_0023722_01,CHA21_0021966_18,CHA21_0021958_19,CHA20_0019010_24,CHA22_0023020_02,CHA21_0022003_16 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 0 | 0 | 3 | 4 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 4 | 4 | 3 | 3 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Aubagne-Toulon_011 | Aubagne-00 | Toulon-BV | 23:05 | 05:25 J+1 | 23:05 | 05:25 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 13/14-12-21 au JE/VE 14/15-04-22 du MA/ME 19/20-04-22 au ME/JE 25/26-05-22 du LU/MA 30/31-05-22 au JE/VE 02/03-06-22 et du MA/ME 07/08-06-22 au JE/VE 07/08-07-22 Sauf le(s) : VE/SA 31/01-01-22,VE/SA 07/08-01-22, VE/SA 14/15-01-22,VE/SA 21/22-01-22,VE/SA 28/29-01-22, VE/SA 04/05-02-22,VE/SA 11/12-02-22, VE/SA 18/19-02-22, VE/SA 25/26-02-22,VE/SA 04/05-03-22, VE/SA 11/12-03-22,VE/SA 18/19-03-22, VE/SA 25/26-03-22, VE/SA 01/02-04-22, VE/SA 08/09-04-22,VE/SA 22/23-04-22, VE/SA 29/30-04-22,VE/SA 06/07-05-22, VE/SA 13/14-05-22,VE/SA 20/21-05-22, VE/SA 10/11-06-22,VE/SA 17/18-06-22,VE/SA 24/25-06-22, VE/SA 01/02-07-22 | Gen, V1, 1V/2, 06:20, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_66 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Aubagne-Toulon_012 | Aubagne-00 | Toulon-BV | 22:55 | 05:15 J+1 | 22:55 | 05:15 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 11/12-07-22 au VE/SA 09/10-12-22 Sauf le(s) : JE/VE 14/15-07-22,LU/MA 15/16-08-22, MA/ME 01/02-11-22,VE/SA 11/12-11-22 | Gen, V2, 1V/2, 06:20, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_66 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP22_Toulon-LesArcs_006 | Puget-Ville-00 | Pignans-00 | 21:00 | 06:27 J+1 | 21:00 | 06:27 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-12-21 au JE/VE 16/17-12-21 | Cap, A, 09:27, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021518_04 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Toulon-LesArcs_009 | Puget-Ville-00 | Pignans-00 | 22:10 | 06:41 J+1 | 22:10 | 06:41 J+1 | Jours d'application : VE/SA Périodes : Et le(s) : VE/SA 17/18-12-21 | Cap, A, 08:31, Passe-minuit, VE/SA | CHA21_0021518_04 | NON | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Toulon-LesArcs_008 | Puget-Ville-00 | Les Arcs-Draguignan-V4 | 21:00 | 06:05 J+1 | 21:00 | 06:05 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-12-21 au JE/VE 16/17-12-21 | Def, V2, 2V/2, 09:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021518_04 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Toulon-LesArcs_016 | Puget-Ville-00 | Les Arcs-Draguignan-V4 | 22:10 | 06:41 J+1 | 22:10 | 06:41 J+1 | Jours d'application : VE/SA Périodes : Et le(s) : VE/SA 17/18-12-21 | Def, V2, 2V/2, 08:31, Passe-minuit, VE/SA | CHA21_0021518_04 | NON | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Toulon-LesArcs_017 | Puget-Ville-00 | Les Arcs-Draguignan-V4 | 22:10 | 06:41 J+1 | 22:10 | 06:41 J+1 | Jours d'application : VE/SA Périodes : Et le(s) : VE/SA 17/18-12-21 | Def, V1, 2V/2, 08:31, Passe-minuit, VE/SA | CHA21_0021518_04 | NON | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Toulon-LesArcs_019 | Puget-Ville-00 | Les Arcs-Draguignan-V4 | 21:00 | 06:27 J+1 | 21:00 | 06:27 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-12-21 au JE/VE 16/17-12-21 | Def, V1, 2V/2, 09:27, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021518_04 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Toulon-LesArcs_020 | Carnoules-00 | Le Muy-00 | 22:01 | 06:04 J+1 | 22:01 | 06:04 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 07/08-02-22 au JE/VE 17/18-03-22 | Def, V1, , 08:03, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0023831_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Toulon-LesArcs_021 | Carnoules-00 | Les Arcs-Draguignan-00 | 22:01 | 06:04 J+1 | 22:01 | 06:04 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 07/08-02-22 au JE/VE 17/18-03-22 | Def, V2, , 08:03, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0023831_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Toulon-LesArcs_022 | Carnoules-00 | Le Muy-00 | 23:00 | 05:20 J+1 | 23:00 | 05:20 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 16/17-01-22 au DI/LU 27/28-03-22 | Def, V1,V2, , 06:20, Passe-minuit, DI/LU | CHA21_0023831_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Toulon-LesArcs_023 | Puget-Ville-00 | Les Arcs-Draguignan-V4 | 22:40 | 05:08 J+1 | 22:40 | 05:08 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 20/21-12-21 au JE/VE 23/24-12-21 et du LU/MA 03/04-01-22 au JE/VE 20/21-01-22 | Def, V1,V2, 2V/2, 06:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021518_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Toulon-LesArcs_024 | Puget-Ville-00 | Les Arcs-Draguignan-V4 | 23:54 | 05:39 J+1 | 23:54 | 06:09 J+1 | Jours d'application : VE/SA Périodes : du VE/SA 24/25-12-21 au VE/SA 21/22-01-22 Sauf le(s) : VE/SA 31/01-01-22 | Def, V1,V2, 2V/2, 06:00, Passe-minuit, VE/SA | CHA21_0021518_04 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Toulon-LesArcs_025 | Toulon-V4 | Le Muy-00 | 22:50 | 05:08 J+1 | 22:50 | 05:08 J+1 | Jours d'application : LU/MA Périodes : Et le(s) : LU/MA 18/19-04-22 et LU/MA 06/07-06-22 | Def, V1,V2, 2V/2, 06:18, Passe-minuit, LU/MA | CHA16_0011819_68,CHA20_0018189_03,CHA22_0022703_03,CHA19_0015533_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Toulon-LesArcs_001 | Toulon-V4 | Le Muy-00 | 22:40 | 05:08 J+1 | 22:40 | 05:08 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-12-21 au MA/ME 24/25-05-22 du LU/MA 30/31-05-22 au MA/ME 12/13-07-22 et du LU/MA 18/19-07-22 au JE/VE 08/09-12-22 Sauf le(s) : LU/MA 18/19-04-22,LU/MA 06/07-06-22, LU/MA 15/16-08-22,MA/ME 01/02-11-22,JE/VE 10/11-11-22 | Gen, V1,V2, 2V/2, 06:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021987_11,CHA19_0015533_04,CHA16_0011819_68,CHA21_0022003_18,CHA20_0018189_03,CHA20_0019010_26,CHA21_0023831_01,CHA21_0021293_02,CHA22_0022703_03 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 6 | 6 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 1 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 4 | 0 | 0 | 0 | 4 | 4 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0
|  | FEN22_Toulon-LesArcs_002 | Toulon-V4 | Le Muy-00 | 23:30 | 06:04 J+1 | 00:03 J+1 | 05:39 J+1 | Jours d'application : MA/ME,ME/JE,JE/VE,VE/SA Périodes : du VE/SA 20/21-05-22 au VE/SA 27/28-05-22 et du VE/SA 08/09-07-22 au VE/SA 15/16-07-22 Et le(s) : VE/SA 17/18-12-21 VE/SA 24/25-12-21 VE/SA 31/01-01-22 VE/SA 07/08-01-22 VE/SA 14/15-01-22 VE/SA 21/22-01-22 VE/SA 28/29-01-22 VE/SA 04/05-02-22 VE/SA 11/12-02-22 VE/SA 18/19-02-22 VE/SA 25/26-02-22 VE/SA 04/05-03-22 VE/SA 11/12-03-22 VE/SA 18/19-03-22 VE/SA 25/26-03-22 VE/SA 01/02-04-22 VE/SA 08/09-04-22 VE/SA 15/16-04-22 VE/SA 22/23-04-22 VE/SA 29/30-04-22 VE/SA 06/07-05-22 VE/SA 13/14-05-22 VE/SA 03/04-06-22 VE/SA 10/11-06-22 VE/SA 17/18-06-22 VE/SA 24/25-06-22 VE/SA 01/02-07-22 VE/SA 22/23-07-22 VE/SA 29/30-07-22 VE/SA 05/06-08-22 VE/SA 12/13-08-22 VE/SA 19/20-08-22 VE/SA 26/27-08-22 VE/SA 02/03-09-22 VE/SA 09/10-09-22 VE/SA 16/17-09-22 VE/SA 23/24-09-22 VE/SA 30/01-10-22 VE/SA 07/08-10-22 VE/SA 14/15-10-22 VE/SA 21/22-10-22 VE/SA 28/29-10-22 VE/SA 04/05-11-22 JE/VE 10/11-11-22 VE/SA 18/19-11-22 VE/SA 25/26-11-22 VE/SA 02/03-12-22 et VE/SA 09/10-12-22 Sauf le(s) : MA/ME 24/25-05-22,JE/VE 26/27-05-22,MA/ME 12/13-07-22,JE/VE 14/15-07-22 | Gen, V1,V2, 2V/2, 06:05, Passe-minuit, MA/ME,ME/JE,JE/VE,VE/SA | CHA21_0021987_11,CHA16_0011819_68,CHA19_0015533_04,CHA21_0021293_02,CHA20_0018189_03,CHA20_0019010_26,CHA22_0022703_03,CHA21_0022003_18 | NON | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
|  | FEN22_Toulon-LesArcs_003 | Toulon-V4 | La Farlède-00 | 09:42 | 10:42 | 09:50 | 10:50 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : ME 26-01-22,LU 18-04-22,JE 26-05-22, LU 06-06-22,JE 14-07-22,LU 15-08-22,MA 01-11-22, VE 11-11-22 | Sur, V1, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_68 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Toulon-LesArcs_004 | Toulon-V4 | La Pauline-Hyères-GZ | 10:16 | 11:16 | 10:08 | 11:08 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : ME 26-01-22,LU 18-04-22,JE 26-05-22, LU 06-06-22,JE 14-07-22,LU 15-08-22,MA 01-11-22, VE 11-11-22 | Sur, V2, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_68 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Toulon-LesArcs_005 | La Pauline-Hyères-GZ | Le Muy-00 | 09:50 | 10:50 | 10:26 | 11:26 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : ME 26-01-22,LU 18-04-22,JE 26-05-22, LU 06-06-22,JE 14-07-22,LU 15-08-22,MA 01-11-22, VE 11-11-22 | Sur, V1, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_68 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Toulon-LesArcs_007 | La Pauline-Hyères-BF | Les Arcs-Draguignan-00 | 10:10 | 11:10 | 09:37 | 10:37 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : ME 26-01-22,LU 18-04-22,JE 26-05-22, LU 06-06-22,JE 14-07-22,LU 15-08-22,MA 01-11-22, VE 11-11-22 | Sur, V2, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_68 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP22_LesArcs_005 | Les Arcs-Draguignan-V3 | Le Muy-00 | 22:01 | 06:04 J+1 | 22:01 | 06:04 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 07/08-02-22 au JE/VE 17/18-03-22 | Cap, A, 08:03, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0023831_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_LesArcs_006 | Les Arcs-Draguignan-V3 | Le Muy-00 | 22:40 | 05:08 J+1 | 22:40 | 05:08 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 17/18-01-22 au JE/VE 03/04-02-22 et du LU/MA 21/22-03-22 au JE/VE 24/25-03-22 | Cap, A, 06:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0023831_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_LesArcs_007 | Les Arcs-Draguignan-V3 | Le Muy-00 | 23:00 | 05:20 J+1 | 23:00 | 05:20 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 16/17-01-22 au DI/LU 27/28-03-22 | Cap, A, 06:20, Passe-minuit, DI/LU | CHA21_0023831_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_LesArcs-StRaphael_019 | Les Arcs-Draguignan-00 | Roquebrune-sur-Argens-00 | 22:01 | 06:04 J+1 | 22:01 | 06:04 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 07/08-02-22 au JE/VE 17/18-03-22 | Def, V1, , 08:03, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0023831_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_LesArcs-StRaphael_020 | Les Arcs-Draguignan-V3 | Roquebrune-sur-Argens-00 | 22:01 | 06:04 J+1 | 22:01 | 06:04 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 07/08-02-22 au JE/VE 17/18-03-22 | Def, V2, , 08:03, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0023831_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_LesArcs-StRaphael_021 | Les Arcs-Draguignan-V3 | Roquebrune-sur-Argens-00 | 23:00 | 05:20 J+1 | 23:00 | 05:20 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 16/17-01-22 au DI/LU 27/28-03-22 | Def, V1,V2, , 06:20, Passe-minuit, DI/LU | CHA21_0023831_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_LesArcs-StRaphael_001 | Les Arcs-Draguignan-V3 | Boulouris-sur-Mer-00 | 22:44 | 05:12 J+1 | 22:44 | 05:12 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-12-21 au MA/ME 24/25-05-22 du LU/MA 30/31-05-22 au MA/ME 12/13-07-22 et du LU/MA 18/19-07-22 au JE/VE 08/09-12-22 Sauf le(s) : LU/MA 18/19-04-22,LU/MA 06/07-06-22, LU/MA 15/16-08-22,MA/ME 01/02-11-22,JE/VE 10/11-11-22 | Gen, V1,V2, 2V/2, 06:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA16_0011819_69,CHA21_0022001_18,CHA21_0023831_03,CHA20_0019010_28,CHA21_0022003_19 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | FEN22_LesArcs-StRaphael_002 | Les Arcs-Draguignan-V3 | Boulouris-sur-Mer-00 | 00:03 | 06:15 | 00:20 | 06:15 | Jours d'application : ME,JE,VE,SA Périodes : Et le(s) : SA 18-12-21 SA 08-01-22 SA 15-01-22 SA 22-01-22 SA 29-01-22 SA 05-02-22 SA 12-02-22 SA 19-02-22 SA 26-02-22 SA 05-03-22 SA 12-03-22 SA 19-03-22 SA 26-03-22 SA 02-04-22 SA 09-04-22 SA 16-04-22 SA 23-04-22 SA 30-04-22 SA 07-05-22 SA 14-05-22 SA 21-05-22 SA 28-05-22 SA 04-06-22 SA 11-06-22 SA 18-06-22 SA 25-06-22 SA 02-07-22 SA 09-07-22 SA 16-07-22 SA 23-07-22 SA 30-07-22 SA 06-08-22 SA 13-08-22 SA 20-08-22 SA 27-08-22 SA 03-09-22 SA 10-09-22 SA 17-09-22 SA 24-09-22 SA 01-10-22 SA 08-10-22 SA 15-10-22 SA 22-10-22 SA 29-10-22 SA 05-11-22 SA 12-11-22 SA 19-11-22 SA 26-11-22 SA 03-12-22 et SA 10-12-22 | Gen, V1,V2, 2V/2, 06:03, Nuit non passe-minuit, ME,JE,VE,SA | CHA16_0011819_69,CHA21_0022001_18,CHA21_0022003_19 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | FEN22_LesArcs-StRaphael_003 | Les Arcs-Draguignan-00 | Boulouris-sur-Mer-00 | 10:02 | 11:02 | 10:16 | 11:16 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : LU 18-04-22,JE 26-05-22,LU 06-06-22, JE 14-07-22,LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, V1, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_69 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_LesArcs-StRaphael_004 | Les Arcs-Draguignan-V3 | Boulouris-sur-Mer-00 | 13:33 | 14:33 | 13:16 | 14:16 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : LU 18-04-22,JE 26-05-22,LU 06-06-22, JE 14-07-22,LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, V2, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_69 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_StRaphael-Nice_001 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 23:07 | 05:08 J+1 | 23:07 | 05:08 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-12-21 au MA/ME 24/25-05-22 du LU/MA 30/31-05-22 au MA/ME 12/13-07-22 et du LU/MA 18/19-07-22 au JE/VE 08/09-12-22 Sauf le(s) : MA/ME 15/16-02-22,MA/ME 22/23-02-22, LU/MA 18/19-04-22,LU/MA 06/07-06-22, JE/VE 21/22-07-22,LU/MA 08/09-08-22, ME/JE 10/11-08-22,LU/MA 15/16-08-22, ME/JE 24/25-08-22,MA/ME 01/02-11-22,JE/VE 10/11-11-22 | Gen, ANC,V1,V2, 3V/3, 06:01, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021550_04,CHA19_0016215_17,CHA21_0021246_08,CHA21_0021236_04,CHA21_0022001_19,CHA16_0011819_70,CHA21_0021958_23,CHA21_0022003_20,CHA20_0019010_29 | NON | 0 | 4 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 4 | 3 | 3 | 3 | 0 | 0 | 0 | 5 | 4 | 4 | 4 | 0 | 0 | 0 | 5 | 4 | 4 | 4 | 0 | 0 | 0 | 5 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 4 | 0 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0
|  | FEN22_StRaphael-Nice_005 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 10:12 | 11:12 | 11:33 | 12:33 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au ME 25-05-22 et du LU 30-05-22 au VE 09-12-22 Sauf le(s) : LU 18-04-22,LU 06-06-22,JE 14-07-22,LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, V1, 1V/3, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_70 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_StRaphael-Nice_006 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 13:13 | 14:13 | 12:05 | 13:05 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : LU 18-04-22,JE 26-05-22,LU 06-06-22,JE 14-07-22,LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, V2, 1V/3, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_70 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_StRaphael-Nice_007 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 00:40 | 05:53 | 01:17 | 05:48 | Jours d'application : MA,ME,JE,VE,SA Périodes : Et le(s) : SA 18-12-21 et SA 08-01-22 et SA 15-01-22 et SA 22-01-22 et SA 29-01-22 et SA 05-02-22 et SA 12-02-22 et SA 19-02-22 et SA 26-02-22 et SA 05-03-22 et SA 12-03-22 et SA 19-03-22 et SA 26-03-22 et SA 02-04-22 et SA 09-04-22 et SA 16-04-22 et SA 23-04-22 et SA 30-04-22 et SA 07-05-22 et SA 14-05-22 et SA 21-05-22 et SA 28-05-22 et SA 04-06-22 et SA 11-06-22 et SA 18-06-22 et SA 25-06-22 et SA 02-07-22 et SA 09-07-22 et SA 16-07-22 et SA 23-07-22 et SA 30-07-22 et SA 13-08-22 et SA 20-08-22 et SA 27-08-22 et SA 03-09-22 et SA 10-09-22 et SA 17-09-22 et SA 24-09-22 et SA 01-10-22 et SA 08-10-22 et SA 15-10-22 et SA 22-10-22 et SA 29-10-22 et SA 05-11-22 et SA 12-11-22 et SA 19-11-22 et SA 26-11-22 et SA 03-12-22 et SA 10-12-22 | Gen, ANC,V1,V2, 3V/3, 04:52, Nuit non passe-minuit, MA,ME,JE,VE,SA | CHA21_0021246_08,CHA19_0016215_17,CHA16_0011819_70,CHA21_0021236_04,CHA21_0022001_19,CHA21_0021958_23,CHA20_0019010_29,CHA21_0022003_20 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  | FEN22_StRaphael-Nice_008 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 23:26 | 05:55 J+1 | 23:26 | 05:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : Et le(s) : VE/SA 17/18-12-21 VE/SA 24/25-12-21 VE/SA 07/08-01-22 VE/SA 14/15-01-22 VE/SA 21/22-01-22 VE/SA 28/29-01-22 VE/SA 04/05-02-22 VE/SA 11/12-02-22 VE/SA 18/19-02-22 VE/SA 25/26-02-22 VE/SA 04/05-03-22 VE/SA 11/12-03-22 VE/SA 18/19-03-22 VE/SA 25/26-03-22 VE/SA 01/02-04-22 VE/SA 08/09-04-22 VE/SA 15/16-04-22 VE/SA 22/23-04-22 VE/SA 29/30-04-22 VE/SA 06/07-05-22 VE/SA 13/14-05-22 VE/SA 20/21-05-22 VE/SA 27/28-05-22 VE/SA 03/04-06-22 VE/SA 10/11-06-22 VE/SA 17/18-06-22 VE/SA 24/25-06-22 VE/SA 01/02-07-22 VE/SA 08/09-07-22 VE/SA 15/16-07-22 VE/SA 22/23-07-22 VE/SA 29/30-07-22 VE/SA 12/13-08-22 VE/SA 19/20-08-22 VE/SA 26/27-08-22 VE/SA 02/03-09-22 VE/SA 09/10-09-22 VE/SA 16/17-09-22 VE/SA 23/24-09-22 VE/SA 30/01-10-22 VE/SA 07/08-10-22 VE/SA 14/15-10-22 VE/SA 21/22-10-22 VE/SA 28/29-10-22 VE/SA 04/05-11-22 VE/SA 18/19-11-22 VE/SA 25/26-11-22 VE/SA 02/03-12-22 et VE/SA 09/10-12-22 | Gen, V1, 1V/2, 06:29, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_70 | NON | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | FEN22_StRaphael-Nice_009 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 23:26 | 05:55 J+1 | 23:26 | 05:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : Et le(s) : VE/SA 17/18-12-21 VE/SA 24/25-12-21 VE/SA 07/08-01-22 VE/SA 14/15-01-22 VE/SA 21/22-01-22 VE/SA 28/29-01-22 VE/SA 04/05-02-22 VE/SA 11/12-02-22 VE/SA 18/19-02-22 VE/SA 25/26-02-22 VE/SA 04/05-03-22 VE/SA 11/12-03-22 VE/SA 18/19-03-22 VE/SA 25/26-03-22 VE/SA 01/02-04-22 VE/SA 08/09-04-22 VE/SA 15/16-04-22 VE/SA 22/23-04-22 VE/SA 29/30-04-22 VE/SA 06/07-05-22 VE/SA 13/14-05-22 VE/SA 20/21-05-22 VE/SA 27/28-05-22 VE/SA 03/04-06-22 VE/SA 10/11-06-22 VE/SA 17/18-06-22 VE/SA 24/25-06-22 VE/SA 01/02-07-22 VE/SA 08/09-07-22 VE/SA 15/16-07-22 VE/SA 22/23-07-22 VE/SA 29/30-07-22 VE/SA 12/13-08-22 VE/SA 19/20-08-22 VE/SA 26/27-08-22 VE/SA 02/03-09-22 VE/SA 09/10-09-22 VE/SA 16/17-09-22 VE/SA 23/24-09-22 VE/SA 30/01-10-22 VE/SA 07/08-10-22 VE/SA 14/15-10-22 VE/SA 21/22-10-22 VE/SA 28/29-10-22 VE/SA 04/05-11-22 VE/SA 18/19-11-22 VE/SA 25/26-11-22 VE/SA 02/03-12-22 et VE/SA 09/10-12-22 | Gen, V2, 1V/2, 06:29, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_70 | NON | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | FEN22_StRaphael-Nice_010 | Juan-les-Pins-00 | Cros-de-Cagnes-00 | 23:26 | 05:55 J+1 | 23:26 | 05:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : Et le(s) : VE/SA 17/18-12-21 VE/SA 24/25-12-21 VE/SA 07/08-01-22 VE/SA 14/15-01-22 VE/SA 21/22-01-22 VE/SA 28/29-01-22 VE/SA 04/05-02-22 VE/SA 11/12-02-22 VE/SA 18/19-02-22 VE/SA 25/26-02-22 VE/SA 04/05-03-22 VE/SA 11/12-03-22 VE/SA 18/19-03-22 VE/SA 25/26-03-22 VE/SA 01/02-04-22 VE/SA 08/09-04-22 VE/SA 15/16-04-22 VE/SA 22/23-04-22 VE/SA 29/30-04-22 VE/SA 06/07-05-22 VE/SA 13/14-05-22 VE/SA 20/21-05-22 VE/SA 27/28-05-22 VE/SA 03/04-06-22 VE/SA 10/11-06-22 VE/SA 17/18-06-22 VE/SA 24/25-06-22 VE/SA 01/02-07-22 VE/SA 08/09-07-22 VE/SA 15/16-07-22 VE/SA 22/23-07-22 VE/SA 29/30-07-22 VE/SA 12/13-08-22 VE/SA 19/20-08-22 VE/SA 26/27-08-22 VE/SA 02/03-09-22 VE/SA 09/10-09-22 VE/SA 16/17-09-22 VE/SA 23/24-09-22 VE/SA 30/01-10-22 VE/SA 07/08-10-22 VE/SA 14/15-10-22 VE/SA 21/22-10-22 VE/SA 28/29-10-22 VE/SA 04/05-11-22 VE/SA 18/19-11-22 VE/SA 25/26-11-22 VE/SA 02/03-12-22 et VE/SA 09/10-12-22 | Gen, ANC, 1V/3, 06:29, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_70 | NON | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | FEN22_StRaphael-Nice_011 | Juan-les-Pins-00 | Cros-de-Cagnes-00 | 12:20 | 13:20 | 12:20 | 13:20 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 09-12-22 Sauf le(s) : LU 18-04-22,JE 26-05-22,LU 06-06-22, JE 14-07-22,LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, ANC, 1V/3, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_70 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP22_Nice_039 | Nice-Ville-00 | Nice-St-Roch-P1 | 00:01 | 05:01 | 00:01 | 05:01 | Jours d'application : MA,ME,JE,VE Périodes : du MA 11-01-22 au VE 21-01-22 | Cap, B,C,E,F,G,V1,V2,VA,VB,Z, 05:00, Nuit non passe-minuit, MA,ME,JE,VE | CHA21_0021964_18 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice_040 | Nice-Ville-00 | Nice-St-Roch-P1 | 00:18 | 05:35 | 00:18 | 05:35 | Jours d'application : SA Périodes : du SA 15-01-22 au SA 22-01-22 | Cap, B,C,E,F,G,V1,V2,VA,VB,Z, 05:17, Nuit non passe-minuit, SA | CHA21_0021964_18 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice_041 | Nice-St-Augustin-00 | Nice-Ville-00 | 00:03 | 05:03 | 00:03 | 05:03 | Jours d'application : MA,ME,JE,VE Périodes : du MA 25-01-22 au VE 04-02-22 | Cap, 4,B,C,E,F,V1,V2, 05:00, Nuit non passe-minuit, MA,ME,JE,VE | CHA21_0021964_18 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice_043 | Nice-Ville-00 | Nice-St-Roch-P1 | 00:40 | 06:00 | 01:17 | 05:48 | Jours d'application : SA Périodes : du SA 29-01-22 au SA 05-02-22 | Cap, B,C,E,F,G,V1,V2,VA,VB,Z, 04:55, Nuit non passe-minuit, SA | CHA21_0021964_18 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice_044 | Nice-Ville-00 | Nice-St-Roch-PA | 09:05 | 16:35 | 09:05 | 16:35 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 07-03-22 au VE 29-07-22 | Cap, VA,VB, 07:30, Jour, LU,MA,ME,JE,VE | CHA22_0022921_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice_045 | Nice-Ville-00 | Nice-St-Roch-PA | 09:50 | 16:20 | 09:50 | 16:20 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 21-02-22 au VE 04-03-22 et du LU 01-08-22 au VE 19-08-22 | Cap, VA,VB, 06:30, Jour, LU,MA,ME,JE,VE | CHA22_0022921_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice_046 | Nice-Ville-00 | Nice-Riquier-00 | 23:45 | 05:10 J+1 | 23:45 | 05:10 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 03/04-01-22 au ME/JE 19/20-01-22 et du LU/MA 04/05-04-22 au JE/VE 05/06-05-22 | Cap, V2, 05:25, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021192_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice_047 | Nice-Ville-00 | Nice-Riquier-00 | 00:22 | 05:37 | 00:22 | 05:37 | Jours d'application : SA Périodes : du SA 08-01-22 au SA 15-01-22 et du SA 09-04-22 au SA 07-05-22 | Cap, V2, 05:15, Nuit non passe-minuit, SA | CHA21_0021192_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice_048 | Nice-Ville-00 | Nice-Riquier-00 | 21:58 | 05:38 J+1 | 21:58 | 05:38 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 04/05-04-22 au VE/SA 08/09-04-22 | Cap, V1, 07:40, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA21_0021192_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice_049 | Nice-Ville-00 | Nice-Riquier-00 | 23:45 | 05:10 J+1 | 23:45 | 05:10 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 03/04-01-22 au JE/VE 20/21-01-22 | Cap, V1, 05:25, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021192_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice_050 | Nice-Ville-00 | Nice-Riquier-00 | 00:22 | 05:37 | 00:22 | 05:37 | Jours d'application : SA Périodes : du SA 08-01-22 au SA 15-01-22 | Cap, V1, 05:15, Nuit non passe-minuit, SA | CHA21_0021192_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice_051 | Nice-Ville-00 | Nice-Riquier-00 | 22:05 | 05:43 J+1 | 22:05 | 05:43 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du JE/VE 20/21-01-22 au VE/SA 28/29-01-22 et du LU/MA 21/22-02-22 au VE/SA 01/02-04-22 | Cap, V2, 07:38, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA21_0021192_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice_052 | Nice-Ville-00 | Nice-Riquier-00 | 22:00 | 05:40 | 22:00 | 05:40 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du JE 20-01-22 au SA 02-04-22 | Cap, 20-01-2022, 02-04-2022, Continu | CHA21_0021192_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice_054 | Nice-Ville-00 | Nice-Riquier-00 | 22:01 | 05:38 J+1 | 22:01 | 05:38 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 31/01-02-22 au VE/SA 18/19-02-22 | Cap, V1, 07:37, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA21_0021192_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice_055 | Nice-Ville-00 | Nice-Riquier-00 | 22:01 | 05:38 J+1 | 22:01 | 05:38 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 31/01-02-22 au LU/MA 14/15-02-22 et du JE/VE 17/18-02-22 au VE/SA 18/19-02-22 | Cap, V2, 07:37, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA21_0021192_06 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP22_Nice-Menton_001 | Carnolès-00 | Menton-Garavan-00 | 23:45 | 05:10 J+1 | 23:45 | 05:10 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 28/29-11-22 au JE/VE 08/09-12-22 | Cap, 1BIS, 05:25, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA22_0022928_10 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | CAP22_Nice-Menton_002 | Carnolès-00 | Menton-Garavan-00 | 00:18 | 05:35 | 00:18 | 05:35 | Jours d'application : SA Périodes : du SA 03-12-22 au SA 10-12-22 | Cap, 1BIS, 05:17, Nuit non passe-minuit, SA | CHA22_0022928_10 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | DEF22_Nice-Menton_010 | Nice-Ville-00 | Èze-00 | 00:01 | 05:00 | 00:01 | 05:00 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du DI 12-12-21 au VE 21-01-22 | Def, 1V/2, 12-12-2021, 21-01-2022, Continu | CHA21_0020754_06,CHA21_0021192_07 | NON | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Nice-Menton_013 | Nice-Ville-00 | Èze-00 | 21:58 | 05:38 J+1 | 21:58 | 05:38 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 04/05-04-22 au VE/SA 08/09-04-22 | Def, V1, , 07:40, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA21_0021192_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Nice-Menton_017 | Nice-Ville-00 | Èze-00 | 22:08 | 05:38 J+1 | 22:08 | 05:38 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 31/01-02-22 au LU/MA 14/15-02-22 et du JE/VE 17/18-02-22 au VE/SA 18/19-02-22 | Def, V2, , 07:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA21_0020754_06,CHA21_0021192_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF22_Nice-Menton_018 | Monaco-Monte-Carlo-00 | Menton-00 | 22:00 | 08:00 J+2 | 22:00 | 08:00 J+2 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 25-11-22 au DI 27-11-22 | Def, V1,V2, , 34:00, Continu, VE,SA,DI | CHA22_0023717_01 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Nice-Menton_019 | Nice-Ville-00 | Èze-00 | 22:10 | 05:25 J+1 | 22:10 | 05:25 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 05/06-09-22 au JE/VE 24/25-11-22 Sauf le(s) : VE/SA 11/12-11-22 | Def, V2, , 07:15, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA22_0022616_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF22_Nice-Menton_020 | Nice-Ville-00 | Èze-00 | 22:00 | 08:00 J+2 | 22:00 | 08:00 J+2 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 25-11-22 au DI 27-11-22 | Def, V1,V2, , 34:00, Continu, VE,SA,DI | CHA22_0022616_01 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Nice-Menton_022 | Nice-Ville-00 | Èze-00 | 22:10 | 05:25 J+1 | 22:10 | 05:25 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 05/06-09-22 au VE/SA 25/26-11-22 Sauf le(s) : MA/ME 25/26-10-22,VE/SA 11/12-11-22 | Def, V1, , 07:15, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA22_0022616_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Nice-Menton_025 | Monaco-Monte-Carlo-00 | Menton-00 | 22:28 | 05:33 J+1 | 22:28 | 05:33 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 05/06-09-22 au VE/SA 09/10-12-22 Sauf le(s) : MA/ME 25/26-10-22 | Def, V1, , 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA22_0022631_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | DEF22_Nice-Menton_026 | Monaco-Monte-Carlo-00 | Menton-00 | 22:28 | 05:33 J+1 | 22:28 | 05:33 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 05/06-09-22 au VE/SA 09/10-12-22 Sauf le(s) : JE/VE 08/09-09-22 | Def, V2, , 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA22_0022631_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | DEF22_Nice-Menton_027 | Nice-Ville-00 | Èze-00 | 23:45 | 05:10 J+1 | 23:45 | 05:10 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 03/04-01-22 au JE/VE 20/21-01-22 et du LU/MA 04/05-04-22 au JE/VE 21/22-04-22 | Def, V2, , 05:25, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021192_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Nice-Menton_028 | Nice-Ville-00 | Èze-00 | 00:22 | 05:37 | 00:22 | 05:37 | Jours d'application : SA Périodes : du SA 08-01-22 au SA 22-01-22 et du SA 09-04-22 au SA 23-04-22 | Def, V2, , 05:15, Nuit non passe-minuit, SA | CHA21_0021192_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Nice-Menton_029 | Nice-Ville-00 | Èze-00 | 22:00 | 05:40 | 22:00 | 05:40 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du JE 20-01-22 au SA 02-04-22 | Def, , 20-01-2022, 02-04-2022, Continu | CHA21_0021192_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Nice-Menton_030 | Nice-Ville-00 | Èze-00 | 22:08 | 05:43 J+1 | 22:08 | 05:43 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA,SA/DI Périodes : du JE/VE 20/21-01-22 au VE/SA 28/29-01-22 et du LU/MA 21/22-02-22 au VE/SA 01/02-04-22 Sauf le(s) : SA/DI 22/23-01-22,SA/DI 26/27-02-22, SA/DI 05/06-03-22,SA/DI 12/13-03-22,SA/DI 19/20-03-22, SA/DI 26/27-03-22 | Def, V2, , 07:35, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA,SA/DI | CHA21_0021192_07 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Nice-Menton_032 | Nice-Ville-00 | Èze-00 | 22:08 | 04:30 J+1 | 22:08 | 04:30 J+1 | Jours d'application : MA/ME,ME/JE Périodes : du MA/ME 15/16-02-22 au ME/JE 16/17-02-22 | Def, V2, , 06:22, Passe-minuit, MA/ME,ME/JE | CHA21_0021246_10,CHA16_0011819_72 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Nice-Menton_001 | Nice-Ville-00 | Menton-Garavan-00 | 23:45 | 04:45 J+1 | 23:45 | 04:45 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-12-21 au LU/MA 14/15-02-22 du JE/VE 17/18-02-22 au MA/ME 24/25-05-22 du LU/MA 30/31-05-22 au MA/ME 12/13-07-22 du LU/MA 18/19-07-22 au JE/VE 27/28-10-22 et du ME/JE 02/03-11-22 au JE/VE 08/09-12-22 Sauf le(s) : ME/JE 10/11-08-22,LU/MA 15/16-08-22, JE/VE 10/11-11-22 | Gen, V1,V2, 2V/2, 05:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021246_10,CHA19_0016215_19,CHA22_0022988_02,CHA22_0023717_01,CHA21_0020754_06,CHA22_0022616_01,CHA22_0022631_01,CHA21_0022003_22,CHA21_0022001_21,CHA21_0021192_07,CHA22_0022928_10,CHA16_0011819_72 | NON | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 1 | 1 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 0
|  | FEN22_Nice-Menton_003 | Nice-Ville-00 | Menton-Garavan-00 | 00:35 | 05:35 | 00:35 | 05:35 | Jours d'application : MA,ME,VE,SA Périodes : Et le(s) : SA 02-07-22 SA 09-07-22 SA 16-07-22 SA 23-07-22 SA 30-07-22 SA 06-08-22 SA 13-08-22 SA 20-08-22 SA 27-08-22 SA 03-09-22 et SA 10-09-22 | Gen, V1,V2, 2V/2, 05:00, Nuit non passe-minuit, MA,ME,VE,SA | CHA21_0021246_10,CHA22_0022631_01,CHA16_0011819_72,CHA22_0022616_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN22_Nice-Menton_004 | Nice-Ville-00 | Menton-Garavan-00 | 11:36 | 12:36 | 12:20 | 13:20 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 08-04-22 du MA 19-04-22 au ME 25-05-22 et du LU 30-05-22 au VE 09-12-22 Sauf le(s) : LU 06-06-22,JE 14-07-22,LU 15-08-22, MA 01-11-22,VE 11-11-22 | Sur, V1, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_72 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Nice-Menton_005 | Nice-Ville-00 | Menton-Garavan-00 | 10:27 | 11:27 | 09:40 | 10:40 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 08-04-22 et du MA 19-04-22 au VE 09-12-22 Sauf le(s) : JE 26-05-22,LU 06-06-22,JE 14-07-22, LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, V2, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_72 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN22_Nice-Menton_008 | Nice-Ville-00 | Menton-Garavan-00 | 00:18 | 05:35 | 00:18 | 05:35 | Jours d'application : LU,ME,JE,VE,SA Périodes : du JE 26-05-22 au SA 28-05-22 et du VE 11-11-22 au SA 12-11-22 Et le(s) : SA 18-12-21 SA 08-01-22 SA 15-01-22 SA 22-01-22 SA 29-01-22 SA 05-02-22 SA 12-02-22 SA 19-02-22 SA 26-02-22 SA 05-03-22 SA 12-03-22 SA 19-03-22 SA 26-03-22 SA 02-04-22 SA 09-04-22 SA 16-04-22 SA 23-04-22 SA 30-04-22 SA 07-05-22 SA 14-05-22 SA 21-05-22 SA 04-06-22 SA 11-06-22 SA 18-06-22 SA 25-06-22 SA 17-09-22 SA 24-09-22 SA 01-10-22 SA 08-10-22 SA 15-10-22 SA 22-10-22 SA 29-10-22 SA 05-11-22 SA 19-11-22 SA 26-11-22 SA 03-12-22 et SA 10-12-22 Sauf le(s) : VE 27-05-22 | Gen, V1,V2, 2V/2, 05:17, Nuit non passe-minuit, LU,ME,JE,VE,SA | CHA21_0021246_10,CHA19_0016215_19,CHA22_0022988_02,CHA16_0011819_72,CHA22_0023717_01,CHA21_0020754_06,CHA22_0022616_01,CHA22_0022928_10,CHA21_0022001_21,CHA21_0022003_22 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7
|  | DEF22_Menton-Vintimille_011 | Menton-00 | Vintimille-WI | 00:01 | 05:06 | 00:01 | 05:06 | Jours d'application : SA Périodes : du SA 08-01-22 au SA 02-04-22 Et le(s) : SA 18-12-21 | Def, V2, 1V/2, 05:05, Nuit non passe-minuit, SA | CHA21_0021246_11,CHA16_0011819_73 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF22_Menton-Vintimille_012 | Menton-PV | Vintimille-WI | 23:00 | 07:00 J+1 | 23:00 | 07:00 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 07/08-05-22 | Def, V1,V2, 2V/2, 08:00, Passe-minuit, SA/DI | CHA16_0011819_73 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Yes | FEN22_Menton-Vintimille_001 | Menton-00 | Vintimille-WI | 23:28 | 04:30 J+1 | 23:28 | 04:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-12-21 au MA/ME 24/25-05-22 du LU/MA 30/31-05-22 au MA/ME 12/13-07-22 et du LU/MA 18/19-07-22 au JE/VE 08/09-12-22 Sauf le(s) : LU/MA 18/19-04-22,LU/MA 06/07-06-22, ME/JE 10/11-08-22,LU/MA 15/16-08-22, MA/ME 01/02-11-22,JE/VE 10/11-11-22 | Gen, V1,V2, 2V/2, 05:02, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021246_11,CHA16_0011819_73,CHA22_0022928_11,CHA21_0022003_23 | NON | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0
| Yes | FEN22_Menton-Vintimille_003 | Menton-00 | Vintimille-WI | 00:41 | 05:20 | 00:41 | 05:20 | Jours d'application : ME,JE,VE,SA Périodes : Et le(s) : SA 02-07-22 SA 09-07-22 SA 16-07-22 SA 23-07-22 SA 30-07-22 SA 06-08-22 SA 13-08-22 SA 20-08-22 SA 27-08-22 SA 03-09-22 et SA 10-09-22 | Gen, V1,V2, 2V/2, 04:39, Nuit non passe-minuit, ME,JE,VE,SA | CHA21_0021246_11,CHA16_0011819_73 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Yes | FEN22_Menton-Vintimille_004 | Menton-00 | Vintimille-WI | 00:10 | 05:20 | 00:10 | 05:20 | Jours d'application : ME,JE,VE,SA Périodes : Et le(s) : SA 09-04-22 SA 16-04-22 SA 23-04-22 SA 30-04-22 SA 07-05-22 SA 14-05-22 SA 21-05-22 SA 28-05-22 SA 04-06-22 SA 11-06-22 SA 18-06-22 SA 25-06-22 SA 17-09-22 SA 24-09-22 SA 01-10-22 SA 08-10-22 SA 15-10-22 SA 22-10-22 SA 29-10-22 SA 05-11-22 SA 12-11-22 SA 19-11-22 SA 26-11-22 SA 03-12-22 et SA 10-12-22 | Gen, V2, 1V/2, 05:10, Nuit non passe-minuit, ME,JE,VE,SA | CHA21_0021246_11,CHA16_0011819_73,CHA22_0022928_11,CHA21_0022003_23 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Yes | FEN22_Menton-Vintimille_005 | Menton-00 | Vintimille-WI | 00:32 | 05:42 | 00:32 | 05:42 | Jours d'application : MA,ME,JE,VE,SA Périodes : Et le(s) : SA 18-12-21 et SA 08-01-22 et SA 15-01-22 et SA 22-01-22 et SA 29-01-22 et SA 05-02-22 et SA 12-02-22 et SA 19-02-22 et SA 26-02-22 et SA 05-03-22 et SA 12-03-22 et SA 19-03-22 et SA 26-03-22 et SA 02-04-22 et SA 09-04-22 et SA 16-04-22 et SA 23-04-22 et SA 30-04-22 et SA 07-05-22 et SA 14-05-22 et SA 21-05-22 et SA 28-05-22 et SA 04-06-22 et SA 11-06-22 et SA 18-06-22 et SA 25-06-22 et SA 02-07-22 et SA 09-07-22 et SA 16-07-22 et SA 23-07-22 et SA 30-07-22 et SA 13-08-22 et SA 20-08-22 et SA 27-08-22 et SA 03-09-22 et SA 10-09-22 et SA 17-09-22 et SA 24-09-22 et SA 01-10-22 et SA 08-10-22 et SA 15-10-22 et SA 22-10-22 et SA 29-10-22 et SA 05-11-22 et SA 12-11-22 et SA 19-11-22 et SA 26-11-22 et SA 03-12-22 et SA 10-12-22 | Gen, V1, 1V/2, 05:10, Nuit non passe-minuit, ME,JE,VE,SA | CHA21_0021246_11,CHA16_0011819_73,CHA22_0022928_11,CHA21_0022003_23 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Yes | FEN22_Menton-Vintimille_006 | Menton-00 | Vintimille-WI | 12:19 | 13:19 | 12:35 | 13:35 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au ME 25-05-22 et du LU 30-05-22 au VE 09-12-22 Sauf le(s) : LU 18-04-22,LU 06-06-22,JE 14-07-22, LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, V1, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_73 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
| Yes | FEN22_Menton-Vintimille_007 | Menton-00 | Vintimille-WI | 09:43 | 10:43 | 09:27 | 10:27 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 13-12-21 au VE 08-04-22 et du MA 19-04-22 au VE 09-12-22 Sauf le(s) : JE 26-05-22,LU 06-06-22,JE 14-07-22, LU 15-08-22,MA 01-11-22,VE 11-11-22 | Sur, V2, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_73 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
SNCF RESEAU - WORKS TT2023 - MARSEILLE-VENTIMIGLIA
| =Total closure >12 hrs | [11 empty] | 2022 | [20 empty] | 2023
| = border point Ventimiglia | [11 empty] | DEC | [20 empty] | JAN | [30 empty] | FEV | [27 empty] | MAR | [30 empty] | AVR | [29 empty] | MAI | [30 empty] | JUN | [29 empty] | JUL | [30 empty] | AOU | [30 empty] | SEP | [29 empty] | OCT | [30 empty] | NOV | [29 empty] | DEC
Total closure >12 hrs ? | Border point ? | Identifiant Ressource | Localisation : Starting point | Localisation : Ending point | Start Time Starting point | End Time Starting point | Start Time Ending point | End Time Ending point | Days of activation (night works are identified by : Day1 / Day2) Period of activation | Type of works | Worksites | Weekend | 49 | 50 | [6 empty] | 51 | [6 empty] | 52 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40 | [6 empty] | 41 | [6 empty] | 42 | [6 empty] | 43 | [6 empty] | 44 | [6 empty] | 45 | [6 empty] | 46 | [6 empty] | 47 | [6 empty] | 48 | [6 empty] | 49
|  | CAP23_Marseille_029 | - | Marseille-Blancarde-AB | 22:25 | 06:25 J+1 | 22:25 | 06:25 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 25/26-11-23 | Cap, 3,5,A,GCIRC,MV1,MV2,V1,V1,V1,V2,V2,V2, 08:00, Passe-minuit, SA/DI | CHA21_0021170_41 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Marseille_030 | - | Marseille-Blancarde-AB | 22:25 | 06:25 J+1 | 22:25 | 06:25 J+1 | Jours d'application : VE/SA Périodes : Et le(s) : VE/SA 01/02-12-23 | Cap, 3,5,A,GCIRC,MV1,MV2,V1,V1,V1,V2,V2,V2, 08:00, Passe-minuit, VE/SA | CHA21_0021170_41 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Marseille_031 | - | Marseille-Blancarde-AB | 00:40 | 04:40 | 00:40 | 04:40 | Jours d'application : MA,ME,JE,VE,SA Périodes : du MA 05-09-23 au SA 07-10-23 | Cap, 3,5,A,GCIRC,V1,V2, 04:00, Nuit non passe-minuit, MA,ME,JE,VE,SA | CHA23_0024550_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Marseille_032 | - | Marseille-St-Charles-BT | 21:00 | 05:00 J+1 | 21:00 | 05:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 09/10-10-23 au VE/SA 27/28-10-23 et du LU/MA 20/21-11-23 au VE/SA 24/25-11-23 | Cap, V2, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA23_0024550_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | CAP23_Marseille_033 | - | Marseille-St-Charles-EG | 05:00 | 05:00 J+4 | 05:00 | 05:00 J+4 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du MA 17-10-23 au SA 21-10-23 | Cap, V2, 96:00, Continu, MA,ME,JE,VE,SA | CHA23_0024550_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Marseille_034 | - | Marseille-St-Charles-RE | 20:30 | 04:30 J+1 | 20:30 | 04:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 30/31-10-23 au ME/JE 01/02-11-23 Sauf le(s) : MA/ME 31/01-11-23 | Cap, 3,5,A,GCIRC,V1,V2, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA23_0024550_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | CAP23_Marseille_035 | - | Marseille-Blancarde-AB | 10:00 | 13:00 J+2 | 10:00 | 13:00 J+2 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 03-11-23 au DI 05-11-23 | Cap, 3,5,A,GCIRC,V1,V2, 51:00, Continu, VE,SA,DI | CHA23_0024550_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | CAP23_Marseille_036 | - | Marseille-Blancarde-AB | 23:50 | 04:50 J+3 | 23:50 | 04:50 J+3 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 10-11-23 au LU 13-11-23 | Cap, 3,5,A,GCIRC,V1,V2, 53:00, Continu, LU,VE,SA,DI | CHA23_0024550_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Marseille_037 | - | Marseille-St-Charles-BT | 22:00 | 04:30 J+1 | 22:00 | 04:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 06/07-11-23 au JE/VE 09/10-11-23 | Cap, V1,V1, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA23_0024550_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Marseille_038 | - | Marseille-St-Charles-BT | 22:00 | 04:30 J+1 | 22:00 | 04:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-11-23 au JE/VE 23/24-11-23 | Cap, A,GCIRC,V1,V2, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA23_0024550_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Marseille_039 | - | Marseille-Blancarde-AB | 20:30 | 04:30 J+1 | 20:30 | 04:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 27/28-11-23 au VE/SA 08/09-12-23 | Cap, A,GCIRC,V1,V2, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA23_0024550_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_Marseille_040 | - | Marseille-St-Charles-RE | 23:40 | 04:40 J+1 | 23:40 | 04:40 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 30/31-01-23 au JE/VE 02/03-02-23 | Cap, 3,5,A,GCIRC,V1,V2, 05:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021933_124 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Marseille_041 | - | Marseille-Blancarde-AB | 23:40 | 04:40 J+1 | 23:40 | 04:40 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 06/07-02-23 au JE/VE 09/10-02-23 | Cap, 3,5,A,GCIRC,MV1,MV2,V1,V2, 05:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021933_124 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Marseille_042 | - | Marseille-Blancarde-AB | 23:40 | 04:40 J+1 | 23:40 | 04:40 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-02-23 au JE/VE 16/17-02-23 | Cap, 3,5,A,GCIRC,MV1,MV2,V1,V2, 05:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021933_124 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Marseille_044 | - | Marseille-Blancarde-OR | 23:00 | 06:30 J+1 | 23:00 | 06:30 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 30/31-01-23 au VE/SA 03/04-03-23 et du LU/MA 20/21-03-23 au VE/SA 31/01-04-23 | Cap, UNIQUE, 07:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA23_0025706_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | CAP23_Marseille_045 | - | Marseille-Blancarde-OR | 23:30 | 23:30 J+4 | 23:30 | 23:30 J+4 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du ME 08-03-23 au DI 12-03-23 et du ME 15-03-23 au DI 19-03-23 | Cap, UNIQUE, 96:00, Continu, ME,JE,VE,SA,DI | CHA23_0025706_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Marseille_046 | - | Marseille-Blancarde-OR | 07:30 | 15:00 | 07:30 | 15:00 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 30-01-23 au VE 03-03-23 et du LU 20-03-23 au VE 31-03-23 | Cap, UNIQUE, 07:30, Jour, LU,MA,ME,JE,VE | CHA23_0025706_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | CAP23_Marseille_048 | - | Marseille-Blancarde-AB | 13:33 | 07:00 J+1 | 13:33 | 07:00 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 18/19-11-23 | Cap, 3,5,A,GCIRC,V1,V2, 17:27, Passe-minuit, SA/DI | CHA23_0024550_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Marseille-Aubagne_009 | Marseille-Blancarde-BV | Aubagne-00 | 22:25 | 06:25 J+1 | 22:25 | 06:25 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 25/26-11-23 | Def, V1,V2,VMV3, 3V/3, 08:00, Passe-minuit, SA/DI | CHA21_0021170_42 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Marseille-Aubagne_010 | Marseille-Blancarde-BV | Aubagne-00 | 22:25 | 06:25 J+1 | 22:25 | 06:25 J+1 | Jours d'application : VE/SA Périodes : Et le(s) : VE/SA 01/02-12-23 | Def, V1,V2,VMV3, 3V/3, 08:00, Passe-minuit, VE/SA | CHA21_0021170_42 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Marseille-Aubagne_011 | Marseille-Blancarde-J1 | Aubagne-00 | 22:55 | 05:30 J+1 | 23:29 | 04:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : Et le(s) : ME/JE 08/09-11-23 | Def, V2, , 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA20_0019010_37 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Marseille-Aubagne_012 | Marseille-Blancarde-BV | Aubagne-00 | 23:19 | 05:35 J+1 | 23:19 | 05:35 J+1 | Jours d'application : SA/DI,DI/LU Périodes : du SA/DI 21/22-01-23 au DI/LU 14/15-05-23 du SA/DI 09/10-09-23 au DI/LU 05/06-11-23 et du SA/DI 25/26-11-23 au DI/LU 03/04-12-23 | Def, V1,V2,VMV3, 3V/3, 06:16, Passe-minuit, SA/DI,DI/LU | CHA21_0021966_34 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Marseille-Aubagne_002 | Marseille-Blancarde-BV | Aubagne-00 | 23:19 | 05:35 J+1 | 23:19 | 05:35 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 12/13-12-22 au VE/SA 08/09-12-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,JE/VE 18/19-05-23,LU/MA 29/30-05-23, VE/SA 14/15-07-23,MA/ME 15/16-08-23,ME/JE 01/02-11-23 | Gen, V1,V2,VMV3, 3V/3, 06:16, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_76, CHA21_0022003_32, CHA21_0021966_34 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0
|  | FEN23_Marseille-Aubagne_003 | Marseille-Blancarde-BV | Aubagne-00 | 08:38 | 09:38 | 08:45 | 09:45 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V1, 1V/3, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_76 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_Marseille-Aubagne_004 | Marseille-Blancarde-J1 | Aubagne-00 | 11:20 | 12:20 | 11:12 | 12:12 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V2, 1V/3, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_76 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_Marseille-Aubagne_005 | Marseille-Blancarde-BV | Aubagne-00 | 23:05 | 05:35 J+1 | 23:05 | 05:35 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 12/13-12-22 au VE/SA 30/01-07-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,JE/VE 18/19-05-23,LU/MA 29/30-05-23 | Gen, V1, 2V/3, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_76 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Marseille-Aubagne_006 | Marseille-Blancarde-J1 | Aubagne-00 | 23:05 | 05:35 J+1 | 23:05 | 05:35 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 12/13-12-22 au VE/SA 30/01-07-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,JE/VE 18/19-05-23,LU/MA 29/30-05-23 | Gen, V2, 2V/3, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_76 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Marseille-Aubagne_007 | Marseille-Blancarde-J1 | Aubagne-00 | 23:05 | 05:35 J+1 | 23:05 | 05:35 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 03/04-07-23 au VE/SA 08/09-12-23 Sauf le(s) : VE/SA 14/15-07-23,MA/ME 15/16-08-23, ME/JE 01/02-11-23 | Gen, VMV3, 2V/3, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_76 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_Marseille-Aubagne_008 | Marseille-Blancarde-J1 | Aubagne-00 | 11:10 | 12:10 | 11:10 | 12:10 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, VMV3, 1V/3, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_76 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_Aubagne_012 | Aubagne-00 | ITE Camp-Militaire-Carpiagne-00 | 22:58 | 05:45 J+1 | 22:58 | 05:45 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 12/13-12-22 au JE/VE 15/16-12-22 et du LU/MA 02/03-01-23 au JE/VE 20/21-04-23 Sauf le(s) : LU/MA 10/11-04-23 | Cap, V1,V1,V2,V2, 06:47, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA23_0024696_01 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Aubagne_013 | Aubagne-00 | ITE Camp-Militaire-Carpiagne-00 | 23:08 | 05:45 J+1 | 23:08 | 05:45 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 08/09-01-23 au DI/LU 16/17-04-23 Et le(s) : DI/LU 11/12-12-22 | Cap, V1,V2, 06:37, Passe-minuit, DI/LU | CHA23_0024696_01 | OUI | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Aubagne_014 | Aubagne-00 | ITE Camp-Militaire-Carpiagne-00 | 23:30 | 05:30 J+1 | 23:59 | 04:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 23/24-04-23 au JE/VE 04/05-05-23 Sauf le(s) : LU/MA 01/02-05-23 | Cap, V1,V2, 05:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024696_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Aubagne_017 | Aubagne-J3 | ITE Camp-Militaire-Carpiagne-00 | 22:25 | 06:25 J+1 | 22:25 | 06:25 J+1 | Jours d'application : SA/DI Périodes : Et le(s) : SA/DI 25/26-11-23 | Cap, A,D,E,V1,V2,VMV3, 08:00, Passe-minuit, SA/DI | CHA21_0021170_43 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | CAP23_Aubagne_018 | Aubagne-J3 | ITE Camp-Militaire-Carpiagne-00 | 22:25 | 18:25 J+1 | 22:25 | 18:25 J+1 | Jours d'application : VE/SA Périodes : Et le(s) : VE/SA 01/02-12-23 | Cap, A,D,E,V1,V2,VMV3, 20:00, Passe-minuit, VE/SA | CHA21_0021170_43 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Aubagne_019 | Aubagne-J3 | ITE Camp-Militaire-Carpiagne-00 | 22:55 | 05:29 J+1 | 23:29 | 04:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : Et le(s) : ME/JE 08/09-11-23 | Cap, V2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA20_0019010_38 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aubagne-Toulon_014 | Aubagne-00 | St-Antoine (M) Poste 1-00 | 22:58 | 05:45 J+1 | 22:58 | 05:45 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 12/13-12-22 au JE/VE 15/16-12-22 et du LU/MA 02/03-01-23 au JE/VE 20/21-04-23 Sauf le(s) : LU/MA 10/11-04-23 | Def, V1,V1,V2,V2, 2V/2, 06:47, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA23_0024696_02 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aubagne-Toulon_015 | Aubagne-00 | Cassis-BV | 23:08 | 05:45 J+1 | 23:08 | 05:45 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 08/09-01-23 au DI/LU 16/17-04-23 Et le(s) : DI/LU 11/12-12-22 | Def, V1,V1,V2,V2, 2V/2, 06:37, Passe-minuit, DI/LU | CHA23_0024696_02 | NON | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aubagne-Toulon_016 | St-Antoine (M) Poste 1-00 | La Seyne-Tamaris-sur-Mer-PA | 22:25 | 05:25 J+1 | 22:25 | 05:25 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 29/30-10-23 au JE/VE 07/08-12-23 Sauf le(s) : ME/JE 01/02-11-23 | Def, V1,V2, 2V/2, 07:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024515_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0
|  | DEF23_Aubagne-Toulon_017 | St-Antoine (M) Poste 1-00 | La Seyne-Tamaris-sur-Mer-P1 | 22:25 | 05:25 J+1 | 22:25 | 05:25 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 10/11-09-23 au JE/VE 26/27-10-23 | Def, V1,V2, 2V/2, 07:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0025610_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aubagne-Toulon_018 | Aubagne-00 | St-Antoine (M) Poste 1-00 | 23:30 | 05:30 J+1 | 23:59 | 04:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 23/24-04-23 au JE/VE 04/05-05-23 Sauf le(s) : LU/MA 01/02-05-23 | Def, V1,V1,V2,V2, 2V/2, 05:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024696_02 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aubagne-Toulon_019 | ITE Camp-Militaire-Carpiagne-00 | St-Cyr-les-Lècques-La Cadière-V4 | 22:58 | 05:45 J+1 | 22:58 | 05:45 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 02/03-01-23 au JE/VE 20/21-04-23 Sauf le(s) : LU/MA 10/11-04-23 | Def, V1,V2, 2V/2, 06:47, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA22_0023002_05 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aubagne-Toulon_020 | ITE Camp-Militaire-Carpiagne-00 | St-Cyr-les-Lècques-La Cadière-V4 | 23:08 | 05:45 J+1 | 23:08 | 05:45 J+1 | Jours d'application : DI/LU Périodes : du DI/LU 08/09-01-23 au DI/LU 23/24-04-23 | Def, V1,V2, 2V/2, 06:37, Passe-minuit, DI/LU | CHA22_0023002_05 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aubagne-Toulon_021 | ITE Camp-Militaire-Carpiagne-00 | St-Cyr-les-Lècques-La Cadière-V4 | 23:30 | 05:30 J+1 | 23:59 | 04:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du LU/MA 12/13-12-22 au DI/LU 18/19-12-22 et du LU/MA 24/25-04-23 au DI/LU 14/15-05-23 | Def, V1,V2, 2V/2, 05:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0023002_05 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aubagne-Toulon_022 | Aubagne-00 | Toulon-BV | 22:55 | 05:30 J+1 | 23:29 | 04:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du MA/ME 07/08-11-23 au ME/JE 08/09-11-23 | Def, V2, , 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA20_0019010_39 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aubagne-Toulon_023 | Aubagne-00 | Toulon-BV | 22:55 | 05:30 J+1 | 23:29 | 04:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du JE/VE 09/10-11-23 au LU/MA 13/14-11-23 Sauf le(s) : VE/SA 10/11-11-23 | Def, V1, , 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA20_0019010_39 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Aubagne-Toulon_024 | Aubagne-00 | Toulon-BV | 23:30 | 05:30 J+1 | 23:59 | 04:55 J+1 | Jours d'application : SA/DI,DI/LU Périodes : du SA/DI 21/22-01-23 au DI/LU 14/15-05-23 du SA/DI 09/10-09-23 au DI/LU 05/06-11-23 et du SA/DI 18/19-11-23 au DI/LU 03/04-12-23 | Def, V1,V2, 2V/2, 05:28, Passe-minuit, SA/DI,DI/LU | CHA21_0021966_36 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Aubagne-Toulon_006 | Aubagne-00 | Toulon-BV | 08:48 | 10:10 | 09:32 | 10:32 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V1, 1V/2, 01:11, Jour, LU,MA,ME,JE,VE | CHA16_0011819_78 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_Aubagne-Toulon_007 | Aubagne-00 | Toulon-BV | 11:10 | 12:10 | 10:26 | 11:26 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V2, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_78 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_Aubagne-Toulon_008 | Aubagne-00 | Toulon-BV | 23:30 | 05:30 J+1 | 23:59 | 04:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 12/13-12-22 au VE/SA 08/09-12-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,JE/VE 18/19-05-23,LU/MA 29/30-05-23, VE/SA 14/15-07-23,MA/ME 15/16-08-23,ME/JE 01/02-11-23 | Gen, V1,V2, 2V/2, 05:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_78, CHA21_0021958_37, CHA21_0022003_34, CHA21_0021966_36, CHA20_0019010_39 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 2 | 3 | 3 | 3 | 2 | 0 | 0 | 3 | 3 | 3 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0
|  | FEN23_Aubagne-Toulon_011 | Aubagne-00 | Toulon-BV | 22:55 | 05:15 J+1 | 22:55 | 05:15 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 12/13-12-22 au VE/SA 30/01-07-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,JE/VE 18/19-05-23,LU/MA 29/30-05-23 | Gen, V1, 1V/2, 06:20, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_78 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Aubagne-Toulon_012 | Aubagne-00 | Toulon-BV | 22:55 | 05:15 J+1 | 22:55 | 05:15 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 03/04-07-23 au VE/SA 10/11-11-23 et du JE/VE 16/17-11-23 au VE/SA 08/09-12-23 Sauf le(s) : VE/SA 14/15-07-23,MA/ME 15/16-08-23, ME/JE 01/02-11-23 | Gen, V2, 1V/2, 06:20, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_78 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_Toulon_021 | La Seyne-Tamaris-sur-Mer-P1 | Toulon-V4 | 00:00 | 05:21 | 00:00 | 05:21 | Jours d'application : MA,ME,JE,VE,SA Périodes : du MA 13-06-23 au SA 25-11-23 Sauf le(s) : SA 15-07-23,MA 15-08-23,ME 01-11-23,SA 11-11-23 | Cap, D,E,V1, 05:21, Nuit non passe-minuit, MA,ME,JE,VE,SA | CHA23_0024334_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Toulon_022 | La Seyne-Tamaris-sur-Mer-P1 | Toulon-V4 | 20:45 | 06:00 J+1 | 20:45 | 06:00 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du LU/MA 20/21-02-23 au VE/SA 09/10-06-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,JE/VE 18/19-05-23,LU/MA 29/30-05-23 | Cap, B,V1, 09:15, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA23_0024334_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Toulon_023 | La Seyne-Tamaris-sur-Mer-P1 | La Garde-BV | 01:00 | 03:00 | 01:00 | 03:00 | Jours d'application : MA,ME,VE,SA Périodes : du MA 13-06-23 au SA 25-11-23 Sauf le(s) : VE 14-07-23,MA 15-08-23,ME 01-11-23,SA 11-11-23 | Cap, B,D,M,V1,V2, 02:00, Nuit non passe-minuit, MA,ME,VE,SA | CHA23_0024334_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Toulon_024 | La Seyne-Tamaris-sur-Mer-P1 | La Garde-BV | 01:00 | 03:00 | 01:00 | 03:00 | Jours d'application : MA,ME,VE,SA Périodes : du MA 21-02-23 au SA 10-06-23 | Cap, B,M,V2, 02:00, Nuit non passe-minuit, MA,ME,VE,SA | CHA23_0024334_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Toulon-LesArcs_011 | Puget-Ville-00 | Pignans-00 | 22:40 | 05:08 J+1 | 22:40 | 05:08 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 02/03-01-23 au JE/VE 07/08-12-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,LU/MA 29/30-05-23,MA/ME 15/16-08-23 | Cap, A, 06:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA23_0024189_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | CAP23_Toulon-LesArcs_012 | Puget-Ville-00 | Pignans-00 | 23:30 | 06:04 J+1 | 00:03 J+1 | 05:20 J+1 | Jours d'application : VE/SA Périodes : du VE/SA 06/07-01-23 au VE/SA 08/09-12-23 Sauf le(s) : VE/SA 14/15-07-23 | Cap, A, 05:55, Passe-minuit, VE/SA | CHA23_0024189_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | DEF23_Toulon-LesArcs_022 | Toulon-V4 | Le Muy-00 | 00:03 | 05:10 | 00:03 | 05:10 | Jours d'application : SA,DI Périodes : du DI 22-01-23 au DI 14-05-23 du DI 10-09-23 au DI 05-11-23 du DI 19-11-23 au DI 03-12-23 Sauf le(s) : SA 28-01-23,SA 04-02-23,SA 11-02-23,SA 18-02-23, SA 25-02-23,SA 04-03-23,SA 11-03-23,SA 18-03-23, SA 25-03-23,SA 01-04-23,SA 08-04-23,SA 15-04-23, SA 22-04-23,SA 29-04-23,SA 06-05-23,SA 13-05-23, SA 16-09-23,SA 23-09-23,SA 30-09-23,SA 07-10-23, SA 14-10-23,SA 21-10-23,SA 28-10-23,SA 04-11-23, SA 25-11-23,SA 02-12-23 | Def, V1,V2, , 05:07, Nuit non passe-minuit, SA,DI | CHA21_0021966_38 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Toulon-LesArcs_001 | Toulon-V4 | Le Muy-00 | 22:40 | 05:08 J+1 | 22:40 | 05:08 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 12/13-12-22 au JE/VE 07/08-12-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,JE/VE 18/19-05-23,LU/MA 29/30-05-23, MA/ME 15/16-08-23,ME/JE 01/02-11-23 | Gen, V1,V2, 2V/2, 06:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0025609_01, CHA21_0021293_03, CHA20_0018189_04, CHA23_0024189_03, CHA19_0015533_05, CHA16_0011819_80, CHA21_0022003_36, CHA21_0021966_38, CHA20_0019010_41, CHA21_0021958_39 | NON | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 5 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 7 | 7 | 0 | 7 | 0 | 0 | 0 | 8 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 8 | 8 | 7 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 0
|  | FEN23_Toulon-LesArcs_002 | Toulon-V4 | Le Muy-00 | 23:30 | 06:04 J+1 | 00:03 J+1 | 05:39 J+1 | Jours d'application : MA/ME,ME/JE,JE/VE,VE/SA Périodes : du VE/SA 12/13-05-23 au VE/SA 19/20-05-23 Et le(s) : VE/SA 16/17-12-22 VE/SA 23/24-12-22 VE/SA 30/31-12-22 VE/SA 06/07-01-23 VE/SA 13/14-01-23 VE/SA 20/21-01-23 VE/SA 27/28-01-23 VE/SA 03/04-02-23 VE/SA 10/11-02-23 VE/SA 17/18-02-23 VE/SA 24/25-02-23 VE/SA 03/04-03-23 VE/SA 10/11-03-23 VE/SA 17/18-03-23 VE/SA 24/25-03-23 VE/SA 31/01-04-23 VE/SA 07/08-04-23 VE/SA 14/15-04-23 VE/SA 21/22-04-23 VE/SA 28/29-04-23 VE/SA 05/06-05-23 VE/SA 26/27-05-23 VE/SA 02/03-06-23 VE/SA 09/10-06-23 VE/SA 16/17-06-23 VE/SA 23/24-06-23 VE/SA 30/01-07-23 VE/SA 07/08-07-23 JE/VE 13/14-07-23 VE/SA 21/22-07-23 VE/SA 28/29-07-23 VE/SA 04/05-08-23 VE/SA 11/12-08-23 VE/SA 18/19-08-23 VE/SA 25/26-08-23 VE/SA 01/02-09-23 VE/SA 08/09-09-23 VE/SA 15/16-09-23 VE/SA 22/23-09-23 VE/SA 29/30-09-23 VE/SA 06/07-10-23 VE/SA 13/14-10-23 VE/SA 20/21-10-23 VE/SA 27/28-10-23 VE/SA 03/04-11-23 VE/SA 10/11-11-23 VE/SA 17/18-11-23 VE/SA 24/25-11-23 VE/SA 01/02-12-23 et VE/SA 08/09-12-23 Sauf le(s) : MA/ME 16/17-05-23,JE/VE 18/19-05-23 | Gen, V1,V2, 2V/2, 06:05, Passe-minuit, MA/ME,ME/JE,JE/VE,VE/SA | CHA21_0025609_01, CHA20_0018189_04, CHA21_0021293_03, CHA23_0024189_03, CHA19_0015533_05, CHA16_0011819_80, CHA21_0021958_39, CHA21_0022003_36, CHA21_0021966_38, CHA21_0021987_29 | NON | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 7.25 | 0 | 0 | 0 | 0 | 0 | 0 | 8.25 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0
|  | FEN23_Toulon-LesArcs_003 | Toulon-V4 | La Farlède-00 | 09:42 | 10:42 | 09:50 | 10:50 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V1, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_80 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_Toulon-LesArcs_004 | Toulon-V4 | La Pauline-Hyères-GZ | 10:24 | 11:24 | 10:13 | 11:13 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V2, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_80 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_Toulon-LesArcs_005 | La Pauline-Hyères-GZ | Le Muy-00 | 09:50 | 10:50 | 10:15 | 11:15 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V1, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_80 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_Toulon-LesArcs_007 | La Pauline-Hyères-BF | Les Arcs-Draguignan-00 | 10:10 | 11:10 | 09:37 | 10:37 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V2, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_80 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_LesArcs-StRaphael_001 | St-Raphaël-Valescure-P1 | Boulouris-sur-Mer-00 | 00:03 | 06:15 | 00:20 | 06:15 | Jours d'application : SA Périodes : du SA 25-02-23 au SA 29-04-23 | Cap, A, 06:03, Nuit non passe-minuit, SA | CHA23_0024871_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_LesArcs-StRaphael_002 | St-Raphaël-Valescure-P1 | Boulouris-sur-Mer-00 | 22:44 | 05:12 J+1 | 22:44 | 05:12 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 20/21-02-23 au JE/VE 27/28-04-23 Sauf le(s) : LU/MA 10/11-04-23 | Cap, A, 06:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA23_0024871_03 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_LesArcs-StRaphael_019 | Les Arcs-Draguignan-V3 | Boulouris-sur-Mer-00 | 00:20 | 05:30 | 00:20 | 05:30 | Jours d'application : SA,DI Périodes : du SA 21-01-23 au DI 14-05-23 du SA 09-09-23 au DI 05-11-23 et du SA 18-11-23 au DI 03-12-23 | Def, V1,V2, 2V/2, 05:10, Nuit non passe-minuit, SA,DI | CHA21_0021966_39 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_LesArcs-StRaphael_001 | Les Arcs-Draguignan-V3 | Boulouris-sur-Mer-00 | 22:44 | 05:12 J+1 | 22:44 | 05:12 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 12/13-12-22 au MA/ME 16/17-05-23 et du LU/MA 22/23-05-23 au JE/VE 07/08-12-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,LU/MA 29/30-05-23,JE/VE 13/14-07-23, MA/ME 15/16-08-23,ME/JE 01/02-11-23 | Gen, V1,V2, 2V/2, 06:28, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA23_0024871_03, CHA16_0011819_81, CHA21_0022003_37, CHA20_0019010_43 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
|  | FEN23_LesArcs-StRaphael_002 | Les Arcs-Draguignan-V3 | Boulouris-sur-Mer-00 | 00:03 | 06:15 | 00:20 | 06:15 | Jours d'application : ME,JE,VE,SA Périodes : du SA 13-05-23 au SA 20-05-23 et du VE 14-07-23 au SA 15-07-23 Et le(s) : SA 17-12-22 SA 24-12-22 SA 31-12-22 SA 07-01-23 SA 14-01-23 SA 21-01-23 SA 28-01-23 SA 04-02-23 SA 11-02-23 SA 18-02-23 SA 25-02-23 SA 04-03-23 SA 11-03-23 SA 18-03-23 SA 25-03-23 SA 01-04-23 SA 08-04-23 SA 15-04-23 SA 22-04-23 SA 29-04-23 SA 06-05-23 SA 27-05-23 SA 03-06-23 SA 10-06-23 SA 17-06-23 SA 24-06-23 SA 01-07-23 SA 08-07-23 SA 22-07-23 SA 29-07-23 SA 05-08-23 SA 12-08-23 SA 19-08-23 SA 26-08-23 SA 02-09-23 SA 09-09-23 SA 16-09-23 SA 23-09-23 SA 30-09-23 SA 07-10-23 SA 14-10-23 SA 21-10-23 SA 28-10-23 SA 04-11-23 SA 11-11-23 SA 18-11-23 SA 25-11-23 SA 02-12-23 et SA 09-12-23 Sauf le(s) : ME 17-05-23,VE 19-05-23 | Gen, V1,V2, 2V/2, 06:03, Nuit non passe-minuit, ME,JE,VE,SA | CHA16_0011819_81, CHA23_0024871_03, CHA21_0022003_37 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | FEN23_LesArcs-StRaphael_003 | Les Arcs-Draguignan-00 | Boulouris-sur-Mer-00 | 10:02 | 11:02 | 10:16 | 11:16 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V1, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_81 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_LesArcs-StRaphael_004 | Les Arcs-Draguignan-V3 | Boulouris-sur-Mer-00 | 13:33 | 14:33 | 13:16 | 14:16 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V2, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_81 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_StRaphael-Nice_001 | Cannes-Marchandises-PO | Cagnes-sur-Mer-BV | 22:35 | 05:40 J+1 | 22:35 | 05:40 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,DI/LU Périodes : du DI/LU 12/13-03-23 au ME/JE 24/25-05-23 et du DI/LU 22/23-10-23 au ME/JE 29/30-11-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,ME/JE 01/02-11-23 | Cap, 3,4,A, 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,DI/LU | CHA22_0022928_23, CHA19_0016215_27 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | CAP23_StRaphael-Nice_002 | Antibes-00 | Cagnes-sur-Mer-BV | 23:10 | 23:10 J+2 | 23:10 | 23:10 J+2 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 10-11-23 au DI 12-11-23 | Cap, 3,4, 48:00, Continu, VE,SA,DI | CHA22_0022928_23, CHA19_0016215_27 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_StRaphael-Nice_003 | Cannes-Marchandises-PO | Cagnes-sur-Mer-BV | 23:10 | 05:40 J+1 | 23:10 | 05:40 J+1 | Jours d'application : JE/VE Périodes : du JE/VE 16/17-03-23 au JE/VE 25/26-05-23 et du JE/VE 26/27-10-23 au JE/VE 30/01-12-23 Sauf le(s) : JE/VE 18/19-05-23 | Cap, 3,4,A, 06:30, Passe-minuit, JE/VE | CHA22_0022928_23, CHA19_0016215_27 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StRaphael-Nice_006 | Mandelieu-la-Napoule-00 | Nice-Ville-00 | 22:35 | 05:40 J+1 | 22:35 | 05:40 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,DI/LU Périodes : du DI/LU 12/13-03-23 au ME/JE 24/25-05-23 et du DI/LU 22/23-10-23 au ME/JE 29/30-11-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23,LU/MA 08/09-05-23,ME/JE 01/02-11-23 | Def, ANC,V1,V2, 3V/3, 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,DI/LU | CHA22_0022928_23, CHA19_0016215_27 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_StRaphael-Nice_018 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 06:00 | 18:00 J+1 | 06:00 | 18:00 J+1 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du SA 11-11-23 au DI 12-11-23 | Def, V1,V2, 2V/2, 36:00, Continu, SA,DI | CHA21_0021246_14 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_StRaphael-Nice_019 | Juan-les-Pins-00 | Cros-de-Cagnes-00 | 23:10 | 23:10 J+2 | 23:10 | 23:10 J+2 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 10-11-23 au DI 12-11-23 | Def, ANC,V1,V2, 3V/3, 48:00, Continu, VE,SA,DI | CHA22_0022928_23, CHA19_0016215_27 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StRaphael-Nice_020 | Villeneuve-Loubet-Plage-00 | Cros-de-Cagnes-00 | 22:35 | 05:40 J+1 | 22:35 | 05:40 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,DI/LU Périodes : du DI/LU 22/23-10-23 au ME/JE 29/30-11-23 Sauf le(s) : ME/JE 01/02-11-23 | Def, ANC,V1,V2, 3V/3, 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,DI/LU | CHA22_0022928_23, CHA19_0016215_27 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StRaphael-Nice_022 | Juan-les-Pins-00 | Nice-Ville-00 | 22:35 | 05:40 J+1 | 22:35 | 05:40 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,DI/LU Périodes : du DI/LU 12/13-03-23 au ME/JE 24/25-05-23 et du DI/LU 29/30-10-23 au ME/JE 29/30-11-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,ME/JE 01/02-11-23 | Def, ANC,V1,V2, 3V/3, 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,DI/LU | CHA22_0022928_23 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StRaphael-Nice_023 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 23:07 | 05:08 J+1 | 23:07 | 05:08 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 13/14-03-23 au JE/VE 30/31-03-23 et du LU/MA 02/03-10-23 au JE/VE 19/20-10-23 | Def, V1,V2, 2V/2, 06:01, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0022001_37 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StRaphael-Nice_024 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 00:40 | 05:53 | 01:17 | 05:48 | Jours d'application : SA Périodes : du SA 18-03-23 au SA 01-04-23 et du SA 07-10-23 au SA 21-10-23 | Def, V1,V2, 2V/2, 04:52, Nuit non passe-minuit, SA | CHA21_0022001_37 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_StRaphael-Nice_025 | Cagnes-sur-Mer-BV | Nice-Ville-00 | 23:10 | 23:10 J+2 | 23:10 | 23:10 J+2 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 10-11-23 au DI 12-11-23 | Def, V1,V2, 2V/2, 48:00, Continu, VE,SA,DI | CHA19_0016215_27, CHA22_0022928_23 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StRaphael-Nice_026 | Anthéor-Cap-Roux-VA | Cannes-Marchandises-P1 | 23:07 | 05:08 J+1 | 23:07 | 05:08 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : Et le(s) : VE/SA 03/04-11-23 | Def, V2, , 06:01, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA20_0019010_44 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StRaphael-Nice_027 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 01:17 | 05:05 | 01:17 | 05:05 | Jours d'application : SA,DI Périodes : du SA 21-01-23 au DI 14-05-23 du SA 09-09-23 au DI 05-11-23 et du SA 18-11-23 au DI 03-12-23 | Def, V1,V2, 2V/2, 03:48, Nuit non passe-minuit, SA,DI | CHA21_0021966_40 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StRaphael-Nice_028 | Mandelieu-la-Napoule-00 | Nice-Ville-00 | 23:10 | 05:40 J+1 | 23:10 | 05:40 J+1 | Jours d'application : JE/VE Périodes : du JE/VE 16/17-03-23 au JE/VE 25/26-05-23 et du JE/VE 26/27-10-23 au JE/VE 30/01-12-23 Sauf le(s) : JE/VE 18/19-05-23 | Def, ANC,V1,V2, 3V/3, 06:30, Passe-minuit, JE/VE | CHA19_0016215_27, CHA22_0022928_23 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_StRaphael-Nice_029 | Juan-les-Pins-00 | Nice-Ville-00 | 23:10 | 05:40 J+1 | 23:10 | 05:40 J+1 | Jours d'application : JE/VE Périodes : du JE/VE 16/17-03-23 au JE/VE 25/26-05-23 et du JE/VE 26/27-10-23 au JE/VE 30/01-12-23 Sauf le(s) : JE/VE 18/19-05-23 | Def, ANC,V1,V2, 3V/3, 06:30, Passe-minuit, JE/VE | CHA19_0016215_27, CHA22_0022928_23 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_StRaphael-Nice_001 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 23:07 | 05:08 J+1 | 23:07 | 05:08 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 12/13-12-22 au MA/ME 16/17-05-23 et du LU/MA 22/23-05-23 au JE/VE 07/08-12-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,LU/MA 29/30-05-23,JE/VE 13/14-07-23, MA/ME 15/16-08-23 | Gen, ANC,V1,V2, 3V/3, 06:01, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0021246_14, CHA16_0011819_82, CHA23_0024871_02, CHA21_0022003_38, CHA23_0025679_01, CHA23_0024540_01, CHA20_0019010_44 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 3 | 2 | 5 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0
|  | FEN23_StRaphael-Nice_005 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 10:09 | 11:09 | 11:21 | 12:21 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V1, 1V/3, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_82 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_StRaphael-Nice_006 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 13:23 | 14:23 | 12:17 | 13:17 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V2, 1V/3, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_82 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_StRaphael-Nice_007 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 00:40 | 05:53 | 01:17 | 05:48 | Jours d'application : MA,ME,JE,VE,SA Périodes : du JE 18-05-23 au SA 20-05-23 et du VE 14-07-23 au SA 15-07-23 Et le(s) : SA 17-12-22 SA 24-12-22 SA 31-12-22 SA 07-01-23 SA 14-01-23 SA 21-01-23 SA 28-01-23 SA 04-02-23 SA 11-02-23 SA 18-02-23 SA 25-02-23 SA 04-03-23 SA 11-03-23 SA 18-03-23 SA 25-03-23 SA 01-04-23 SA 08-04-23 SA 15-04-23 SA 22-04-23 SA 29-04-23 SA 06-05-23 SA 13-05-23 SA 27-05-23 SA 03-06-23 SA 10-06-23 SA 17-06-23 SA 24-06-23 SA 01-07-23 SA 08-07-23 SA 22-07-23 SA 29-07-23 SA 05-08-23 SA 12-08-23 SA 19-08-23 SA 26-08-23 SA 02-09-23 SA 09-09-23 SA 16-09-23 SA 23-09-23 SA 30-09-23 SA 07-10-23 SA 14-10-23 SA 21-10-23 SA 28-10-23 SA 04-11-23 SA 11-11-23 SA 18-11-23 SA 25-11-23 SA 02-12-23 et SA 09-12-23 Sauf le(s) : VE 19-05-23 | Gen, ANC,V1,V2, 3V/3, 04:52, Nuit non passe-minuit, MA,ME,JE,VE,SA | CHA21_0021246_14, CHA16_0011819_82, CHA23_0024540_01, CHA23_0025679_01, CHA23_0024871_02, CHA21_0022003_38 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3
|  | FEN23_StRaphael-Nice_008 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 23:26 | 05:55 J+1 | 23:26 | 05:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du ME/JE 17/18-05-23 au VE/SA 19/20-05-23 Et le(s) : VE/SA 16/17-12-22 VE/SA 23/24-12-22 VE/SA 30/31-12-22 VE/SA 06/07-01-23 VE/SA 13/14-01-23 VE/SA 20/21-01-23 VE/SA 27/28-01-23 VE/SA 03/04-02-23 VE/SA 10/11-02-23 VE/SA 17/18-02-23 VE/SA 24/25-02-23 VE/SA 03/04-03-23 VE/SA 10/11-03-23 VE/SA 17/18-03-23 VE/SA 24/25-03-23 VE/SA 31/01-04-23 VE/SA 07/08-04-23 VE/SA 14/15-04-23 VE/SA 21/22-04-23 VE/SA 28/29-04-23 VE/SA 05/06-05-23 VE/SA 12/13-05-23 VE/SA 26/27-05-23 VE/SA 02/03-06-23 VE/SA 09/10-06-23 VE/SA 16/17-06-23 VE/SA 23/24-06-23 VE/SA 30/01-07-23 VE/SA 07/08-07-23 JE/VE 13/14-07-23 VE/SA 21/22-07-23 VE/SA 28/29-07-23 VE/SA 04/05-08-23 VE/SA 11/12-08-23 VE/SA 18/19-08-23 VE/SA 25/26-08-23 VE/SA 01/02-09-23 VE/SA 08/09-09-23 VE/SA 15/16-09-23 VE/SA 22/23-09-23 VE/SA 29/30-09-23 VE/SA 06/07-10-23 VE/SA 13/14-10-23 VE/SA 20/21-10-23 VE/SA 27/28-10-23 VE/SA 03/04-11-23 VE/SA 10/11-11-23 VE/SA 17/18-11-23 VE/SA 24/25-11-23 VE/SA 01/02-12-23 et VE/SA 08/09-12-23 Sauf le(s) : JE/VE 18/19-05-23 | Gen, V1, 1V/2, 06:29, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_82 | NON | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | FEN23_StRaphael-Nice_009 | St-Raphaël-Valescure-BV | Nice-Ville-00 | 23:26 | 05:55 J+1 | 23:26 | 05:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du ME/JE 17/18-05-23 au VE/SA 19/20-05-23 Et le(s) : VE/SA 16/17-12-22 VE/SA 23/24-12-22 VE/SA 30/31-12-22 VE/SA 06/07-01-23 VE/SA 13/14-01-23 VE/SA 20/21-01-23 VE/SA 27/28-01-23 VE/SA 03/04-02-23 VE/SA 10/11-02-23 VE/SA 17/18-02-23 VE/SA 24/25-02-23 VE/SA 03/04-03-23 VE/SA 10/11-03-23 VE/SA 17/18-03-23 VE/SA 24/25-03-23 VE/SA 31/01-04-23 VE/SA 07/08-04-23 VE/SA 14/15-04-23 VE/SA 21/22-04-23 VE/SA 28/29-04-23 VE/SA 05/06-05-23 VE/SA 12/13-05-23 VE/SA 26/27-05-23 VE/SA 02/03-06-23 VE/SA 09/10-06-23 VE/SA 16/17-06-23 VE/SA 23/24-06-23 VE/SA 30/01-07-23 VE/SA 07/08-07-23 JE/VE 13/14-07-23 VE/SA 21/22-07-23 VE/SA 28/29-07-23 VE/SA 04/05-08-23 VE/SA 11/12-08-23 VE/SA 18/19-08-23 VE/SA 25/26-08-23 VE/SA 01/02-09-23 VE/SA 08/09-09-23 VE/SA 15/16-09-23 VE/SA 22/23-09-23 VE/SA 29/30-09-23 VE/SA 06/07-10-23 VE/SA 13/14-10-23 VE/SA 20/21-10-23 VE/SA 27/28-10-23 VE/SA 03/04-11-23 VE/SA 10/11-11-23 VE/SA 17/18-11-23 VE/SA 24/25-11-23 VE/SA 01/02-12-23 et VE/SA 08/09-12-23 Sauf le(s) : JE/VE 18/19-05-23 | Gen, V2, 1V/2, 06:29, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_82 | NON | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | FEN23_StRaphael-Nice_010 | Juan-les-Pins-00 | Cros-de-Cagnes-00 | 23:26 | 05:55 J+1 | 23:26 | 05:55 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,VE/SA Périodes : du ME/JE 17/18-05-23 au VE/SA 19/20-05-23 Et le(s) : VE/SA 16/17-12-22 VE/SA 23/24-12-22 VE/SA 30/31-12-22 VE/SA 06/07-01-23 VE/SA 13/14-01-23 VE/SA 20/21-01-23 VE/SA 27/28-01-23 VE/SA 03/04-02-23 VE/SA 10/11-02-23 VE/SA 17/18-02-23 VE/SA 24/25-02-23 VE/SA 03/04-03-23 VE/SA 10/11-03-23 VE/SA 17/18-03-23 VE/SA 24/25-03-23 VE/SA 31/01-04-23 VE/SA 07/08-04-23 VE/SA 14/15-04-23 VE/SA 21/22-04-23 VE/SA 28/29-04-23 VE/SA 05/06-05-23 VE/SA 12/13-05-23 VE/SA 26/27-05-23 VE/SA 02/03-06-23 VE/SA 09/10-06-23 VE/SA 16/17-06-23 VE/SA 23/24-06-23 VE/SA 30/01-07-23 VE/SA 07/08-07-23 JE/VE 13/14-07-23 VE/SA 21/22-07-23 VE/SA 28/29-07-23 VE/SA 04/05-08-23 VE/SA 11/12-08-23 VE/SA 18/19-08-23 VE/SA 25/26-08-23 VE/SA 01/02-09-23 VE/SA 08/09-09-23 VE/SA 15/16-09-23 VE/SA 22/23-09-23 VE/SA 29/30-09-23 VE/SA 06/07-10-23 VE/SA 13/14-10-23 VE/SA 20/21-10-23 VE/SA 27/28-10-23 VE/SA 03/04-11-23 VE/SA 10/11-11-23 VE/SA 17/18-11-23 VE/SA 24/25-11-23 VE/SA 01/02-12-23 et VE/SA 08/09-12-23 Sauf le(s) : JE/VE 18/19-05-23 | Gen, ANC, 1V/3, 06:29, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA | CHA16_0011819_82 | NON | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | FEN23_StRaphael-Nice_011 | Juan-les-Pins-00 | Cros-de-Cagnes-00 | 12:20 | 13:20 | 12:20 | 13:20 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, ANC, 1V/3, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_82 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | CAP23_Nice_038 | Nice-Ville-00 | Nice-St-Roch-P1 | 00:30 | 04:51 | 00:30 | 04:51 | Jours d'application : MA,ME,JE,VE Périodes : du MA 07-03-23 au VE 31-03-23 et du MA 03-10-23 au VE 13-10-23 | Cap, B,C,E,F,G,V1,V2,VA,VB,Z, 04:21, Nuit non passe-minuit, MA,ME,JE,VE | CHA21_0021964_36 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Nice_039 | Nice-Ville-00 | Nice-Riquier-00 | 00:30 | 05:10 | 00:30 | 05:10 | Jours d'application : SA Périodes : du SA 11-03-23 au SA 01-04-23 et du SA 07-10-23 au SA 14-10-23 | Cap, B,C,E,V1,V2,Z, 04:40, Nuit non passe-minuit, SA | CHA21_0021964_36 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Nice_040 | Nice-St-Augustin-00 | Nice-Ville-00 | 00:03 | 04:53 | 00:03 | 04:53 | Jours d'application : MA,ME,JE,VE Périodes : du MA 14-02-23 au VE 03-03-23 et du MA 12-09-23 au VE 29-09-23 | Cap, 4,B,C,E,F,V1,V2, 04:50, Nuit non passe-minuit, MA,ME,JE,VE | CHA21_0021964_36 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | CAP23_Nice_051 | Nice-St-Augustin-00 | Nice-Ville-00 | 23:10 | 23:10 J+2 | 23:10 | 23:10 J+2 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 10-11-23 au DI 12-11-23 | Cap, V1,V2, 48:00, Continu, VE,SA,DI | CHA22_0022928_24,CHA19_0016215_23 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Nice_052 | Nice-St-Augustin-00 | Nice-Ville-00 | 22:35 | 05:40 J+1 | 22:35 | 05:40 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,DI/LU Périodes : du DI/LU 12/13-03-23 au ME/JE 24/25-05-23 et du DI/LU 22/23-10-23 au ME/JE 29/30-11-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,ME/JE 01/02-11-23 | Cap, V1,V2, 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,DI/LU | CHA19_0016215_23,CHA22_0022928_24 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.25 | 1.25 | 1.25 | 0 | 0 | 0 | 2.25 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Nice_053 | Nice-St-Augustin-00 | Nice-Ville-00 | 00:08 | 05:08 | 00:08 | 05:08 | Jours d'application : LU,MA,ME,JE,DI Périodes : du DI 12-03-23 au JE 23-03-23 | Cap, B,C,E,F,G,H,V1,V2, 05:00, Nuit non passe-minuit, LU,MA,ME,JE,DI | CHA22_0022928_24 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Nice_054 | Nice-St-Augustin-00 | Nice-Riquier-00 | 00:08 | 05:08 | 00:08 | 05:08 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 09-01-23 au JE 02-02-23 Sauf le(s) : VE 13-01-23,VE 20-01-23,VE 27-01-23 | Cap, B,C,E,V1,V2, 05:00, Nuit non passe-minuit, LU,MA,ME,JE,VE | CHA22_0022928_24 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Nice_055 | Nice-Ville-00 | Nice-Riquier-00 | 22:15 | 05:20 J+1 | 22:15 | 05:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 08/09-01-23 au JE/VE 09/10-03-23 et du DI/LU 08/09-10-23 au JE/VE 26/27-10-23 | Cap, V1,V2, 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022928_24 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Nice_056 | Nice-St-Augustin-00 | Nice-Ville-00 | 23:10 | 05:40 J+1 | 23:10 | 05:40 J+1 | Jours d'application : JE/VE Périodes : du JE/VE 16/17-03-23 au JE/VE 25/26-05-23 et du JE/VE 26/27-10-23 au JE/VE 30/01-12-23 Sauf le(s) : JE/VE 18/19-05-23 | Cap, V1,V2, 06:30, Passe-minuit, JE/VE | CHA19_0016215_23,CHA22_0022928_24 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAP23_Nice_057 | Nice-Ville-00 | Nice-St-Roch-P1 | 01:15 | 05:05 | 01:15 | 05:05 | Jours d'application : SA Périodes : du SA 11-03-23 au SA 01-04-23 et du SA 07-10-23 au SA 14-10-23 | Cap, F,G,VA,VB, 03:50, Nuit non passe-minuit, SA | CHA21_0021964_36 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_Nice-Menton_016 | Nice-Ville-00 | Èze-00 | 22:00 | 08:00 J+2 | 22:00 | 08:00 J+2 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 20-01-23 au DI 22-01-23 | Def, V1,V2, , 34:00, Continu, VE,SA,DI | CHA22_0022616_02 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Nice-Menton_022 | Nice-Ville-00 | Monaco-Monte-Carlo-00 | 22:15 | 05:20 J+1 | 22:15 | 05:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du LU/MA 16/17-01-23 au JE/VE 11/12-05-23 Sauf le(s) : DI/LU 02/03-04-23,LU/MA 10/11-04-23, LU/MA 01/02-05-23,LU/MA 08/09-05-23 | Def, V1,V2, 2V/2, 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA21_0021246_16 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Nice-Menton_024 | Nice-Ville-00 | Menton-Garavan-00 | 22:15 | 05:20 J+1 | 22:15 | 05:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 08/09-01-23 au JE/VE 08/09-06-23 et du DI/LU 08/09-10-23 au JE/VE 26/27-10-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23,LU/MA 08/09-05-23,JE/VE 18/19-05-23,LU/MA 29/30-05-23 | Def, V1,V2, 2V/2, 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022928_25 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Nice-Menton_025 | Nice-Ville-00 | Menton-Garavan-00 | 22:33 | 05:03 J+1 | 22:33 | 05:03 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 11/12-06-23 au JE/VE 06/07-07-23 | Def, V1,V2, 2V/2, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022928_25 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Nice-Menton_026 | Villefranche-sur-Mer-00 | Monaco-Monte-Carlo-IP | 22:15 | 05:20 J+1 | 22:15 | 05:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 08/09-01-23 au JE/VE 09/10-03-23 et du DI/LU 08/09-10-23 au JE/VE 26/27-10-23 | Def, V1,V2, 2V/2, 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022928_25 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Nice-Menton_027 | Nice-Ville-00 | Èze-00 | 22:15 | 05:20 J+1 | 22:15 | 05:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 08/09-01-23 au JE/VE 09/10-03-23 et du DI/LU 08/09-10-23 au JE/VE 26/27-10-23 | Def, V1,V2, 2V/2, 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022928_25 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Nice-Menton_029 | Monaco-Monte-Carlo-00 | Menton-00 | 22:15 | 05:20 J+1 | 22:15 | 05:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 08/09-01-23 au JE/VE 22/23-06-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,JE/VE 18/19-05-23,LU/MA 29/30-05-23 | Def, V1,V2, 2V/2, 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024568_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Nice-Menton_030 | Monaco-Monte-Carlo-00 | Menton-00 | 22:33 | 05:03 J+1 | 22:33 | 05:03 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 25/26-06-23 au JE/VE 06/07-07-23 | Def, V1,V2, 2V/2, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA23_0024568_01 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes |  | DEF23_Nice-Menton_031 | Monaco-Monte-Carlo-00 | Menton-00 | 22:00 | 08:00 J+2 | 22:00 | 08:00 J+2 | Jours d'application : Fréquence en continu de plus de 24 heures Périodes : du VE 24-11-23 au DI 26-11-23 | Def, V1,V2, , 34:00, Continu, VE,SA,DI | CHA22_0023717_03 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Nice-Menton_032 | Monaco-Monte-Carlo-00 | Menton-00 | 22:15 | 05:20 J+1 | 22:15 | 05:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du LU/MA 12/13-12-22 au JE/VE 22/23-12-22 et du LU/MA 02/03-01-23 au JE/VE 26/27-01-23 | Def, V1,V2, 2V/2, 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022631_03 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Nice-Menton_033 | Nice-Ville-00 | Menton-Garavan-00 | 23:45 | 05:10 J+1 | 23:45 | 05:10 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 27/28-03-23 au JE/VE 13/14-04-23 et du LU/MA 11/12-09-23 au JE/VE 28/29-09-23 Sauf le(s) : LU/MA 10/11-04-23 | Def, V1,V2, 2V/2, 05:25, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA21_0022001_39 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Nice-Menton_034 | Nice-Ville-00 | Menton-Garavan-00 | 00:22 | 05:15 | 00:22 | 05:15 | Jours d'application : SA Périodes : du SA 01-04-23 au SA 15-04-23 et du SA 16-09-23 au SA 30-09-23 | Def, V1,V2, 2V/2, 04:53, Nuit non passe-minuit, SA | CHA21_0022001_39 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Nice-Menton_035 | Villefranche-sur-Mer-00 | Monaco-Monte-Carlo-IP | 22:15 | 05:20 J+1 | 22:15 | 05:20 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE,DI/LU Périodes : du DI/LU 08/09-01-23 au JE/VE 09/10-03-23 et du DI/LU 08/09-10-23 au JE/VE 26/27-10-23 | Def, V1,V2, 2V/2, 07:05, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,DI/LU | CHA22_0022928_25 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DEF23_Nice-Menton_036 | Nice-Ville-00 | Menton-Garavan-00 | 00:40 | 05:15 | 00:40 | 05:15 | Jours d'application : SA,DI Périodes : du SA 21-01-23 au DI 14-05-23 du SA 09-09-23 au DI 05-11-23 et du SA 18-11-23 au DI 03-12-23 | Def, V1,V2, 2V/2, 04:35, Nuit non passe-minuit, SA,DI | CHA21_0021966_42 | OUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | FEN23_Nice-Menton_001 | Nice-Ville-00 | Menton-Garavan-00 | 23:45 | 05:10 J+1 | 23:45 | 05:10 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 12/13-12-22 au MA/ME 16/17-05-23 et du LU/MA 22/23-05-23 au JE/VE 07/08-12-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,LU/MA 29/30-05-23,JE/VE 13/14-07-23, MA/ME 15/16-08-23,ME/JE 01/02-11-23 | Gen, V1,V2, 2V/2, 05:25, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA22_0022616_02, CHA21_0021246_16, CHA22_0023717_03, CHA21_0022003_40, CHA16_0011819_84 | NON | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0
|  | FEN23_Nice-Menton_004 | Nice-Ville-00 | Menton-Garavan-00 | 11:30 | 12:30 | 12:05 | 13:05 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V1, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_84 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_Nice-Menton_005 | Nice-Ville-00 | Menton-Garavan-00 | 10:09 | 11:09 | 09:33 | 10:33 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V2, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_84 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
|  | FEN23_Nice-Menton_009 | Nice-Ville-00 | Menton-Garavan-00 | 00:22 | 05:37 | 00:22 | 05:37 | Jours d'application : MA,JE,VE,SA Périodes : du SA 13-05-23 au SA 20-05-23 et du VE 14-07-23 au SA 15-07-23 Et le(s) : SA 17-12-22 SA 24-12-22 SA 31-12-22 SA 07-01-23 SA 14-01-23 SA 21-01-23 SA 28-01-23 SA 04-02-23 SA 11-02-23 SA 18-02-23 SA 25-02-23 SA 04-03-23 SA 11-03-23 SA 18-03-23 SA 25-03-23 SA 01-04-23 SA 08-04-23 SA 15-04-23 SA 22-04-23 SA 29-04-23 SA 06-05-23 SA 27-05-23 SA 03-06-23 SA 10-06-23 SA 17-06-23 SA 24-06-23 SA 01-07-23 SA 08-07-23 SA 22-07-23 SA 29-07-23 SA 05-08-23 SA 12-08-23 SA 19-08-23 SA 26-08-23 SA 02-09-23 SA 09-09-23 SA 16-09-23 SA 23-09-23 SA 30-09-23 SA 07-10-23 SA 14-10-23 SA 21-10-23 SA 28-10-23 SA 04-11-23 SA 11-11-23 SA 18-11-23 SA 25-11-23 SA 02-12-23 et SA 09-12-23 Sauf le(s) : MA 16-05-23,VE 19-05-23 | Gen, V1,V2, 2V/2, 05:15, Nuit non passe-minuit, MA,JE,VE,SA | CHA22_0022616_02, CHA16_0011819_84, CHA22_0023717_03, CHA21_0022003_40, CHA21_0021246_16 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Yes | DEF23_Menton-Vintimille_010 | Menton-00 | Vintimille-WI | 00:40 | 04:55 | 00:40 | 04:55 | Jours d'application : SA,DI Périodes : du SA 21-01-23 au DI 14-05-23 du SA 09-09-23 au DI 05-11-23 et du SA 18-11-23 au DI 03-12-23 | Def, V1,V2, 2V/2, 04:15, Nuit non passe-minuit, SA,DI | CHA21_0021966_43 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Yes | FEN23_Menton-Vintimille_001 | Menton-00 | Vintimille-WI | 23:49 | 04:51 J+1 | 23:49 | 04:51 J+1 | Jours d'application : LU/MA,MA/ME,ME/JE,JE/VE Périodes : du LU/MA 12/13-12-22 au MA/ME 16/17-05-23 et du LU/MA 22/23-05-23 au JE/VE 07/08-12-23 Sauf le(s) : LU/MA 10/11-04-23,LU/MA 01/02-05-23, LU/MA 08/09-05-23,LU/MA 29/30-05-23,JE/VE 13/14-07-23, MA/ME 15/16-08-23,ME/JE 01/02-11-23 | Gen, V1,V2, 2V/2, 05:02, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE | CHA16_0011819_85, CHA21_0022003_41, CHA21_0022001_40 | NON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0
| Yes | FEN23_Menton-Vintimille_006 | Menton-00 | Vintimille-WI | 12:05 | 13:05 | 12:23 | 13:23 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V1, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_85 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
| Yes | FEN23_Menton-Vintimille_007 | Menton-00 | Vintimille-WI | 09:33 | 10:33 | 09:17 | 10:17 | Jours d'application : LU,MA,ME,JE,VE Périodes : du LU 12-12-22 au VE 08-12-23 Sauf le(s) : LU 10-04-23,LU 01-05-23,LU 08-05-23,JE 18-05-23, LU 29-05-23,VE 14-07-23,MA 15-08-23,ME 01-11-23 | Sur, V2, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE | CHA16_0011819_85 | NON | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
| Yes | FEN23_Menton-Vintimille_008 | Menton-00 | Vintimille-WI | 23:40 | 05:15 J+1 | 23:40 | 05:15 J+1 | Jours d'application : ME/JE,JE/VE,VE/SA Périodes : du VE/SA 12/13-05-23 au VE/SA 19/20-05-23 et du VE/SA 07/08-07-23 au JE/VE 13/14-07-23 Et le(s) : VE/SA 16/17-12-22 VE/SA 23/24-12-22 VE/SA 30/31-12-22 VE/SA 06/07-01-23 VE/SA 13/14-01-23 VE/SA 20/21-01-23 VE/SA 27/28-01-23 VE/SA 03/04-02-23 VE/SA 10/11-02-23 VE/SA 17/18-02-23 VE/SA 24/25-02-23 VE/SA 03/04-03-23 VE/SA 10/11-03-23 VE/SA 17/18-03-23 VE/SA 24/25-03-23 VE/SA 31/01-04-23 VE/SA 07/08-04-23 VE/SA 14/15-04-23 VE/SA 21/22-04-23 VE/SA 28/29-04-23 VE/SA 05/06-05-23 VE/SA 26/27-05-23 VE/SA 02/03-06-23 VE/SA 09/10-06-23 VE/SA 16/17-06-23 VE/SA 23/24-06-23 VE/SA 30/01-07-23 VE/SA 21/22-07-23 VE/SA 28/29-07-23 VE/SA 04/05-08-23 VE/SA 11/12-08-23 VE/SA 18/19-08-23 VE/SA 25/26-08-23 VE/SA 01/02-09-23 VE/SA 08/09-09-23 VE/SA 15/16-09-23 VE/SA 22/23-09-23 VE/SA 29/30-09-23 VE/SA 06/07-10-23 VE/SA 13/14-10-23 VE/SA 20/21-10-23 VE/SA 27/28-10-23 VE/SA 03/04-11-23 VE/SA 10/11-11-23 VE/SA 17/18-11-23 VE/SA 24/25-11-23 VE/SA 01/02-12-23 et VE/SA 08/09-12-23 Sauf le(s) : JE/VE 18/19-05-23,ME/JE 12/13-07-23 | Gen, V2, 1V/2, 05:35, Passe-minuit, ME/JE,JE/VE,VE/SA | CHA16_0011819_85, CHA21_0022003_41, CHA21_0022001_40 | NON | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| Yes | FEN23_Menton-Vintimille_009 | Menton-00 | Vintimille-WI | 00:32 | 05:33 | 00:32 | 05:33 | Jours d'application : JE,VE,SA Périodes : du SA 13-05-23 au SA 20-05-23 et du SA 08-07-23 au SA 15-07-23 Et le(s) : SA 17-12-22 SA 24-12-22 et SA 31-12-22 SA 07-01-23 SA 14-01-23 SA 21-01-23 SA 28-01-23 SA 04-02-23 SA 11-02-23 SA 18-02-23 et SA 25-02-23 SA 04-03-23 SA 11-03-23 SA 18-03-23 SA 25-03-23 SA 01-04-23 SA 08-04-23 SA 15-04-23 SA 22-04-23 SA 29-04-23 et SA 06-05-23 SA 27-05-23 SA 03-06-23 SA 10-06-23 SA 17-06-23 SA 24-06-23 SA 01-07-23 SA 22-07-23 et SA 29-07-23 SA 05-08-23 SA 12-08-23 SA 19-08-23 SA 26-08-23 SA 02-09-23 SA 09-09-23 SA 16-09-23 SA 23-09-23 SA 30-09-23 SA 07-10-23 SA 14-10-23 SA 21-10-23 SA 28-10-23 SA 04-11-23 SA 18-11-23 SA 25-11-23 SA 02-12-23 et SA 09-12-23 Sauf le(s) : VE 19-05-23,JE 13-07-23 | Gen, V1, 1V/2, 05:01, Nuit non passe-minuit, JE,VE,SA | CHA16_0011819_85, CHA21_0022003_41, CHA21_0022001_40 | NON | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2

## RFI - July 2022
Section | Line | Reason for restriction | Period from | Period to | Description | LH | REG | Freight | Traffic impact
TORINO - MODANE | Lyon-Torino (St Jean And St Michel) | Lyon-Torino Tunnel (TELT) | 2022-10-28 | 2022-11-01 | 4-DAY LINE INTERRUPTION (SNCF) | X | X | X | >50% | Medium
TORINO - MODANE | Chiomonte - Exilles - Salbertrand | Interventions MS Exilles Tunnel and Serra La Voute Tunnel + extraordinary line maintenance | 12-giu-22 | 12-set-22 | 90-DAY ODD BINARY BREAK | X | X | X | Tra 10% e 30%
TORINO - MODANE | Bussoleno - Avigliana - Collegno | Extraordinary maintenance and technological upgrading activities | 12-dic-21 | 10-dic-22 | INTERRUPTION OF 3 HOURS OF CONTEMPORARY + 1 OF TRACK FOR 3 NIGHTS PER WEEK - FROM FRI / SAT TO SUN / MON | X |  | X | < 10%
NODO DI MILANO | Milano Greco Pirelli - Mirabello Milano Greco Pirelli - T.B. Seveso | PC80 and pedestrian walkway | 25-lug-22 | 4-set-22 | 45 DAY TRACK INTERRUPTION | X | X | X | Tra 30% e 50% | High
NODO DI VENEZIA | Venezia S.L. -Venezia Mestre | New TE piling | 2022-07-25 | 2022-09-04 | INTERRUPTION OF 45 DAYS OF THE EQUAL TRACK OF THE PONTE VECCHIO LINE | X | X |  | Tra 10% e 30%
VENEZIA - TRIESTE | Trieste C.M. | New PRG and ACC | 12-dic-21 | 10-dic-22 | 300 4 HOURS INTERRUPTIONS - NIGHT BAND |  |  | X | < 10%
VENEZIA - TRIESTE | Bivio D'Aurisina - Monfalcone | Extraordinary maintenance of the SABLICE Viaduct Km 120 + 696 | 6-ago-22 | 4-set-22 | TRACK BREAK OF 30 DAYS (EVEN 15 AND ODD 15) WITH 3 LINE BREAKS OF 24 HOURS | X | X | X | Tra 30% e 50% | High
NODO DI TORINO | TORINO PN – TORINO LINGOTTO | Extraordinary maintenance at Km 1+737 "Corso Dante" | set-23 | ott-23 | 4 INTERRUPTIONS OF 24h FROM TORINO PN TO TORINO LINGOTTO (GENOVA LINE DIRECTION) | X | X |  | Tra 30% e 50%
TORINO – ALESSANDRIA | TROFARELLO - ASTI | Extraordinary maintenance | ago-23 | dic-23 | 2 LINE INTERRUPTIONS OF 10 DAYS | X | X | X | > 50%
TORINO - MODANE | LYON-TORINO (ST JEAN AND ST MICHEL) | Lyon-Torino Tunnel (TELT) - works made by SNCF- R | 2023-05-01 | 2023-11-01 | IN THE PERIODS BETWEEN: 5-12 MAY, 1-2 JULY, 22-23 JULY, 29 OCTOBER - 2 NOVEMBER LINE INTERRUPTION IN FRANCE AND MEANWHILE EXTRAORDINARY MAINTENANCE FROM COLLEGNO TO AVIGLIANA AND FROM AVIGLIANA TO BUSSOLENO | X | X | X | > 50%
TORINO - MODANE | CHIOMONTE - EXILLES - SALBERTRAND | Extraordinary maintenance at Exilles tunnel (odd) and tunnel Serra La Voute (odd) + line extraordinary maintenance | 2023-06-11 | 2023-09-10 | 90 DAYS OF ODD TRACK INTERRUPTION | X | X | X | Tra 10% e 30%
TORINO - MODANE | TORINO - MODANE | Extraordinary maintenance | 2022-12-11 | 2023-12-09 | 300 OF LINE INTERRUPTION (3h and 30min in the night from Saturday to Sunday and from Sunday to Monday, 2h and 30min for al the other night of the week - all the interruption occur during the night) |  | X | X | Tra 10% e 30%
ALESSANDRIA - PIACENZA | SPINETTA - TORTONA | Works belonging to the "III Valico" project | dic-23 | gen-24 | 45 DAYS OF LINE INTERRUPTION AND 10 WEEKEND WITH 24/48h OF LINE INTERRUPTION IN THE PERIOD BETWEEN GENUARY AND JUNE | X | X | X | > 50%
NODO DI MILANO | LINEA CINTURA | Bridge extraordinary maintenance Viale Fulvio Testi | gen-23 | lug-23 | 6 INTERRUPTIONS OF 56h OF THE LINES BELONGING TO THE "NODO of MILANO" - TRAINS TO OTHER PATHS | X | X | X | Tra 30% e 50%
NODO DI VERONA | VERONA QUADRANTE EUROPA | Railroad switch renewal at Verona Q.E. | 2023-08-06 | 2023-08-23 | INTERRUPTION OF A PART OF VERONA Q.E. |  |  | X | Tra 30% e 50%
BRESCIA - VENEZIA | BRESCIA - VERONA | new AV/AC line - Sommacampagna | gen-23 | apr-23 | 80 DAYS INTERRUPTION OF PRECEDENCE TRACK OF SOMMACAMPAGNA | X | X | X | Tra 10% e 30%
BRESCIA - VENEZIA | BRESCIA - VERONA VERONA - VICENZA | new AV/AC line | 2022-12-11 | 2023-12-09 | 320 LINE INTERRUPTIONS OF 4.5/5h FOR 6 NIGHT IN EVERY WEEK + 1 INTERRUPTION OF 80h OF THE LINE FROM VERONA TO VICENZA (2-5 NOVEMBER) + 2 INTERRUPTIONS OF 50h OF THE LINE FROM BRESCIA TO VICENZA (9-10 E 23-24 SEPTEMBER) + 8 INTERRUPTIONS OF 48h OF THE LINE FROM VERONA TO VICENZA | X | X | X | Tra 10% e 30%
NODO DI VENEZIA | VENEZIA MESTRE | new switch from historical line to new AV/AC line | set-23 | 2023-12-09 | 30 INTERRUPTIONS OF A PART OF THE STATION OF VENEZIA MESTRE FOR 5-6h | X | X |  | < 10%
VENEZIA - TRIESTE | TORVISCOSA - CERVIGNANO | Bridge extraordinary maintenance at Cervignano | set-23 | dic-23 | 90 DAYS OF ONE TRACK INTERRUPTION - TRAINS IN THE SINGLE TRACK FROM TORVISCOSA TO CERVIGNANO - CHECK FOR THE DEGRADING OF THE LINE TO CATEGORY C3 |  | X | X | Tra 10% e 30%
VENEZIA - TRIESTE | TRIESTE CAMPO MARZIO | PRG and ACC | 2022-12-11 | 2023-12-09 | 300 INTERRUPTIONS OF 4h - DURING THE NIGHT + 2INTERRUPTIONS OF 3 DAYS (IN AUGUST AND DECEMBER) |  | X |  | > 50%
NODO DI TORINO | TORINO PORTA SUSA | Railroad switch renewal at Torino Porta Susa | dic-23 | apr-24 | 40 INTERRUPTIONS OF THE STATION OF 5h AND 30min + 10 INTERRUPTIONS OF 7h - NIGHT | X | X | X | Tra 10% e 30%
TORINO - MODANE | SALBELTRAND - TORINO | Extraordinary maintenance | 10-dic-23 | 14-dic-24 | 300 LINE INTERRUPTIONS OF 3h AND 30min - NIGHT |  | X | X | Tra 10% e 30%
TORINO-MODANE | BARDONECCHIA - SALBERTRAND | Extraordinary maintenance | 10-dic-23 | 14-dic-24 | 300 INTERRUPTIONS OF 2h - DAYTIME |  | X | X | Tra 10% e 30%
TORINO-MODANE | SALBERTRAND - MODANE | Extraordinary maintenance | mag-24 | mag-24 | 15 DAYS LINE INTERRUPTION (PROBABLY FROM 8 MAY TO 12 MAY PARTLY IN SHADE WITH FRENCH WORKS) | X | X | X | > 50%
TORINO - MODANE | LYON-TORINO (ST JEAN AND ST MICHEL) | Lyon-Torino Tunnel (TELT) - works made by SNCF- R | 8-nov-24 | 12-nov-24 | 4 DAYS LINE INTERRUTION IN FRANCE | X | X | X | > 50%
NODO DI MILANO | MILANO C.LE | PRG and ACC | 2023-12-10 | 2024-12-14 | INTERRUPTION OF STATION TRACK WITH REMODELLING OF TRAIN STOPS IN OTHER STATIONS OF THE MILAN NODE | X | X |  | Tra 10% e 30%
MILANO - VENEZIA AC/AV | VERONA - VICENZA | new AV/AC line - Bivio Vicenza | 3-ago-24 | 23-ago-24 | 21 DAYS OF LINE INTERRUPTION | X | X | X | > 50%
BRESCIA - VENEZIA | BRESCIA - VERONA VERONA - VICENZA | new AV/AC line | 2022-12-11 | 2023-12-09 | 320 LINE INTERRUPTIONS OF 4.5/5h FOR 6 NIGHT IN EVERY WEEK + 8 LINE INTERRUPTIONS OF 48h | X | X | X | Tra 10% e 30%
VENEZIA - TRIESTE | TORVISCOSA – CERVIGNANO | Bridge extraordinary maintenance at Cervignano | mar-24 | mag-24 | 90 DAYS OF ONE TRACK INTERRUPTION - TRAINS IN THE SINGLE TRACK FROM TORVISCOSA TO CERVIGNANO - CHECK FOR THE DEGRADING OF THE LINE TO CATEGORY C3 |  | X | X | Tra 10% e 30%
NODO DI TRIESTE | TRIESTE CM | PRG and propedeutical works for ACC | dic-23 | dic-24 | 300 INTERRUPTIONS OF 4h - NIGHT |  |  | X | Tra 10% e 30%
VENEZIA - UDINE - TARVISIO B. | UGOVIZZA VALBRUNA - CARNIA | Replacement of the slab track system (IPA tecnology) with the ballasted track system. | 2023-05-18 | 06-ago-23 | TRACK INTERRUPTION OF 80 DAYS WITH LINE INTERRUPTION OF 3h DURING DAYTIME (IF THERE IS THE ACTIVATION OF PC AUPA) - THIS INTERRUPTION DOESN'T INVOLVE THE CORRIDOR LINE, BUT FOR THE HIGH IMPACT CORRELATED TO THE INTERESTED LINE CAN CREATE SOME EFFECT ALSO TO THE CORRIDOR LINES | X | X | X | Tra 30% e 50%
BOLOGNA - PRATO | PIANORO - SAN BENEDETTO | Activity for the standardization of the line to P/C 80 | 2023-06-11 | 2023-09-10 | 90 DAYS OF LINE INTERRUPTION AND INTERRUPTION 7h IN DAYTIME AND NIGHT BAND IN THE LINE FROM SAN BENEDETTO TO VERNIO IN THE PERIOD FROM 10 AUGUST TO 10 SEPTEMBER THE LINE INTERRUPTION INVOLVE VERNIO - THIS INTERRUPTION DOESN'T INVOLVE THE CORRIDOR LINE, BUT FOR THE HIGH IMPACT CORRELATED TO THE INTERESTED LINE CAN CREATE SOME EFFECT ALSO TO THE CORRIDOR LINES | X | X | X | > 50%
BOLOGNA - PRATO | PIANORO - SAN BENEDETTO - PRATO | Activity for the standardization of the line to P/C 81 | gen-23 | nov-23 | 12 INTERRUPTIONS OF 31h BEFORE THE LINE INTERRUPTION FROM PIANORO TO SAN BENEDETTO DESCRIBED PREVIOUSLY AND 5 INTERRUPTIONS AFTER THE RIACTIVATION OF THE LINE + 200 INTERRUPTIONS OF 3.5h - DAYTIME BAND - THIS INTERRUPTION DOESN'T INVOLVE THE CORRIDOR LINE, BUT FOR THE HIGH IMPACT CORRELATED TO THE INTERESTED LINE CAN CREATE SOME EFFECT ALSO TO THE CORRIDOR LINES | X | X | X | Tra 10% e 30%
UDINE - TARVISIO | CARNIA - UGOVIZZA | Replacement of the slab track system (IPA tecnology) with the ballasted track system. | 2024-06-10 | 2024-09-08 | 90 DAYS OF TRACK INTERRUPTION AND 3h OF LINE INTERRUPTION IN DAYTIME (IF THERE IS THE ACTIVATION OF PC AUPA) - THIS INTERRUPTION DOESN'T INVOLVE THE CORRIDOR LINE, BUT FOR THE HIGH IMPACT CORRELATED TO THE INTERESTED LINE CAN CREATE SOME EFFECT ALSO TO THE CORRIDOR LINES | X | X | X | Tra 30% e 50%
BOLOGNA - PRATO | PIANORO - SAN BENEDETTO | Activity for the standardization of the line to P/C 80 | 9-giu-23 | 8-set-24 | 90 DAYS OF LINE INTERRUPTION AND INTERRUPTION 7h IN DAYTIME AND NIGHT BAND IN THE LINE FROM SAN BENEDETTO TO VERNIO FOR 30 DAYS THE LINE INTERRUPTION INVOLVE VERNIO - THIS INTERRUPTION DOESN'T INVOLVE THE CORRIDOR LINE, BUT FOR THE HIGH IMPACT CORRELATED TO THE INTERESTED LINE CAN CREATE SOME EFFECT ALSO TO THE CORRIDOR LINES | X | X | X | > 50%
BOLOGNA - PRATO | PIANORO - SAN BENEDETTO - PRATO | Activity for the standardization of the line to P/C 80 | feb-24 | set-24 | LINE INTERRUPTION FOR 3 WEEKEND EVERY MONTH + 4h OF INTERRUPTION DURING THE DAYTIME BAND IN WEEKDAYS - THIS INTERRUPTION DOESN'T INVOLVE THE CORRIDOR LINE, BUT FOR THE HIGH IMPACT CORRELATED TO THE INTERESTED LINE CAN CREATE SOME EFFECT ALSO TO THE CORRIDOR LINES | X | X | X | Tra 10% e 30%

## SZ-I - July 2022
2022
N° | IM | LINE | SECTION | DECRIPTION OF WORKS / TCRs | Period (START - END) |  | DETAIL OF WORKS / TCRs | TIMETABLE TRAINS ADJUSTMENTS | SLOWDOWN | NOTES
[5 empty] | FROM | TO
1 | SZ-I | Pragersko-Zidani Most | Slovenska Bistrica-Pragersko | upgrading the line | 2.8.2022, 22.8.2022 | 17.8.2022, 20.9.2022 | RIGHT TRACK/ LEFT TRACK Regular maintenance, updating of track | NO
2 | SZ-I | Divača-Koper | Divača-Koper | maintenance works | 2 mondays every month |  | TOTAL CLOSED Regular maintenance, updating of track | NO
3 | SZ-I | Ljubljana-Sežana | Brezovica-Preserje-Borovnica | upgrading the line | 2022-10-15 | 2022-12-31 | CLOSED LEFT TRACK Detail track upgrade, speed increase, signaling block upgrade | YES | right track slowdown 30km/h | alternative bus services for local passenger trains
4 | SZ-I | Ljubljana-Sežana | Borovnica-Verd | maintenance works | 2022-09-06 | 2022-09-10 | RIGHT TRACK/ LEFT TRACK Regular maintenance, updating of track | NO
5 | SZ-I | Ljubljana-Sežana | Postojna-Prestranek | maintenance works | 2022-10-08 | 2022-10-11 | RIGHT TRACK/ LEFT TRACK Regular maintenance, updating of track | NO
6 | SZ-I | Ljubljana-Sežana | Prestranek-Pivka | maintenance works | 2022-11-07 | 2022-11-12 | Right track, maintenance | NO
2023
N° | IM | LINE | SECTION | DECRIPTION OF WORKS / TCRs | Period (START - END) |  | DETAIL OF WORKS / TCRs | TIMETABLE TRAINS ADJUSTMENTS | SLOWDOWN | NOTES
[5 empty] | FROM | TO
1 | SZ-I | Divača-Koper | Divača-Koper | maintenance works | 2 mondays every month |  | TOTAL CLOSED Regular maintenance, updating of track | NO
2 | SZ-I | Divača-Koper | Divača-Koper | maintenance works | 29.4.2023, 12.8.2023, 26.8.2023 | 2.5.2023, 15.8.2023, 29.8.2023 | TOTAL CLOSED Regular maintenance, updating of track | NO | TOTAL CLOSED
3 | SZ-I | Ljubljana-Sežana | Brezovica-Preserje-Borovnica | upgrading the line | 2023-01-05 | 2023-03-31 | CLOSED right TRACK Detail track upgrade, speed increase, signaling block upgrade | YES | left track slowdown 30km/h | alternative bus services for local passenger trains
4 | SZ-I | Ljubljana-Sežana | Logatec-Rakek | maintenance works | 26.8.2023, 2.9.2023 | 30.8.2023, 6.9.2023 | LEFT/RIGHT TRACK Regular maintenance, updating of track | NO
5 | SZ-I | Ljubljana-Sežana | Rakek-Postojna | maintenance works | 16.9.2023, 23.9.2023 | 20.9.2023, 27.9.2023 | RIGHT TRACK/ LEFT TRACK Regular maintenance, updating of track | NO
6 | SZ-I | Ljubljana-Sežana | Logatec-Rakek-Postojna | maintenance works | 12.8.2023, 26.8.2023 | 15.8.2023, 29.8.2023 | LEFT/RIGHT TRACK Regular maintenance, updating of track | NO
7 | SZ-I | Ljubljana-Sežana | Postojna-Prestranek | maintenance works | 13.5.2023, 20.5.2023 | 18.5.2023, 25.5.2023 | RIGHT TRACK/ LEFT TRACK Regular maintenance, updating of track | NO
8 | SZ-I | Ljubljana-Sežana | Prestranek-Pivka | maintenance works | 29.4.2023, 6.5.2023 | 2.5.2023, 9.5.2023 | RIGHT TRACK/ LEFT TRACK Regular maintenance, updating of track | NO

## HZ-I july 2018 (hidden)
IM | ID | Section | Direction | Line |  | Year |  | Week |  | Period from |  | Period to |  | Duration | Time of day | Reason for restriction | Traffic impact |  |  |  |  | Traffic measures |  |  |  |  | Description | International coordination | In yearly timetable | IM Project ID (Optional)
|  |  |  | From | To | From | To | From | To | Date from | Time from | Date to | Time to |  |  |  | Total Closure | Reduced Track Availability | Speed Restrictions | Weight, Length, Profile | Diesel only | Cancellation | Re-routing | Train replacement | Delays | Other
HŽ Infrastruktura | HZI001 | Savski Marof - Zagreb ZK | <> | Savski Marof | Podsused TV | 2018 | 2019 | 22 | 14 | 2018-07-01 |  | 2019-04-30 |  | 8 | Day | Track work |  | x | x |  |  | X |  |  | X | X | Closure of running track alternate left and right |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI002 | Savski Marof - Zagreb ZK | <> | Savski Marof | Podsused TV | 2019 | 2019 | 14 | 35 | 2019-04-01 |  | 2019-08-31 |  | singly permanent | All day | Track work | x | x | x | [5 empty] | x |  | Singulary track clousure in stations |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI003 | Savski Marof - Zagreb ZK | <> | Savski Marof | Podsused TV | 2019 | 2019 | 35 | 39 | 2019-08-01 |  | 2019-09-30 |  | 2018-08-06 | Day | Signal work |  | x |  |  |  | x |  |  | x | x | Closure of running track alternate left and right |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI004 | Dugo Selo - Koprivnica | <> | Vrbovec | Križevci | 2017 | 2019 | 9 | 52 | 2017-03-01 |  | 2019-12-27 |  | 9 | Day | Track work | x |  | x |  |  | x |  |  | x |  | Reconstruction of existing and construction of a second track. Occasional total closure during the weekend up to 72 hours. |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI005 | Dugo Selo - Koprivnica | <> | Dugo Selo | Vrbovec | 2018 | 2019 | 52 | 52 | 2018-12-01 |  | 2019-12-01 |  | 9 | Day | Track work | x |  | x |  |  | x |  |  | x |  | Reconstruction of existing and construction of a second track. Occasional total closure during the weekend up to 72 hours. |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI006 | Dugo Selo - Koprivnica | <> | Križevci | Koprivnica | 2019 | 2023 | 23 | 52 | 2019-06-01 |  | 2023-12-31 |  | 9 | Day | Track work | x |  | x |  |  | x |  |  | x |  | Reconstruction of existing and construction of a second track. Occasional total closure during the weekend up to 72 hours. |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI007 | Koprivnica - Gyekenyes | <> | Koprivnica | Koprivnica gr. | 2019 | 2023 | 23 | 52 | 2019-06-01 |  | 2023-12-30 |  | 9 | Day | Track work | x |  | x |  |  | x |  |  | x |  | Reconstruction of existing and construction of a second track. Occasional total closure during the weekend up to 72 hours. |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI008 | Rijeka - Sušak Pećine | <> | Rijeka | Rijeka Brajdica | 2018 | 2020 | 18 | 52 | 2018-07-01 |  | 2020-12-28 |  | operational clousure | All day | Track work | x |  | x | [5 empty] | x |  | Reconstruction of station Rijeka and construction of container terminal on "Zagreb" dock |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI009 | Sušak Pećine - Rijeka Brajdica | <> | Sušak Pećine | Rijeka Brajdica | 2018 | 2020 | 9 | 52 | 2018-03-01 |  | 2020-12-28 |  | permanent | All day | Track work | x | [5 empty] | x |  | x |  | Multimodal platform development project at Rijeka port for connection with container terminal "Jadranska vrata" - project Brajdica |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI010 | Moravice - Zagreb RK | <> | Duga Resa | Gomirje | 2017 | 2018 | 35 | 52 | 2017-09-01 |  | 2018-12-31 |  | 6h | Day | Track work | x | [7 empty] | x |  | Operational clousure of tracks in stations: Duga Resa, Zvečaj, Generalski Stol, Gornje Dubrave, Oštarije, Ogulin and Gomirje |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI011 | Rijeka - Sušak Pećine | <> | Sušak Pećine | Rijeka | 2018 | 2019 | 1 | 52 | 2018-01-01 |  | 2019-03-30 |  | 6 | Day | Catenary work | x |  | x | [5 empty] | x |  | Reconstruction of the cuttings, every working day, occasional total closure up to 24h |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI012 | Sušak Pećine - Škrljevo | <> | Škrljevo | Sušak Pećine2018 | 2018 | 2019 | 1 | 52 | 2018-01-01 |  | 2019-03-31 |  | 6 | Day | Catenary work | x |  | x | [5 empty] | x |  | Reconstruction of the cuttings, every working day, occasional total closure up to 24h |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI013 | Škrljevo - Lokve | <> | Lokve | Škrljevo | 2018 | 2019 | 1 | 52 | 2018-01-01 |  | 2019-03-30 |  | 6 | Day | Catenary work | x |  | x | [5 empty] | x |  | Reconstruction of the cuttings, every working day, occasional total closure up to 24h |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI014 | Lokve - Moravice | <> | Moravice | Lokve | 2018 | 2019 | 1 | 12 | 2018-01-01 |  | 2019-03-31 |  | 6 | Day | Catenary work | x |  | x | [5 empty] | x |  | Reconstruction of the cuttings, every working day, occasional total closure up to 24h |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI015 | Moravice - Zagreb RK | <> | Ogulin | Moravice | 2018 | 2019 | 1 | 12 | 2018-01-01 |  | 2019-03-01 |  | 6 | Day | Catenary work | x |  | x | [5 empty] | x |  | Reconstruction of the cuttings, every working day, occasional total closure up to 24h |  |  |  | RFC6 Main
HŽ Infrastruktura | HZI016 |  | <> | Dugo Selo | Novska | 2019 | 2024 | 48 | 17 | 2019-12-01 |  | 2024-04-30 |  | 9 | Day | Track work | x |  | x | [5 empty] | x | x | Reconstruction of existing and construction of a second track.
HŽ Infrastruktura | HZI017 |  | <> | Dugo Selo | Novska | 2018 | 2018 | 1 | 48 | 2018-01-03 |  | 2018-11-30 |  | 8 | Day | Signal work | [8 empty] | x | x | Reconstruction of electrical network
HŽ Infrastruktura | HZI018 |  | < | Garčin | Vinkovci | 2018 | 2018 | 1 | 52 | 2018-01-03 |  | 2018-12-30 |  | 8 | Day | Misc. Work |  | x | [6 empty] | x | x | Reconstruction of electrical network

## SZ-I - july 2018 (hidden)
IM | ID | Section | Direction | Line |  | Year |  | Week |  | Period from |  | Period to |  | Duration | Time of day | Reason for restriction | Traffic impact |  |  |  |  | Traffic measures |  |  |  |  | Description | International coordination | In yearly timetable | IM Project ID (Optional)
|  |  |  | From | To | From | To | From | To | Date from | Time from | Date to | Time to |  |  |  | Total Closure | Reduced Track Availability | Speed Restrictions | Weight, Length, Profile | Diesel only | Cancellation | Re-routing | Train replacement | Delays | Other
SŽ Infrastruktura | SŽ-I 01 | Divača – Koper | <> | Divača | Koper | 2018 | 2018 | 4 | 48 | 2018-02-01 |  | 2018-12-01 |  | Every second Monday in month | 8.00-15.00 | Maintanance | x | [7 empty] | x
SŽ Infrastruktura | SŽ-I 02 | Station Celje | <> | Station Celje |  | 2017 | 2018 | 7 | 21 | 2017-02-13 |  | 2018-05-30 |  | 480 | days | Track work (upgrade) |  | x | x | x |  |  |  |  | x
SŽ Infrastruktura | SŽ-I 03 | Laško- Celje | <> | Laško | Celje | 2017 | 2018 | 45 | 40 | 2017-11-01 |  | 2018-10-30 |  | 340 | days | Track work (upgrade) |  | x | x | x |  |  |  |  | x
SŽ Infrastruktura | SŽ-I 04 | Rimske Toplice - Laško | <> | Rimske Toplice | Laško | 2018 | 2018 | 8 | 22 | 2018-07-19 |  | 2018-10-16 |  | 108 | days | Track work (upgrade) |  | x | x | x |  |  |  |  | x
SŽ Infrastruktura | SŽ-I 05 | Rimske Toplice - Laško | <> | Rimske Toplice | Laško | 2018 | 2018 | 39 | 51 | 2018-09-25 |  | 2018-10-28 |  |  |  | Track work (upgrade) |  | x | x | x |  |  |  |  | x
SŽ Infrastruktura | SŽ-I 06 | Zidani most - Rimske Toplice | <> | Zidani most | Rimske toplice | 2018 | 2019 | 7 | 22 | 2019-07-01 |  | 2020-06-10 |  | 420 | days |  |  | x | x | x |  |  |  |  | x
SŽ Infrastruktura | SŽ-I 07 | Station Rimske Toplice | <> | Station Rimske Toplice |  | 2018 | 2019 | 21 | 22 | 2019-06-01 |  | 2020-06-30 |  | 300 | days |  |  | x | x | x |  |  |  |  | x
SŽ Infrastruktura | SŽ-I 08 | Poljčane-Slovenska Bistrica | <> | Poljčane | Slovenska Bistrica | 2017 | 2018 | 35 | 15 | 2017-09-02 |  | 2018-04-04 |  | 214 | days | Track work (upgrade) |  | x | x | x |  |  |  |  | x
SŽ Infrastruktura | SŽ-I 09 | Station Pragersko | <> | Station Pragersko |  | 2018 | 2020 | 22 | 31 | 2018-06-01 |  | 2020-06-01 |  | 990 | days | Reconstruction of the station |  | x | x | x |  |  |  |  | x
SŽ Infrastruktura | SŽ-I 10 | Divača - Koper | < > | Divača | Koper | 2018 | 2018 | 1 | 1 | 2018-01-05 |  | 2018-01-07 |  | 48 h |  | Track work (upgrade) | x |  | x |  |  | x |  |  | x
SŽ Infrastruktura | SŽ-I 11 | Divača - Koper | < > | Divača | Koper | 2018 | 2018 | 2 | 2 | 2018-01-12 |  | 2018-01-14 |  | 48 h |  | Track work (upgrade) | x |  | x |  |  | x |  |  | x
SŽ Infrastruktura | SŽ-I 12 | Divača - Koper | < > | Divača | Koper | 2018 | 2018 |  |  | 2018-08-11 |  | 2018-08-13 |  | 48 h |  | Track work (upgrade) | x |  | x |  |  | x |  |  | x
SŽ Infrastruktura | SŽ-I 13 | Divača - Koper | < > | Divača | Koper | 2018 | 2018 |  |  | 2018-08-18 |  | 2018-08-20 |  | 48 h |  | Track work (upgrade) | x |  | x |  |  | x |  |  | x
SŽ Infrastruktura | SŽ-I 14 | Divača - Koper | < > | Divača | Koper | 2018 | 2018 |  |  | 2018-08-25 |  | 2018-08-27 |  | 48 h |  | Track work (upgrade) | x |  | x |  |  | x |  |  | x
SŽ Infrastruktura | SŽ-I 15 | Divača - Koper | < > | Divača | Koper | 2018 | 2018 |  |  | 2018-12-25 |  | 2018-12-29 |  | 96 h |  | Track work (upgrade) | x |  |  |  |  | x
SŽ Infrastruktura | SŽ-I 16 | Postojna - Rakek (DT) | <> | Postojna | Rakek | 2018 | 2018 | 35 | 36 | 2018-09-01 |  | 2018-09-01 |  | 3 | Day | Maintanance |  | x | x | x |  |  |  |  | x | [5 empty] | RFC6 Main
SŽ Infrastruktura | SŽ-I 17 | Ljubljana - Borovnica | <> | Ljubljana | Borovnica | 2020 | 2020 |  |  | 2020-07-01 |  | 2020-10-28 |  | 10 | 7.00-17.00 | Maintanance |  | x | x | x |  |  |  |  | x | [5 empty] | RFC6 Main
SŽ Infrastruktura | SŽ-I 18 | Ljubljana - Borovnica | <> | Ljubljana | Borovnica | 2021 | 2021 |  |  | 2021-02-01 |  | 2021-05-31 |  | 10 | 7.00-17.00 | Maintanance |  | x | x | x |  |  |  |  | x | [5 empty] | RFC6 Main
SŽ Infrastruktura | SŽ-I 19 | Borovnica - Preserje (DT) | <> | Borovnica | Preserje | 2018 | 2018 | 14 | 18 | 2018-04-01 |  | 2018-04-29 |  | 10 | 7.00-17.00 | Maintanance |  | x | x | x |  |  |  |  | x | [5 empty] | RFC6 Main
SŽ Infrastruktura | SŽ-I 20 | Brestanica - Brežice (LT) | <> | Brestanica | Brežice | 2018 | 2018 | 32 | 33 | 2018-09-21 |  | 2018-09-23 |  | 3 | Day | Maintanance |  | x | x | x |  |  |  |  | x | [5 empty] | RFC6 Main
SŽ Infrastruktura | SŽ-I 21 | Brežice - Dobova (DT) | <> | Brežica | Dobova | 2018 | 2018 | 1 | 52 | 2018-10-19 |  | 2018-10-21 |  | 3 | Day | Maintanance |  | x | x | x |  |  |  |  | x | [5 empty] | RFC6 Main
SŽ Infrastruktura | SŽ-I 22 | Pragersko - Ormož | <> | Pragersko | Ormož | 2018 | 2018 | 16 | 18 | 2018-04-09 |  | 2018-04-30 |  | 4 | 7.00-15.00 | Maintanance | x | [7 empty] | x | [5 empty] | RFC6 Main
SŽ Infrastruktura | SŽ-I 23 | Ormož - Hodoš | <> | Ormož | Hodoš | 2018 | 2018 | 18 | 22 | 2018-05-07 |  | 2018-05-28 |  | 4 | 7:00-13:00 | Maintanance | x | [7 empty] | x | [5 empty] | RFC6 Main
SŽ Infrastruktura | SŽ-I 24 | Pragersko - Ormož | <> | Pragersko | Ormož | 2018 | 2018 | 35 | 37 | 2018-09-03 |  | 2018-09-24 |  | 4 | 7.00-15.00 | Maintanance | x | [7 empty] | x | [5 empty] | RFC6 Main
SŽ Infrastruktura | SŽ-I 25 | Ormož - Hodoš | <> | Ormož | Hodoš | 2018 | 2018 | 41 | 43 | 2018-10-01 |  | 2018-10-29 |  | 5 | 7:00-13:00 | Maintanance | x | [7 empty] | x | [5 empty] | RFC6 Main
SŽ Infrastruktura | SŽ-I 26 | Hrastnik-Zidani Most | <> | Hrastnik | Zidani most | 2019 | 2020 | 32 | 15 | 2019-06-01 |  | 2020-02-02 | [5 empty] | x | x | x |  |  |  |  | x | [5 empty] | RFC6 Main

## HZ-I July 2022
Year | Period | Line | Reason for restriction | Traffic impact | Traffic measures | Infra-structure | estimated delay* | Path coordination | Conflict | Solution | Description
2022
| May 2020 - August 2022 | Savski Marof - Zaprešić - Zagreb ZK (Kustošija) | Renewal | Reduced track availability | Restricted speed running | HŽI |  |  |  |  | Permanent closure of one track for the laying of subbase, permanent closure of one track for replacing of the track, closures by day (Monday - Sunday) 6-8 hours (as needed)
| May 2020 - August 2022 | Savski Marof, Zaprešić, Podsused and Zagreb ZK stations | Renewal | Reduced track availability | Restricted speed running | HŽI |  |  |  |  | Closures by day (Monday - Sunday) for 6 to 8 hours, alternately left track and right track (as needed), possible closures for 36 hours according to the needs of contractors
| December 2019 - December 2022 | Dugo Selo - Križevci | Reconstruction / Construction | Reduced track availability | Restricted speed running | HŽI |  |  |  |  | line subsection Dugo Selo-Vrbovec: 8 hours day closure every working day (Monday - Friday) from 7:00 am to 4:00 pm, occasional closures at weekends for up to 72 hours according to the needs of contractors, possible closures on the sections Dugo Selo-Sesvete, Dugo Selo - Ivanić Grad (8 hours closure from 7:00 am to 4:00 pm and occasional closures of the line for up to 72 hours)
| June 2020 (expected) - December 2023 | Križevci - Koprivnica - State border | Reconstruction / Construction | Reduced track availability | Restricted speed running | HŽI |  |  |  |  | line subsection Križevci - Koprivnica: Denivelation will be performed (owerpasses and underpasses) and deviation. Daily closures (Monday - Sunday) of the line (8 hours closure in interval from 6:00 am to 4:00 pm) and occasional closures at weekends for up to 72 hours. Possible closures on the section Koprivnica-Rasinja, Koprivnica-Bregi (8 hours closure in interval from 7:00 am to 4:00 pm and occasional closures for up to 72 hours). If needed possible closures longer than 72 hours. line subsection Koprivnica - state border: Works on the route will be performed. Daily closures (Monday - Sunday) of the line (8 hours closure in interval from 6:00 am to 4:00 pm) and occasional closures for up to 72 hours. Possible closures on the section Koprivnica-Rasinja, Koprivnica-Bregi (8 hours closure in interval from 7:00 am to 4:00 pm and occasional closures for up to 72 hours).
| December 2020 - December 2023 | Hrvatski Leskovac - Karlovac | Track reconstruction / construction of the second track | Reduced track availability | Restricted speed running | HŽI |  |  |  |  | line subsection Jastrebarsko - Karlovac: Daily closures of the line (8- hour closures in interval from 7:00 am to 4:00 pm), occasional closures at weekends for up to 72 hours according to the needs of contractors, possible closures on the sections Karlovac-Kamanje, Karlovac - Mrzlo Polje (8 hours of closure in interval from 7:00 am to 4:00 pm)
2023
| September 2022 - December 2023 | Zagreb ZK station (Kustošija) - Zagreb GK | Track reconstruction | Reduced track availability | Restricted speed running | HŽI |  |  |  |  | permanent closure of one track for tamponing, permanent closure of one track for track change, daily closures (Mon-Sun) 6-8 hours (if necessary). Possible closures on the section Zagreb ZK-Trešnjevka rsp, daily closures (Mon-Sun) 6- 8 hours (if necessary), and possible closures of up to 72 hours according to the needs of the contractor
| September 2022 - December 2023 | Zagreb ZK - station | Renewal | Reduced track availability | Restricted speed running | HŽI |  |  |  |  | daily closures (Mon-Sun) lasting from 6 to 8 hours, alternately left track and right track (if necessary), and possible closures up to 72 hours according to the needs of the contractor. Possible closures on the section Zagreb ZK-Trešnjevka rsp, daily closures (Mon-Sun) 6-8 hours (if necessary), and possible closures of up to 72 hours according to the needs of the contractor
| December 2019 - December 2023 | Dugo Selo - Križevci | Reconstruction / Construction | Reduced track availability | Restricted speed running | HŽI |  |  |  |  | line subsection Dugo Selo-Vrbovec: 8 hours day closure every working day (Monday - Friday) from 7:00 am to 4:00 pm, occasional closures at weekends for up to 72 hours according to the needs of contractors, possible closures on the sections Dugo Selo-Sesvete, Dugo Selo - Ivanić Grad (8 hours closure from 7:00 am to 4:00 pm and occasional closures of the line for up to 72 hours)
| June 2020 - December 2023 | Križevci - Koprivnica - State border | Reconstruction / Construction | Reduced track availability | Restricted speed running | HŽI |  |  |  |  | line subsection Križevci - Koprivnica: Denivelation will be performed (owerpasses and underpasses) and deviation. Daily closures (Monday - Sunday) of the line (8 hours closure in interval from 6:00 am to 4:00 pm) and occasional closures at weekends for up to 72 hours. Possible closures on the section Koprivnica-Rasinja, Koprivnica-Bregi (8 hours closure in interval from 7:00 am to 4:00 pm and occasional closures for up to 72 hours). If needed possible closures longer than 72 hours. line subsection Koprivnica - state border: Works on the route will be performed. Daily closures (Monday - Sunday) of the line (8 hours closure in interval from 6:00 am to 4:00 pm) and occasional closures for up to 72 hours. Possible closures on the section Koprivnica-Rasinja, Koprivnica-Bregi (8 hours closure in interval from 7:00 am to 4:00 pm and occasional closures for up to 72 hours).
| June 2022 - June 2025 | Hrvatski Leskovac - Karlovac | Track reconstruction / construction of the second track | Reduced track availability | Restricted speed running | HŽI |  |  |  |  | line subsection Jastrebarsko - Karlovac: Daily closures of the line (8- hour closures in interval from 7:00 am to 4:00 pm), occasional closures at weekends for up to 72 hours according to the needs of contractors, possible closures on the sections Karlovac-Kamanje, Karlovac - Mrzlo Polje (8 hours of closure in interval from 7:00 am to 4:00 pm)
| June 2023 - October 2023 | Line Zagreb GK - Rijeka Bukovac tunnel | Renewal | Reduced track availability | Restricted speed running | HŽI |  |  |  |  | closure of the section Lokve - Fužine for 6 hours 5 days a week (Monday - Friday).

## MAV - July 2022
IM | ID | Section | Direction | Line |  | Year |  | Week |  | Date |  | Time |  | Duration | Time of day | Reason for restriction | Traffic impact |  |  |  |  | Traffic measures |  |  |  |  | Description | International coordination | IM Project ID (Optional)
|  |  |  | From | To | From | To | From | To | From | To | From | To |  |  |  | Total Closure | Reduced Track Availability | Speed Restrictions | Weight, Length, Profile | Diesel only | Cancellation | Re-routing | Train replacement | Delays | Other
MAV | 5506001001 | Hegyeshalom-Ferencváros | > | Szárliget | Tatabánya | 2022 | 2022 | 1 | 2 | 2022-01-03 | 2022-01-09 | 0:00 | 23:59 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001002 | Hegyeshalom-Ferencváros | > | Szárliget | Tatabánya | 2022 | 2022 | 2 | 3 | 2022-01-10 | 2022-01-16 | 0:00 | 23:59 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001003 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 3 | 3 | 2022-01-17 | 2022-01-18 | 21:30 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001004 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 4 | 4 | 2022-01-24 | 2022-01-25 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001005 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 4 | 4 | 2022-01-25 | 2022-01-26 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001006 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 4 | 4 | 2022-01-26 | 2022-01-27 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001007 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 4 | 4 | 2022-01-27 | 2022-01-28 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001008 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 4 | 4 | 2022-01-28 | 2022-01-29 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001009 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 5 | 5 | 2022-01-31 | 2022-02-01 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001010 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 5 | 5 | 2022-02-01 | 2022-02-02 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001011 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 5 | 5 | 2022-02-02 | 2022-02-03 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001012 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 5 | 5 | 2022-02-03 | 2022-02-04 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001013 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 6 | 6 | 2022-02-07 | 2022-02-08 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001014 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 6 | 6 | 2022-02-08 | 2022-02-09 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001015 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 6 | 6 | 2022-02-09 | 2022-02-10 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001016 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 6 | 6 | 2022-02-10 | 2022-02-11 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001017 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 6 | 6 | 2022-02-11 | 2022-02-12 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001018 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 7 | 7 | 2022-02-14 | 2022-02-15 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001019 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 7 | 7 | 2022-02-15 | 2022-02-16 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001020 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 7 | 7 | 2022-02-16 | 2022-02-17 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001021 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 7 | 7 | 2022-02-17 | 2022-02-18 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001022 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 7 | 7 | 2022-02-18 | 2022-02-19 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001023 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 12 | 12 | 2022-03-21 | 2022-03-22 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001024 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 12 | 12 | 2022-03-22 | 2022-03-23 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001025 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 12 | 12 | 2022-03-23 | 2022-03-24 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001026 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 17 | 17 | 2022-04-25 | 2022-04-26 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001027 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 17 | 17 | 2022-04-26 | 2022-04-27 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001028 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 17 | 17 | 2022-04-27 | 2022-04-28 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001029 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 17 | 17 | 2022-04-28 | 2022-04-29 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001030 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 17 | 17 | 2022-04-29 | 2022-04-30 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001031 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 18 | 18 | 2022-05-02 | 2022-05-03 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001032 | Hegyeshalom-Ferencváros | > | Herceghalom | Bicske | 2022 | 2022 | 18 | 18 | 2022-05-02 | 2022-05-03 | 22:00 | 4:50 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001033 | Hegyeshalom-Ferencváros | < | Herceghalom | Bicske | 2022 | 2022 | 18 | 18 | 2022-05-03 | 2022-05-03 | 1:00 | 3:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001034 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 18 | 18 | 2022-05-03 | 2022-05-04 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001035 | Hegyeshalom-Ferencváros | > | Herceghalom | Bicske | 2022 | 2022 | 18 | 18 | 2022-05-03 | 2022-05-04 | 22:00 | 4:50 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001036 | Hegyeshalom-Ferencváros | <> | Herceghalom | Bicske | 2022 | 2022 | 18 | 18 | 2022-05-04 | 2022-05-04 | 1:00 | 3:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506001037 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 18 | 18 | 2022-05-04 | 2022-05-05 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001038 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 18 | 18 | 2022-05-05 | 2022-05-06 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001039 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 18 | 18 | 2022-05-06 | 2022-05-07 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001040 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 19 | 19 | 2022-05-09 | 2022-05-10 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001041 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 19 | 19 | 2022-05-10 | 2022-05-11 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001042 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 19 | 19 | 2022-05-11 | 2022-05-12 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001043 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 19 | 19 | 2022-05-12 | 2022-05-13 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001044 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 19 | 19 | 2022-05-13 | 2022-05-14 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001045 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 20 | 20 | 2022-05-16 | 2022-05-17 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001046 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 20 | 20 | 2022-05-17 | 2022-05-18 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001047 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 20 | 20 | 2022-05-18 | 2022-05-19 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001048 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 20 | 20 | 2022-05-19 | 2022-05-20 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001049 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 20 | 20 | 2022-05-20 | 2022-05-21 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001050 | Hegyeshalom-Ferencváros | < | Herceghalom | Bicske | 2022 | 2022 | 20 | 21 | 2022-05-22 | 2022-05-23 | 0:10 | 4:20 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001051 | Hegyeshalom-Ferencváros | > | Tatabánya | Tata | 2022 | 2022 | 21 | 21 | 2022-05-28 | 2022-05-29 | 0:00 | 3:50 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001052 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 24 | 24 | 2022-06-14 | 2022-06-15 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001053 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 24 | 24 | 2022-06-15 | 2022-06-16 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001054 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 24 | 24 | 2022-06-16 | 2022-06-17 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001055 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 26 | 26 | 2022-06-27 | 2022-06-28 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001056 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 26 | 26 | 2022-06-28 | 2022-06-29 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001057 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 27 | 30 | 2022-07-08 | 2022-07-31 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001058 | Hegyeshalom-Ferencváros | > | Ferencváros | Kelenföld | 2022 | 2022 | 27 | 27 | 2022-07-09 | 2022-07-09 | 22:00 | 4:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001059 | Hegyeshalom-Ferencváros | > | Ferencváros | Kelenföld | 2022 | 2022 | 27 | 27 | 2022-07-10 | 2022-07-10 | 0:30 | 4:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001060 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 30 | 30 | 2022-07-31 | 2022-07-31 | 5:30 | 21:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001061 | Hegyeshalom-Ferencváros | > | Ferencváros | Kelenföld | 2022 | 2022 | 30 | 33 | 2022-07-31 | 2022-08-15 | 22:00 | 5:30 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001057 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 27 | 30 | 2022-07-11 | 2022-08-03 | 5:30 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506001058 | Hegyeshalom-Ferencváros | > | Ferencváros | Kelenföld | 2022 | 2022 | 27 | 27 | 2022-07-12 | 2022-07-12 | 0:30 | 4:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506001059 | Hegyeshalom-Ferencváros | > | Ferencváros | Kelenföld | 2022 | 2022 | 27 | 27 | 2022-07-13 | 2022-07-13 | 0:30 | 4:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506001060 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 30 | 30 | 2022-08-03 | 2022-08-03 | 5:30 | 21:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506001061 | Hegyeshalom-Ferencváros | > | Ferencváros | Kelenföld | 2022 | 2022 | 30 | 33 | 2022-08-03 | 2022-08-19 | 21:30 | 5:30 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506001062 | Hegyeshalom-Ferencváros | < | Ferencváros | Kelenföld | 2022 | 2022 | 35 | 35 | 2022-09-01 | 2022-09-02 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001063 | Hegyeshalom-Ferencváros | > | Ferencváros | Kelenföld | 2022 | 2022 | 35 | 35 | 2022-09-02 | 2022-09-03 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001064 | Hegyeshalom-Ferencváros | > | Ferencváros | Kelenföld | 2022 | 2022 | 35 | 35 | 2022-09-03 | 2022-09-04 | 22:00 | 5:30 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001065 | Hegyeshalom-Ferencváros | < | Budapest-Kelenföld | Budaörs | 2022 | 2022 | 36 | 37 | 2022-09-09 | 2022-09-12 | 22:00 | 5:00 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001066 | Hegyeshalom-Ferencváros | < | Budapest-Kelenföld | Budaörs | 2022 | 2022 | 37 | 38 | 2022-09-16 | 2022-09-19 | 22:00 | 5:00 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506001067 | Hegyeshalom-Ferencváros | > | Komárom | Ács | 2022 | 2022 | 40 | 41 | 2022-10-07 | 2022-10-10 | 22:00 | 4:00 | continuous closure | Night | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506010001 | Celldömölk-Győr | <> | Győrszabadhegy elágazás | Győrszemere | 2022 | 2022 | 11 | 11 | 2022-03-20 | 2022-03-20 | 6:00 | 14:00 | continuous closure | Day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506010002 | Celldömölk-Győr | <> | Pápa | Celldömölk | 2022 | 2022 | 38 | 38 | 2022-09-19 | 2022-09-20 | 22:45 | 4:35 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506010003 | Celldömölk-Győr | <> | Pápa | Celldömölk | 2022 | 2022 | 38 | 38 | 2022-09-20 | 2022-09-21 | 22:45 | 4:35 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506010004 | Celldömölk-Győr | <> | Pápa | Celldömölk | 2022 | 2022 | 38 | 38 | 2022-09-21 | 2022-09-22 | 22:45 | 4:35 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506010005 | Celldömölk-Győr | <> | Győrszabadhegy | Győrszemere | 2022 | 2022 | 38 | 38 | 2022-09-22 | 2022-09-23 | 23:10 | 4:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506010006 | Celldömölk-Győr | <> | Győrszemere | Gyömöre | 2022 | 2022 | 38 | 38 | 2022-09-23 | 2022-09-24 | 23:10 | 4:20 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506017001 | Gyékényes-Zalaszentiván | <> | Újudvar | Nagykanizsa | 2022 | 2022 | 14 | 14 | 2022-04-09 | 2022-04-10 | 19:30 | 6:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506017002 | Gyékényes-Zalaszentiván | <> | Újudvar | Nagykanizsa | 2022 | 2022 | 14 | 15 | 2022-04-10 | 2022-04-11 | 21:30 | 6:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506017003 | Gyékényes-Zalaszentiván | <> | Újudvar | Nagykanizsa | 2022 | 2022 | 15 | 15 | 2022-04-11 | 2022-04-12 | 21:30 | 6:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506017004 | Gyékényes-Zalaszentiván | <> | Gelse | Újudvar | 2022 | 2022 | 15 | 15 | 2022-04-11 | 2022-04-12 | 21:50 | 6:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506017005 | Gyékényes-Zalaszentiván | <> | Újudvar | Nagykanizsa | 2022 | 2022 | 15 | 15 | 2022-04-12 | 2022-04-13 | 21:30 | 6:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506017006 | Gyékényes-Zalaszentiván | <> | Gelse | Újudvar | 2022 | 2022 | 15 | 15 | 2022-04-12 | 2022-04-13 | 21:50 | 6:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506017007 | Gyékényes-Zalaszentiván | <> | Újudvar | Nagykanizsa | 2022 | 2022 | 15 | 15 | 2022-04-13 | 2022-04-14 | 21:30 | 6:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506017008 | Gyékényes-Zalaszentiván | <> | Zalaszentiván | Nagykapornak | 2022 | 2022 | 16 | 18 | 2022-04-19 | 2022-05-03 | 4:00 | 23:59 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506017009 | Gyékényes-Zalaszentiván | <> | Zalaszentiván | Nagykapornak | 2022 | 2022 | 36 | 36 | 2022-09-05 | 2022-09-06 | 22:10 | 3:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506020001 | Murakeresztúr-Székesfehérvár | <> | Székesfehérvár | Várpalota | 2022 | 2022 | 11 | 11 | 2022-03-18 | 2022-03-20 | 0:00 | 23:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506020002 | Murakeresztúr-Székesfehérvár | <> | Várpalota | Veszprém | 2022 | 2022 | 12 | 13 | 2022-03-21 | 2022-03-28 | 1:30 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506020003 | Murakeresztúr-Székesfehérvár | <> | Ajka | Boba | 2022 | 2022 | 13 | 13 | 2022-03-29 | 2022-03-30 | 4:00 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506020004 | Murakeresztúr-Székesfehérvár | <> | Celldömölk | Porpác | 2022 | 2022 | 13 | 13 | 2022-03-31 | 2022-04-03 | 0:00 | 4:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506020005 | Murakeresztúr-Székesfehérvár | <> | Veszprém | Ajka | 2022 | 2022 | 24 | 34 | 2022-06-18 | 2022-08-28 | 0:00 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 550625001 | Hodos-Boba | <> | Andráshida elágazás Zalaszentiván elág. | Andráshida Andráshida elágazás | 2022 | 2022 | 35 | 35 | 2022-09-02 | 2022-09-04 | 5:20 | 33:20 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 550625002 | Hodos-Boba | <> | Zalaszentiván | Zalaegerszeg; Andráshida elág. | 2022 | 2022 | 35 | 35 | 2022-09-02 | 2022-09-03 | 5:45 | 7:25 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 550625003 | Hodos-Boba | <> | Zalaszentiván | Zalaegerszeg; Andráshida elág. | 2022 | 2022 | 35 | 35 | 2022-09-03 | 2022-09-04 | 5:45 | 7:25 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 550625004 | Hodos-Boba | <> | Zalaszentiván | Zalaegerszeg; Andráshida elág. | 2022 | 2022 | 35 | 36 | 2022-09-04 | 2022-09-05 | 5:45 | 7:25 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 550625005 | Hodos-Boba | <> | Pankasz mrh. | Őriszentpéter | 2022 | 2022 | 36 | 36 | 2022-09-05 | 2022-09-06 | 4:50 | 7:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 550625006 | Hodos-Boba | <> | Zalaszentiván | Zalaegerszeg; Andráshida elág. | 2022 | 2022 | 36 | 36 | 2022-09-05 | 2022-09-06 | 3:00 | 4:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 550625007 | Hodos-Boba | <> | Andráshida | Őriszentpéter | 2022 | 2022 | 36 | 36 | 2022-09-10 | 2022-09-11 | 4:50 | 7:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 550625008 | Hodos-Boba | <> | Zalabér-Batyk | Pókaszepetk | 2022 | 2022 | 36 | 36 | 2022-09-10 | 2022-09-11 | 6:00 | 8:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 550625009 | Hodos-Boba | <> | Zalalövő | Őriszentpéter | 2022 | 2022 | 36 | 37 | 2022-09-11 | 2022-09-12 | 4:50 | 7:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 550625010 | Hodos-Boba | <> | Ukk | Zalabér-Batyk | 2022 | 2022 | 37 | 37 | 2022-09-12 | 2022-09-13 | 4:00 | 6:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 550625011 | Hodos-Boba | <> | Ukk | Zalabér-Batyk | 2022 | 2022 | 37 | 37 | 2022-09-13 | 2022-09-14 | 4:00 | 6:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030001 | Székesfehérvár-Ferencváros | < | Budapest-Kelenföld | Nagytétény | 2022 | 2022 | 1 | 1 | 2022-01-08 | 2022-01-08 | 8:35 | 15:15 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030002 | Székesfehérvár-Ferencváros | < | Budapest-Kelenföld | Nagytétény | 2022 | 2022 | 1 | 1 | 2022-01-09 | 2022-01-09 | 8:35 | 15:15 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030003 | Székesfehérvár-Ferencváros | > | Nagytétény | Tárnok | 2022 | 2022 | 2 | 2 | 2022-01-15 | 2022-01-15 | 8:00 | 15:00 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030004 | Székesfehérvár-Ferencváros | > | Martonvásár | Kápolnásnyék | 2022 | 2022 | 4 | 4 | 2022-01-24 | 2022-01-24 | 8:05 | 15:05 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030005 | Székesfehérvár-Ferencváros | > | Martonvásár | Kápolnásnyék | 2022 | 2022 | 4 | 4 | 2022-01-25 | 2022-01-25 | 8:05 | 15:05 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030006 | Székesfehérvár-Ferencváros | < | Martonvásár | Kápolnásnyék | 2022 | 2022 | 4 | 4 | 2022-01-26 | 2022-01-26 | 8:05 | 15:05 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030007 | Székesfehérvár-Ferencváros | < | Martonvásár | Kápolnásnyék | 2022 | 2022 | 4 | 4 | 2022-01-27 | 2022-01-27 | 8:05 | 15:05 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030008 | Székesfehérvár-Ferencváros | > | Kápolnásnyék | Gárdony | 2022 | 2022 | 4 | 4 | 2022-01-29 | 2022-01-29 | 9:00 | 16:00 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030009 | Székesfehérvár-Ferencváros | > | Kápolnásnyék | Gárdony | 2022 | 2022 | 4 | 4 | 2022-01-30 | 2022-01-30 | 9:00 | 16:00 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030010 | Székesfehérvár-Ferencváros | < | Ódinnyés | Székesfehérvár | 2022 | 2022 | 5 | 5 | 2022-02-05 | 2022-02-05 | 8:50 | 15:50 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030011 | Székesfehérvár-Ferencváros | < | Ódinnyés | Székesfehérvár | 2022 | 2022 | 5 | 5 | 2022-02-06 | 2022-02-06 | 8:50 | 15:50 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030012 | Székesfehérvár-Ferencváros | < | Székesfehérvár | Szabadbattyán | 2022 | 2022 | 6 | 6 | 2022-02-12 | 2022-02-12 | 7:35 | 16:50 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030013 | Székesfehérvár-Ferencváros | < | Székesfehérvár | Szabadbattyán | 2022 | 2022 | 6 | 6 | 2022-02-13 | 2022-02-13 | 7:35 | 16:50 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030014 | Székesfehérvár-Ferencváros | > | Székesfehérvár | Szabadbattyán | 2022 | 2022 | 7 | 7 | 2022-02-19 | 2022-02-19 | 7:35 | 16:50 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030015 | Székesfehérvár-Ferencváros | > | Székesfehérvár | Szabadbattyán | 2022 | 2022 | 7 | 7 | 2022-02-20 | 2022-02-20 | 7:35 | 16:50 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506030016 | Murakeresztúr-Székesfehérvár | <> | Balatonszentgyörgy | Nagykanizsa | 2022 | 2022 | 9 | 9 | 2022-03-01 | 2022-03-01 | 8:50 | 13:50 | continuous closure | Day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030017 | Murakeresztúr-Székesfehérvár | <> | Balatonszentgyörgy | Nagykanizsa | 2022 | 2022 | 9 | 9 | 2022-03-02 | 2022-03-02 | 8:50 | 13:50 | continuous closure | Day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030018 | Murakeresztúr-Székesfehérvár | <> | Balatonszentgyörgy | Nagykanizsa | 2022 | 2022 | 9 | 9 | 2022-03-03 | 2022-03-03 | 8:50 | 13:50 | continuous closure | Day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030019 | Murakeresztúr-Székesfehérvár | <> | Balatonszentgyörgy | Nagykanizsa | 2022 | 2022 | 9 | 9 | 2022-03-04 | 2022-03-04 | 8:50 | 13:50 | continuous closure | Day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030020 | Murakeresztúr-Székesfehérvár | <> | Siófok | Balatonszemes | 2022 | 2022 | 11 | 11 | 2022-03-16 | 2022-03-17 | 21:55 | 5:20 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030021 | Murakeresztúr-Székesfehérvár | <> | Siófok | Balatonszemes | 2022 | 2022 | 11 | 11 | 2022-03-17 | 2022-03-18 | 21:55 | 5:20 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030022 | Murakeresztúr-Székesfehérvár | <> | Siófok | Balatonszemes | 2022 | 2022 | 11 | 11 | 2022-03-18 | 2022-03-19 | 21:55 | 5:20 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030023 | Murakeresztúr-Székesfehérvár | <> | Siófok | Balatonszemes | 2022 | 2022 | 11 | 11 | 2022-03-19 | 2022-03-20 | 21:55 | 5:20 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030024 | Murakeresztúr-Székesfehérvár | <> | Siófok | Balatonboglár | 2022 | 2022 | 11 | 11 | 2022-03-20 | 2022-03-21 | 21:55 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030025 | Murakeresztúr-Székesfehérvár | <> | Balatonszemes | Balatonboglár | 2022 | 2022 | 12 | 12 | 2022-03-21 | 2022-03-22 | 21:35 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030026 | Murakeresztúr-Székesfehérvár | <> | Balatonszemes | Balatonboglár | 2022 | 2022 | 12 | 12 | 2022-03-22 | 2022-03-23 | 21:35 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030027 | Murakeresztúr-Székesfehérvár | <> | Balatonszemes | Balatonboglár | 2022 | 2022 | 12 | 12 | 2022-03-23 | 2022-03-24 | 21:35 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030028 | Murakeresztúr-Székesfehérvár | <> | Balatonszemes | Fonyód | 2022 | 2022 | 12 | 12 | 2022-03-24 | 2022-03-25 | 21:40 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030029 | Murakeresztúr-Székesfehérvár | <> | Balatonboglár | Balatonszentgyörgy | 2022 | 2022 | 12 | 12 | 2022-03-25 | 2022-03-26 | 22:00 | 4:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030030 | Murakeresztúr-Székesfehérvár | <> | Balatonboglár | Balatonszentgyörgy | 2022 | 2022 | 12 | 12 | 2022-03-26 | 2022-03-27 | 22:00 | 4:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030031 | Murakeresztúr-Székesfehérvár | <> | Balatonboglár | Balatonszentgyörgy | 2022 | 2022 | 12 | 12 | 2022-03-27 | 2022-03-28 | 22:00 | 4:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030032 | Murakeresztúr-Székesfehérvár | <> | Balatonboglár | Balatonszentgyörgy | 2022 | 2022 | 13 | 13 | 2022-03-28 | 2022-03-29 | 22:00 | 4:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030033 | Murakeresztúr-Székesfehérvár | <> | Balatonboglár | Balatonszentgyörgy | 2022 | 2022 | 13 | 13 | 2022-03-29 | 2022-03-30 | 22:00 | 4:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030034 | Murakeresztúr-Székesfehérvár | <> | Balatonboglár | Balatonszentgyörgy | 2022 | 2022 | 13 | 13 | 2022-03-30 | 2022-03-31 | 22:00 | 4:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030035 | Murakeresztúr-Székesfehérvár | <> | Balatonboglár | Balatonszentgyörgy | 2022 | 2022 | 13 | 13 | 2022-03-31 | 2022-04-01 | 22:00 | 4:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030036 | Murakeresztúr-Székesfehérvár | <> | Balatonboglár | Balatonszentgyörgy | 2022 | 2022 | 13 | 13 | 2022-04-01 | 2022-04-02 | 22:00 | 4:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030037 | Murakeresztúr-Székesfehérvár | <> | Szabadbattyán | Lepsény | 2022 | 2022 | 13 | 14 | 2022-04-03 | 2022-04-08 | 23:30 | 4:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030037 | Murakeresztúr-Székesfehérvár | <> | Szabadbattyán | Lepsény | 2022 | 2022 | 13 | 14 | 2022-04-03 | 2022-04-09 | 23:30 | 4:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506030038 | Murakeresztúr-Székesfehérvár | <> | Lepsény | Balatonaliga | 2022 | 2022 | 14 | 14 | 2022-04-04 | 2022-04-05 | 23:50 | 4:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030039 | Murakeresztúr-Székesfehérvár | <> | Balatonaliga | Szabadisóstó | 2022 | 2022 | 14 | 14 | 2022-04-05 | 2022-04-06 | 23:50 | 4:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030040 | Murakeresztúr-Székesfehérvár | <> | Szabadbattyán | Lepsény | 2022 | 2022 | 17 | 17 | 2022-04-26 | 2022-04-27 | 23:30 | 4:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506030041 | Murakeresztúr-Székesfehérvár | <> | Balatonszentgyörgy | Nagykanizsa | 2022 | 2022 | 41 | 42 | 2022-10-10 | 2022-10-21 | 0:00 | 47:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040001 | Pusztaszabolcs-Ferencváros | > | Százhalombatta | Dunai Finomító | 2022 | 2022 | 6 | 6 | 2022-02-07 | 2022-02-07 | 8:00 | 14:00 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506040002 | Pusztaszabolcs-Ferencváros | < | Százhalombatta | Dunai Finomító | 2022 | 2022 | 6 | 6 | 2022-02-08 | 2022-02-08 | 8:00 | 14:00 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506040003 | Pusztaszabolcs-Ferencváros | > | Dunai Finomító | Ercsi | 2022 | 2022 | 6 | 6 | 2022-02-09 | 2022-02-09 | 8:00 | 14:00 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506040004 | Pusztaszabolcs-Ferencváros | > | Dunai Finomító | Ercsi | 2022 | 2022 | 6 | 6 | 2022-02-10 | 2022-02-10 | 8:00 | 14:00 | continuous closure | Day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2021-10-08
MAV | 5506040005 | Dombovár-Pusztaszabolcs | <> | Szakály-Hőgyész | Dombóvár | 2022 | 2022 | 16 | 16 | 2022-04-19 | 2022-04-20 | 0:00 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040006 | Dombovár-Pusztaszabolcs | <> | Simontornya | Szakály-Hőgyész | 2022 | 2022 | 16 | 16 | 2022-04-21 | 2022-04-25 | 0:00 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040007 | Dombovár-Pusztaszabolcs | <> | Szakály-Hőgyész | Kurd | 2022 | 2022 | 16 | 16 | 2022-04-21 | 2022-04-22 | 22:00 | 3:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040008 | Dombovár-Pusztaszabolcs | <> | Rétszilas | Simontornya | 2022 | 2022 | 16 | 16 | 2022-04-22 | 2022-04-23 | 22:45 | 3:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040009 | Dombovár-Pusztaszabolcs | <> | Pusztaszabolcs | Sárosd | 2022 | 2022 | 21 | 21 | 2022-05-23 | 2022-05-24 | 22:15 | 3:35 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040010 | Dombovár-Pusztaszabolcs | <> | Szabadegyháza | Nagylók | 2022 | 2022 | 21 | 21 | 2022-05-24 | 2022-05-25 | 22:30 | 3:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040011 | Dombovár-Pusztaszabolcs | <> | Sárosd | Nagylók | 2022 | 2022 | 21 | 21 | 2022-05-25 | 2022-05-26 | 22:30 | 3:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040012 | Dombovár-Pusztaszabolcs | <> | Nagylók | Sárbogárd | 2022 | 2022 | 21 | 21 | 2022-05-26 | 2022-05-27 | 22:30 | 3:20 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040013 | Dombovár-Pusztaszabolcs | <> | Sárbogárd | Rétszilas | 2022 | 2022 | 22 | 22 | 2022-05-30 | 2022-05-31 | 22:40 | 3:15 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040014 | Dombovár-Pusztaszabolcs | <> | Pusztaszabolcs | Sárosd | 2022 | 2022 | 35 | 35 | 2022-08-29 | 2022-08-30 | 21:20 | 6:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040015 | Dombovár-Pusztaszabolcs | <> | Szabadegyháza | Sárbogárd | 2022 | 2022 | 35 | 35 | 2022-08-30 | 2022-08-31 | 21:15 | 5:50 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040016 | Dombovár-Pusztaszabolcs | <> | Nagylók | Sárbogárd | 2022 | 2022 | 35 | 35 | 2022-08-31 | 2022-09-01 | 21:05 | 4:50 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040017 | Dombovár-Pusztaszabolcs | <> | Sárbogárd | Simontornya | 2022 | 2022 | 35 | 35 | 2022-08-31 | 2022-09-01 | 21:15 | 6:20 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040018 | Dombovár-Pusztaszabolcs | <> | Sárbogárd | Simontornya | 2022 | 2022 | 35 | 35 | 2022-09-01 | 2022-09-02 | 21:15 | 6:20 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040019 | Dombovár-Pusztaszabolcs | <> | Sárbogárd | Pincehely | 2022 | 2022 | 35 | 35 | 2022-09-02 | 2022-09-03 | 21:20 | 6:20 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040020 | Dombovár-Pusztaszabolcs | <> | Simontornya | Keszőhidegkút-Gyönk | 2022 | 2022 | 36 | 36 | 2022-09-05 | 2022-09-06 | 21:25 | 6:25 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040021 | Dombovár-Pusztaszabolcs | <> | Pincehely | Szakály-Hőgyész | 2022 | 2022 | 36 | 36 | 2022-09-06 | 2022-09-07 | 21:35 | 6:20 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040022 | Dombovár-Pusztaszabolcs | <> | Keszőhidegkút-Gyönk | Kurd | 2022 | 2022 | 36 | 36 | 2022-09-07 | 2022-09-08 | 21:40 | 6:15 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040023 | Dombovár-Pusztaszabolcs | <> | Szakály-Hőgyész | Dombóvár | 2022 | 2022 | 36 | 36 | 2022-09-08 | 2022-09-09 | 21:50 | 6:05 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040024 | Dombovár-Pusztaszabolcs | <> | Kurd | Dombóvár | 2022 | 2022 | 36 | 36 | 2022-09-09 | 2022-09-10 | 21:50 | 6:05 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506040025 | Dombovár-Pusztaszabolcs | <> | Kurd | Dombóvár | 2022 | 2022 | 36 | 36 | 2022-09-10 | 2022-09-11 | 21:55 | 6:05 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041001 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 18 | 18 | 2022-05-02 | 2022-05-03 | 22:30 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041002 | Gyékényes-Dombovár | <> | Kaposvár | Jákó-Nagybajom | 2022 | 2022 | 18 | 18 | 2022-05-03 | 2022-05-03 | 0:00 | 3:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041003 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 18 | 18 | 2022-05-03 | 2022-05-04 | 22:30 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041004 | Gyékényes-Dombovár | <> | Kaposvár | Jákó-Nagybajom | 2022 | 2022 | 18 | 18 | 2022-05-04 | 2022-05-04 | 0:00 | 3:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041005 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 18 | 18 | 2022-05-04 | 2022-05-05 | 22:30 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041006 | Gyékényes-Dombovár | <> | Kaposvár | Jákó-Nagybajom | 2022 | 2022 | 18 | 18 | 2022-05-05 | 2022-05-05 | 0:00 | 3:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041007 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 18 | 18 | 2022-05-05 | 2022-05-06 | 22:30 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041008 | Gyékényes-Dombovár | <> | Kaposvár | Jákó-Nagybajom | 2022 | 2022 | 18 | 18 | 2022-05-06 | 2022-05-06 | 0:00 | 3:30 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041009 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 18 | 18 | 2022-05-06 | 2022-05-07 | 22:30 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041010 | Gyékényes-Dombovár | <> | Jákó-Nagybajom | Somogyszob | 2022 | 2022 | 18 | 18 | 2022-05-06 | 2022-05-07 | 23:35 | 4:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041011 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 18 | 18 | 2022-05-07 | 2022-05-08 | 22:30 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041012 | Gyékényes-Dombovár | <> | Jákó-Nagybajom | Somogyszob | 2022 | 2022 | 18 | 18 | 2022-05-07 | 2022-05-08 | 23:35 | 4:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041013 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 18 | 19 | 2022-05-08 | 2022-05-09 | 22:30 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041014 | Gyékényes-Dombovár | <> | Jákó-Nagybajom | Somogyszob | 2022 | 2022 | 18 | 19 | 2022-05-08 | 2022-05-09 | 23:35 | 4:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041015 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 19 | 19 | 2022-05-09 | 2022-05-10 | 22:30 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041016 | Gyékényes-Dombovár | <> | Jákó-Nagybajom | Somogyszob | 2022 | 2022 | 19 | 19 | 2022-05-09 | 2022-05-10 | 23:35 | 4:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041017 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 19 | 19 | 2022-05-10 | 2022-05-11 | 22:30 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041018 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 19 | 19 | 2022-05-11 | 2022-05-12 | 22:30 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041019 | Gyékényes-Dombovár | <> | Jákó-Nagybajom | Somogyszob | 2022 | 2022 | 19 | 19 | 2022-05-11 | 2022-05-12 | 23:35 | 4:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041020 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 19 | 19 | 2022-05-12 | 2022-05-13 | 22:30 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041021 | Gyékényes-Dombovár | <> | Somogyszob | Gyékényes | 2022 | 2022 | 21 | 21 | 2022-05-23 | 2022-05-24 | 20:45 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041022 | Gyékényes-Dombovár | <> | Somogyszob | Gyékényes | 2022 | 2022 | 21 | 21 | 2022-05-24 | 2022-05-25 | 20:45 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041023 | Gyékényes-Dombovár | <> | Somogyszob | Gyékényes | 2022 | 2022 | 21 | 21 | 2022-05-25 | 2022-05-26 | 20:45 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041024 | Gyékényes-Dombovár | <> | Somogyszob | Gyékényes | 2022 | 2022 | 21 | 21 | 2022-05-26 | 2022-05-27 | 20:45 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041025 | Gyékényes-Dombovár | <> | Somogyszob | Gyékényes | 2022 | 2022 | 21 | 21 | 2022-05-27 | 2022-05-28 | 20:45 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041026 | Gyékényes-Dombovár | <> | Somogyszob | Gyékényes | 2022 | 2022 | 21 | 21 | 2022-05-28 | 2022-05-29 | 20:45 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041027 | Gyékényes-Dombovár | <> | Somogyszob | Gyékényes | 2022 | 2022 | 21 | 22 | 2022-05-29 | 2022-05-30 | 20:45 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041028 | Gyékényes-Dombovár | <> | Somogyszob | Gyékényes | 2022 | 2022 | 22 | 22 | 2022-05-30 | 2022-05-31 | 20:45 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-10-08
MAV | 5506041029 | Gyékényes-Dombovár | <> | Somogyszob | Gyékényes | 2022 | 2022 | 22 | 22 | 2022-05-31 | 2022-06-01 | 20:45 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506041030 | Gyékényes-Dombovár | <> | Jákó-Nagybajom | Somogyszob | 2022 | 2022 | 18 | 18 | 2022-05-06 | 2022-05-07 | 23:40 | 4:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506041031 | Gyékényes-Dombovár | <> | Jákó-Nagybajom | Somogyszob | 2022 | 2022 | 18 | 18 | 2022-05-07 | 2022-05-08 | 23:40 | 4:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506041032 | Gyékényes-Dombovár | <> | Jákó-Nagybajom | Somogyszob | 2022 | 2022 | 18 | 19 | 2022-05-08 | 2022-05-09 | 23:40 | 4:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506041033 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 19 | 19 | 2022-05-13 | 2022-05-14 | 22:35 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506041034 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 19 | 19 | 2022-05-14 | 2022-05-15 | 22:35 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506041035 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 19 | 20 | 2022-05-15 | 2022-05-16 | 22:35 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506041036 | Gyékényes-Dombovár | <> | Dombóvár | Kaposvár | 2022 | 2022 | 20 | 20 | 2022-05-16 | 2022-05-17 | 22:35 | 5:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506041037 | Gyékényes-Dombovár | <> | Somogyszob | Gyékényes | 2022 | 2022 | 21 | 21 | 2022-05-24 | 2022-05-29 | 0:05 | 22:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506150001 | Ferencváros-Kelebia | <> | Soroksár | Kiskunhalas | 2022 | 2022 | 5 | 49 | 2022-02-01 | 2022-12-10 | 0:00 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506150002 | Ferencváros-Kelebia | <> | Kiskunhalas | Kelebia | 2022 | 2022 | 5 | 49 | 2022-02-01 | 2022-12-10 | 0:00 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506150003 | Ferencváros-Kelebia | <> | Délegyháza | Kiskunhalas | 2022 | 2022 | 5 | 17 | 2022-02-01 | 2022-04-30 | 0:00 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506150004 | Ferencváros-Kelebia | <> | Soroksár | Kiskunhalas | 2022 | 2022 | 17 | 49 | 2022-05-01 | 2022-12-10 | 0:00 | 23:59 | [15 empty] | 2022-03-20
MAV | 5506150005 | Ferencváros-Kelebia | <> | Kiskunhalas | Kelebia | 2022 | 2022 | 5 | 30 | 2022-02-01 | 2022-07-31 | 7:00 | 19:00 | periodical continous | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506150006 | Ferencváros-Kelebia | <> | Kiskunhalas | Kelebia | 2022 | 2022 | 31 | 49 | 2022-08-01 | 2022-12-10 | 8:00 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506150001 | Ferencváros-Kelebia | <> | Soroksár | Kiskunhalas | 2022 | 2023 | 50 | 49 | 2022-12-11 | 2023-12-09 | 0:00 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506150002 | Ferencváros-Kelebia | <> | Kiskunhalas | Kelebia | 2022 | 2023 | 50 | 49 | 2022-12-11 | 2023-12-09 | 0:00 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506010001 | Celldömölk-Győr | <> | Mezőlak | Vinár | 2023 | 2023 | 9 | 9 | 2023-02-27 | 2023-02-27 | 8:20 | 15:40 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506010002 | Celldömölk-Győr | <> | Mezőlak | Vinár | 2023 | 2023 | 9 | 9 | 2023-02-28 | 2023-02-28 | 8:20 | 15:40 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506010003 | Celldömölk-Győr | <> | Mezőlak | Vinár | 2023 | 2023 | 9 | 9 | 2023-03-01 | 2023-03-01 | 8:20 | 15:40 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506010004 | Celldömölk-Győr | <> | Győrszabadhegy-elágazás | Pápa | 2023 | 2023 | 39 | 40 | 2023-09-25 | 2023-10-06 | 0:00 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506010005 | Celldömölk-Győr | <> | Ménfőcsanak | Gyömöre | 2023 | 2023 | 43 | 43 | 2023-10-24 | 2023-10-25 | 23:10 | 4:20 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506010006 | Celldömölk-Győr | <> | Vinár | Celldömölk | 2023 | 2023 | 43 | 43 | 2023-10-25 | 2023-10-26 | 23:00 | 4:35 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506010007 | Celldömölk-Győr | <> | Vinár | Celldömölk | 2023 | 2023 | 43 | 43 | 2023-10-26 | 2023-10-27 | 23:00 | 4:35 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506025001 | Hodos-Boba | <> | Zalalövő | Zalacséb-Salomvár | 2023 | 2023 | 16 | 16 | 2023-04-17 | 2023-04-18 | 23:00 | 5:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506025001 | Hodos-Boba | <> | Pókaszepetk | Zalaszentiván | 2023 | 2023 | 16 | 16 | 2023-04-18 | 2023-04-19 | 23:35 | 3:40 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506025001 | Hodos-Boba | <> | Andráshida-elágazás | Zalacséb-Salomvár | 2023 | 2023 | 16 | 16 | 2023-04-19 | 2023-04-20 | 21:40 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506025001 | Hodos-Boba | <> | Andráshida-elágazás | Zalacséb-Salomvár | 2023 | 2023 | 16 | 16 | 2023-04-20 | 2023-04-21 | 21:40 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506025001 | Hodos-Boba | <> | Andráshida-elágazás | Zalacséb-Salomvár | 2023 | 2023 | 16 | 16 | 2023-04-21 | 2023-04-22 | 21:40 | 4:55 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506025001 | Hodos-Boba | <> | Zalalövő | Őriszentpéter | 2023 | 2023 | 16 | 16 | 2023-04-22 | 2023-04-22 | 1:20 | 5:20 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506025001 | Hodos-Boba | <> | Zalaszentiván elágazás | Zalaegerszeg | 2023 | 2023 | 16 | 16 | 2023-04-22 | 2023-04-23 | 22:10 | 4:10 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506025001 | Hodos-Boba | <> | Boba | Ukk | 2023 | 2023 | 16 | 17 | 2023-04-23 | 2023-04-24 | 22:35 | 4:50 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506025001 | Hodos-Boba | <> | Boba | Ukk | 2023 | 2023 | 17 | 17 | 2023-04-24 | 2023-04-25 | 22:35 | 4:50 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506025001 | Hodos-Boba | <> | Kerta | Boba / Jánosházai elágazás | 2023 | 2023 | 17 | 17 | 2023-04-25 | 2023-04-26 | 23:20 | 2:20 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2021-12-02
MAV | 5506025001 | Hodos-Boba | <> | Boba |  | 2023 | 2023 | 17 | 17 | 2023-04-25 | 2023-04-26 | 23:20 | 2:20 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary!
MAV | 5506025001 | Hodos-Boba | <> | Zalaszentiván | Zalaszegerszeg | 2023 | 2023 | 17 | 17 | 2023-04-27 | 2023-04-28 | 22:15 | 4:15 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary!
MAV | 5506025001 | Hodos-Boba | <> | Zalaszentiván | Zalaszegerszeg | 2023 | 2023 | 17 | 17 | 2023-04-28 | 2023-04-29 | 22:15 | 2:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary!
MAV | 5506025001 | Hodos-Boba | <> | Zalaszegerszeg | Andráshida | 2023 | 2023 | 17 | 17 | 2023-04-29 | 2023-04-29 | 2:00 | 6:00 | continuous closure | Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary!
MAV | 5506025001 | Hodos-Boba | <> | Ukk | Zalabér-Batyk | 2023 | 2023 | 31 | 35 | 2023-08-01 | 2023-08-28 | 0:00 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary!
MAV | 5506080001 | Miskolc-Nyíregyháza | <> | Mezőzombor | Nyíregyháza | 2022 | 2022 | 20 | 22 | 2022-05-16 | 2022-05-31 | 18:40 | 5:20 | continuous closure | All Night | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080002 | Miskolc-Nyíregyháza | < | Miskolc | Felsőzsolca | 2022 | 2022 | 45 | 46 | 2022-11-07 | 2022-11-15 | 0:00 | 23:59 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080003 | Miskolc-Nyíregyháza | > | Miskolc | Felsőzsolca | 2022 | 2022 | 46 | 47 | 2022-11-16 | 2022-11-22 | 0:00 | 23:59 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080004 | Nyíregyháza-Záhony | < | Nyíregyháza | Sóstóhegy | 2022 | 2022 | 39 | 39 | 2022-09-28 | 2022-09-30 | 0:00 | 23:59 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080004 | Nyíregyháza-Záhony | <> | Nyíregyháza-Északi kitérő | Sóstóhegy elágazás | 2022 | 2022 | 39 | 39 | 2022-09-28 | 2022-09-30 | 0:00 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080005 | Nyíregyháza-Záhony | > | Nyíregyháza | Sóstóhegy | 2022 | 2022 | 40 | 40 | 2022-10-03 | 2022-10-09 | 0:00 | 23:59 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080006 | Nyíregyháza-Záhony | <> | Tuzsér | Záhony | 2022 | 2022 | 21 | 21 | 2022-05-24 | 2022-05-25 | 6:05 | 11:10 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080007 | Nyíregyháza-Záhony | < | Demecser | Pátroha | 2022 | 2022 | 19 | 19 | 2022-05-09 | 2022-05-11 | 18:00 | 6:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080008 | Nyíregyháza-Záhony | < | Ebes | Debrecen | 2022 | 2022 | 18 | 18 | 2022-05-02 | 2022-05-07 | 22:55 | 4:55 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080009 | Nyíregyháza-Záhony | > | Ebes | Debrecen | 2022 | 2022 | 18 | 19 | 2022-05-06 | 2202-05-11 | 22:55 | 4:55 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080010 | Nyíregyháza-Záhony | > | Ebes | Debrecen | 2022 | 2022 | 19 | 20 | 2022-05-12 | 2022-05-16 | 22:55 | 4:55 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080011 | Nyíregyháza-Záhony | <> | Komoró | Eperjeske-Átrakó | 2022 | 2022 | 20 | 20 | 2022-05-17 | 2022-05-18 | 0:00 | 23:59 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080012 | Nyíregyháza-Záhony | < | Sóstóhegy | Kemecse | 2022 | 2022 | 18 | 18 | 2022-05-02 | 2022-05-03 | 17:00 | 5:30 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080013 | Nyíregyháza-Záhony | > | Sóstóhegy | Kemecse | 2022 | 2022 | 18 | 18 | 2022-05-03 | 2022-05-04 | 17:00 | 5:30 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080014 | Nyíregyháza-Záhony | < | Sóstóhegy | Kemecse | 2022 | 2022 | 18 | 18 | 2022-05-04 | 2022-05-05 | 17:00 | 5:30 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080015 | Nyíregyháza-Záhony | > | Sóstóhegy | Kemecse | 2022 | 2022 | 18 | 18 | 2022-05-05 | 2022-05-06 | 17:00 | 5:30 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080016 | Nyíregyháza-Záhony | < | Sóstóhegy | Kemecse | 2022 | 2022 | 18 | 18 | 2022-05-06 | 2022-05-07 | 17:00 | 5:30 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080017 | Nyíregyháza-Záhony | > | Sóstóhegy | Kemecse | 2022 | 2022 | 18 | 18 | 2022-05-06 | 2022-05-07 | 22:00 | 5:30 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080018 | Budapest-Cegléd-Szolnok | > | Pestszentlőrinc | Vecsés | 2022 | 2022 | 24 | 25 | 2022-06-17 | 2022-06-20 | 23:00:00 | 04:00:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080019 | Budapest-Cegléd-Szolnok | < | Pestszentlőrinc | Vecsés | 2022 | 2022 | 24 | 24 | 2022-06-17 | 2022-06-18 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080020 | Budapest-Cegléd-Szolnok | < | Pestszentlőrinc | Vecsés | 2022 | 2022 | 24 | 24 | 2022-06-18 | 2022-06-19 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080021 | Budapest-Cegléd-Szolnok | < | Pestszentlőrinc | Vecsés | 2022 | 2022 | 24 | 25 | 2022-06-19 | 2022-06-20 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080022 | Budapest-Cegléd-Szolnok | > | Vecsés | Üllő | 2022 | 2022 | 25 | 25 | 2022-06-20 | 2022-06-24 | 04:00:00 | 23:00:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080023 | Budapest-Cegléd-Szolnok | <> | Pestszentlőrinc | Üllő | 2022 | 2022 | 25 | 25 | 2022-06-20 | 2022-06-21 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080024 | Budapest-Cegléd-Szolnok | <> | Pestszentlőrinc | Üllő | 2022 | 2022 | 25 | 25 | 2022-06-21 | 2022-06-22 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080025 | Budapest-Cegléd-Szolnok | <> | Pestszentlőrinc | Üllő | 2022 | 2022 | 25 | 25 | 2022-06-22 | 2022-06-23 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080026 | Budapest-Cegléd-Szolnok | <> | Pestszentlőrinc | Üllő | 2022 | 2022 | 25 | 25 | 2022-06-23 | 2022-06-24 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080027 | Budapest-Cegléd-Szolnok | > | Pestszentlőrinc | Üllő | 2022 | 2022 | 25 | 26 | 2022-06-24 | 2022-06-27 | 23:00:00 | 04:00:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080028 | Budapest-Cegléd-Szolnok | < | Pestszentlőrinc | Üllő | 2022 | 2022 | 25 | 25 | 2022-06-24 | 2022-06-25 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080029 | Budapest-Cegléd-Szolnok | < | Pestszentlőrinc | Üllő | 2022 | 2022 | 25 | 25 | 2022-06-25 | 2022-06-26 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080030 | Budapest-Cegléd-Szolnok | < | Pestszentlőrinc | Üllő | 2022 | 2022 | 25 | 26 | 2022-06-26 | 2022-06-27 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080031 | Budapest-Cegléd-Szolnok | > | Vecsés | Üllő | 2022 | 2022 | 26 | 26 | 2022-06-27 | 2022-06-29 | 04:00:00 | 03:40:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080032 | Budapest-Cegléd-Szolnok | <> | Pestszentlőrinc | Üllő | 2022 | 2022 | 26 | 26 | 2022-06-27 | 2022-06-28 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080033 | Budapest-Cegléd-Szolnok | <> | Pestszentlőrinc | Üllő | 2022 | 2022 | 26 | 26 | 2022-06-28 | 2022-06-29 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080034 | Budapest-Cegléd-Szolnok | < | Vecsés | Üllő | 2022 | 2022 | 26 | 26 | 2022-06-29 | 2022-07-01 | 03:40:00 | 23:00:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080035 | Budapest-Cegléd-Szolnok | <> | Pestszentlőrinc | Üllő | 2022 | 2022 | 26 | 26 | 2022-06-29 | 2022-06-30 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080036 | Budapest-Cegléd-Szolnok | <> | Pestszentlőrinc | Üllő | 2022 | 2022 | 26 | 26 | 2022-06-30 | 2022-07-01 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080037 | Budapest-Cegléd-Szolnok | < | Pestszentlőrinc | Üllő | 2022 | 2022 | 26 | 27 | 2022-07-01 | 2022-07-04 | 23:00:00 | 04:00:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080038 | Budapest-Cegléd-Szolnok | > | Pestszentlőrinc | Üllő | 2022 | 2022 | 26 | 26 | 2022-07-01 | 2022-07-02 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080039 | Budapest-Cegléd-Szolnok | > | Pestszentlőrinc | Üllő | 2022 | 2022 | 26 | 26 | 2022-07-02 | 2022-07-03 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080040 | Budapest-Cegléd-Szolnok | > | Pestszentlőrinc | Üllő | 2022 | 2022 | 26 | 27 | 2022-07-03 | 2022-07-04 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080041 | Budapest-Cegléd-Szolnok | < | Vecsés | Üllő | 2022 | 2022 | 27 | 27 | 2022-07-04 | 2022-07-08 | 03:40:00 | 23:00:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080042 | Budapest-Cegléd-Szolnok | <> | Pestszentlőrinc | Üllő | 2022 | 2022 | 27 | 27 | 2022-07-04 | 2022-07-05 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080043 | Budapest-Cegléd-Szolnok | <> | Pestszentlőrinc | Üllő | 2022 | 2022 | 27 | 27 | 2022-07-05 | 2022-07-06 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080044 | Budapest-Cegléd-Szolnok | <> | Pestszentlőrinc | Üllő | 2022 | 2022 | 27 | 27 | 2022-07-06 | 2022-07-07 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080045 | Budapest-Cegléd-Szolnok | <> | Pestszentlőrinc | Üllő | 2022 | 2022 | 27 | 27 | 2022-07-07 | 2022-07-08 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080046 | Budapest-Cegléd-Szolnok | < | Pestszentlőrinc | Üllő | 2022 | 2022 | 27 | 28 | 2022-07-08 | 2022-07-11 | 23:00:00 | 23:00:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080047 | Budapest-Cegléd-Szolnok | > | Pestszentlőrinc | Üllő | 2022 | 2022 | 27 | 27 | 2022-07-08 | 2022-07-09 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080048 | Budapest-Cegléd-Szolnok | > | Pestszentlőrinc | Üllő | 2022 | 2022 | 27 | 27 | 2022-07-09 | 2022-07-10 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080049 | Budapest-Cegléd-Szolnok | > | Pestszentlőrinc | Üllő | 2022 | 2022 | 27 | 28 | 2022-07-10 | 2022-07-11 | 23:50:00 | 03:40:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080050 | Nyíregyháza-Záhony oh | > | Pátroha | Kisvárda | 2022 | 2022 | 29 | 29 | 2022-07-19 | 2022-07-20 | 0:00 | 23:59 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080051 | Nyíregyháza-Záhony oh | < | Pátroha | Kisvárda | 2022 | 2022 | 29 | 29 | 2022-07-21 | 2022-07-22 | 0:00 | 7:00 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080052 | Nyíregyháza-Záhony oh | <> | Záhony | Záhony oh. | 2022 | 2022 | 33 | 33 | 2022-08-15 | 2022-08-15 | 6:15 | 18:15 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080053 | Nyíregyháza-Záhony oh | <> | Záhony | Záhony oh. | 2022 | 2022 | 33 | 33 | 2022-08-17 | 2022-08-17 | 6:15 | 18:15 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080054 | Debrecen-Nyíregyháza | > | Hajdúhadház | Újfehértó | 2022 | 2022 | 37 | 37 | 2022-09-12 | 2022-09-13 | 21:05 | 5:45 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080055 | Debrecen-Nyíregyháza | > | Hajdúhadház | Újfehértó | 2022 | 2022 | 37 | 37 | 2022-09-13 | 2022-09-14 | 21:05 | 5:45 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080056 | Debrecen-Nyíregyháza | < | Hajdúhadház | Újfehértó | 2022 | 2022 | 37 | 37 | 2022-09-14 | 2022-09-15 | 21:05 | 5:45 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080057 | Debrecen-Nyíregyháza | > | Hajdúhadház | Újfehértó | 2022 | 2022 | 37 | 37 | 2022-09-15 | 2022-09-16 | 21:05 | 5:45 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080058 | Debrecen-Nyíregyháza | > | Apafa | Hajdúhadház | 2022 | 2022 | 36 | 36 | 2022-09-05 | 2022-09-06 | 19:30 | 5:50 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080059 | Debrecen-Nyíregyháza | > | Apafa | Hajdúhadház | 2022 | 2022 | 36 | 36 | 2022-09-06 | 2022-09-07 | 19:30 | 5:50 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080060 | Debrecen-Nyíregyháza | < | Apafa | Hajdúhadház | 2022 | 2022 | 36 | 36 | 2022-09-07 | 2022-09-08 | 19:30 | 5:50 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080061 | Debrecen-Nyíregyháza | < | Apafa | Hajdúhadház | 2022 | 2022 | 36 | 36 | 2022-09-08 | 2022-09-09 | 19:30 | 5:50 | continuous closure | All day | Track & Rail |  | X | X | [5 empty] | X |  | Single line operation (closure of one track of a double track line) |  | 2022-03-20
MAV | 5506080062 | Nyíregyháza-Záhony oh | <> | Tuzsér | Záhony | 2022 | 2022 | 37 | 37 | 2022-09-13 | 2022-09-13 | 6:05 | 11:15 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20
MAV | 5506080063 | Nyíregyháza-Záhony oh | <> | Tuzsér | Záhony | 2022 | 2022 | 37 | 37 | 2022-09-14 | 2022-09-14 | 6:05 | 11:15 | continuous closure | All day | Track & Rail | X | [5 empty] | X |  |  |  | Total closure, Train replacement necessary! Re-routing necessary! |  | 2022-03-20